## April 2022 - Indiana
Project Sponsor | KIPDA ID | Funding Source | Project Name | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | Notes
Congestion Mitigation and Air Quality (CMAQ) - MPO Projects
APCD | 370 | CMAQ | KAIRE | Program | Program | Program | Program | Program | Program
Floyd County | 2128 | CMAQ | Charleston Road Complete Streets | R | R |  | C
TARC | 2408 | CMAQ | TARC Cross River Connectors | Program | Operations
Highway Safety Improvement Program (HSIP) - MPO Projects
Clark County | 2549 | HSIP | CR 403 and Stacy Road | PE |  | R | U | C
Surface Transportation Block Grant (STBG) - MPO Projects
Clarksville | 2389 | STBG | Blackiston Mill Road Phase 2 |  | R |  | C
Clarksville | 2393 | STBG | Riverside Drive |  | R | PE | C
Floyd County | 1558 | STBG | Bridge 51 | PE |  |  |  | R |  | C
KIPDA | 56 | STBG | Every Commute Counts (Ticket to ride) | Program | Program | Program | Program | Program | Program
New Albany | 309 | STBG | Mount Tabor (Phase 2) | R C |  |  | PE | U | C
New Albany | 3292 | STBG | E. Main St. State St. to 5th St. | PE | PE | C
Transportation Alternatives (TA) - MPO Projects
Clarksville | 2541 | STBG | Montgomery Ave. / Jeffersonville 9th St. Multimodal |  | PE | RR | C
FTA Flex - MPO Projects
TARC | 3011 | FTA | New Albany Bus Stop ADA Improvements |  |  | TC
TARC | 3012 | FTA | Purchase Vehicles for Mobility on Demand Service |  |  | TC
PL Flex - MPO Projects
Floyd County | 3009 | PL | Floyd County Transit and Multi-Modal Planning Study |  |  | Pl
New Albany | 3010 | PL | State Street Congestion Mitigation Planning Study |  |  | Pl
Phase Legend |  | Progress Legend
D = Design |  | On/Ahead Schedule
PE = Preliminary Engineering |  | Behind Schedule
R = Right of Way |  | Obligated
U = Utilities
C = Construction