## Sheet1
Project | KIPDA ID | STATE ID | Phase | Program | MPO Dedicated Federal Funds | Actual or Estimated Date of Authorization | Remarks
English Station Rd. | 188 | 05-00353.00 | Construction | STBG-MPO | 6408000 | 2023-09-01 | R/W condemnations required. Extensive utility involvement.
KY 1931 | 2214 | 05-00536.00 | Right of Way | STBG-MPO | 1220000 | 2023-09-01 | Railroad involvement. Utility relocation complications.
US 42 | 1271 | 05-00441.00 | Right of Way | STBG-MPO | 180000 | 2023-09-01 | ROW funds to remain available for C & U phases
|  |  | Construction | STBG-MPO | 5020000 | 2023-09-01 | Utility relocation is lower priority for companies
KY 2055 | 3042 | 5-80110.00 | Design | STBG-MPO | 120000 | 2023-07-01 | Awaiting programming document, KIPDA 2023-26 TIP, to be approved
Reconnecting West Louisville to the Ohio Riverfront throughout the Riverside Expressway (I-64) Corridor | 3067 | TBD | Planning | STBG-MPO | 600000 | 2023-07-01 | Awaiting programming document, KIPDA 2023-26 TIP, to be approved
KY 1065 | 436 | TBD | Planning | STBG-MPO | 200000 | 2023-07-01 | Awaiting programming document, KIPDA 2023-26 TIP, to be approved
AB Sawyer Greenway Shared Use Path | 1662 | 5-529.00 | Construction | STBG-MPO | 3464000 | 2023-09-01
Baxter/Bardstown Premium Transportation Corridor - Section 1 | 1353 | ? | Design | STBG-MPO | 177750 | 2023-09-01
Bicycle & Pedestrian Education, Encouragement, Enforcement & Evaluation | 337 | 5-965.15 | Program | STBG-MPO | 120000 | Already Authorized - October 2022
Cannons Lane | 2239 | 5-3212.00 | Construction | STBG-MPO | 1000000 | 2023-04-01
Cooper Chapel Rd. Phase 3 | 223 | 05-00404.01 | Design | STBG-MPO | 45400 | 2023-04-01
|  |  | Right of Way | STBG-MPO | 800000 | 2023-04-02
Hikes Lane Rehabilitation | 2897 | 5-583.00 | Construction | STBG-MPO | 3300000 | Already Authorized - February 2023
I-65 | 224 | 05-00378.10 | Design | STBG-MPO | 265000 | Already Authorized - November 2022
Kentuckiana Air Education | 369 | 5-244.00 | Program | STBG-MPO | 200000 | 2023-08-01
Main Street / Story Avenue Intersection | 2388 | 5-561.00 | Design | STBG-MPO | 25000 | 2023-03-01
Newburg road Sidewalk | 2898 | 05-03041.00 | Construction | TA-MPO | 611000 | 2023-05-01
North Hubbards Ln. | 384 | 5-479.00 | Construction | STBG-MPO | 3740000 | 2023-09-01
Northeast Louisville Loop MET, Section 2 Beckley Station to Bircham Rd. | 2269 | 5-3030.20 | Utilities | STBG-MPO | 280000 | 2023-09-01
|  |  | Construction | STBG-MPO | 1800000
Northeast Louisville Loop MET, Section 4 Beckley Creek Park to Eastwood Cutoff | 2271 | 5-3030.40 | Right of Way | STBG-MPO | 350000 | 2023-04-01
Olmsted Parkways Multi-Use Path System Section 1 | 2622 | 05-03709.00 | Construction | STBG-MPO | 2200000 | 2023-09-01
Olmsted Parkways Multi-Use Path System Section 3 | 2624 | 5-3709.00 | Design | STBG-MPO | 100000 | 2023-05-01
Olmsted Parkways Multi-Use Path System Section 6 | 2627 | 5-506.00 | Design | STBG-MPO | 532435 | 2023-05-01
Olmsted Parkways Multi-Use Path System Section 7 | 2628 | 5-506.00 | Design | STBG-MPO | 416195 | 2023-05-01
Olmsted Parkways Multi-Use Path System Section 8 | 2629 | 5-506.00 | Design | STBG-MPO | 259119 | 2023-05-01
Olmsted Parkways Multi-Use Path System Section 9 | 2630 | 5-506.00 | Design | STBG-MPO | 252251 | 2023-05-01
One-Way Street Conversion to Two-Way Phase 1 | 1809 | 5-470.00 | Utilities | STBG-MPO | 220000 | 2023-09-01
River Road | 163 | 5-91.02 | Construction | CRRSAA-MPO | 5981134 | 2023-11-01 | 2024 | Cost Increase Request: $2,000,000 For a new Utility phase in FFY 2024 New Federal Amount = $2,000,000 New Local Match Amount = $500,000 New Total Cost = $2,500,000
|  |  | Construction | STBG-MPO | 15729715
River Road Multi-Modal Improvements | 2540 | 5-3217.00 | Construction | TA-MPO | 1413708 | 2023-09-01 |  | Cost Increase Request: $2,000,000 For a new Utility phase in FFY 2024 New Federal Amount = $2,000,000 New Local Match Amount = $500,000 New Total Cost = $2,500,001
Stony Brook Drive Sidewalk Connector | 2594 | 05-571.00 | Construction | STBG-MPO | 300000 | 2023-06-01
Bus Stop Improvements | 1500 | 05-581.00 | C | 2023 | STBG-MPO | 750000 | 2023-06-30 | Ongoing project. Preparing plans for CY 2023.
Wetherby Avenue | 2229 | 05-03222.00 | ROW | 2023 | TA | 107659 | still waiting on KYTC
|  |  | ROW (CRRSAA) | 2023 | TA | 52341 | still waiting on KYTC
2nd Street / 3rd Street / Museum Drive Intersection and Brandeis Avenue Pedestrian Improvements | 2982 | 5-581 | Design | STBG-MPO | 225000 | 2022-04-26
|  |  | Utilities | STBG-MPO | 1105280 | 2023-06-01
|  |  | Construction | STBG-MPO | 2960000 | 2023-12-01
University of Louisville Pedestrian Improvements - Lighting | 2225 | 05-3218.00 | Construction | STBG-MPO | 359270 | 2023-06-01
University of Louisville Pedestrian Improvements - ADA Curb Cuts & Ramps | 2585 | 05-3220.00 | Construction | STBG-MPO | 350000 | 2023-06-01
KY 329 | 1877 | 05-00542.00 | Utilities | STBG-MPO | 37000 | Estimated date of authorization is September 2023.
|  |  | Construction | STBG-MPO | 2000000 | Estimated date of authorization is September 2023.
KY 393 Trail | 2981 | TBD | Design | STBG-MPO | 222000 | Estimated date of authorization is August 2023.
LaGrange Underpass West of LaGrange | 321 | 05-00434.00 | Design | STBG-MPO | 160000 | Estimated date of authorization is June 2023.
|  |  | Utilities | STBG-MPO | 3895000 | Estimated date of authorization is September 2023.
|  |  | Construction | STBG-MPO | 10500000 | Estimated date of authorization is September 2023.
Oldham County Bicycle & Pedestrian Trail - Old LaGrange Rd. | 2175 | 05-00410.01 | Right of Way | STBG-MPO | 159676 | Estimated date of authorization is July 2023
|  |  | Right of Way | CRRSAA-MPO | 340324 | Estimated date of authorization is July 2023
Historic Multi-Use Trail Segment C | 2479 | 05-03216.00 | Construction | 2023 | STBG-MPO | 2317814 | estimated 10/2023 | Right of Way is waiting on LG&E
|  |  | Construction (CRRSAA) | 2023 | CRRSAA-MPO | 118000 | estimated 10/2023 | Right of Way is waiting on LG&E
|  |  | Construction | 2023 | TA-MPO | 589787 | estimated 10/2023 | Right of Way is waiting on LG&E
Bluegrass Commerce Park Bicycle/Pedestrian Trail Phase II | 2084 | 05-543.00 | Construction | STBG-MPO | 1510000 | 2023-05-01
Galene Drive/Sprowl Road Collector Extension | 3113 | ? | Planning | STBG-MPO | 264000 | 2023-08-01
Good Samaritan Bicycle & Pedestrian Trail Connector | 2082 | 05-486.00 | Construction | STBG-MPO | 1460000 | 2023-09-01
Patti Lane Sidewalk Safety Improvement | 2385 | 5-3219.00 | Construction | TA-MPO | 744344 | authorized February 2023
Ruckriegel Parkway Sidewalk Improvement | 2619 | 5-198.00 | Construction | STBG-MPO | 529008 | 2024-01-01
Watterson Trail Signalized Improvements | 3110 | ? | Design | STBG-MPO | 132000 | 2023-08-01
Watterson Trail Phase 2 | 1583 | 05-00518.00 | Utilities | STBG-MPO | 352000 | authorized November 2022