## Sheet1
Indiana Fall Progress Report Summary
Clark County
Project | KIPDA ID | STATE ID | Phase | Fiscal Year | Program | MPO Dedicated Federal Funds | Actual or Estimated Date of Authorization | Project Phase Status | Progress In Past Quarter
Stacy Road... | 2549 | 1802805 | PE | 2020 | HSIP-MPO | 283500 | 2023-09-19
|  |  | U | 2024 | STBG-MPO | 134029 |  | Federal Funding Not Yet Authorized | Duke is concerned with their guy wires and the forcemain location we are working with Duke to resolve this issue. Also we are working with two property owners to finalize their concerns. | Utitlities hold up may lead to phases not making 2024 deadline
|  |  | C | 2024 | HSIP-MPO | 2147735 | 2023-01-24 | Federal Funding Not Yet Authorized | Construction Letting Scheduled for Jan 18, 2024 |  |  | Potential new letting date of march
Jeff Charlestown Pike Improvements | 3177 | TBD | ROW | 2027 | TA | 765000 |  | Federal Funding Not Yet Authorized | Starting to gather information for property acquitition | In future, this project may be locally funded, and 2027 and 2028 funds may become available. Update coming from Clark County in Spring 2024
|  |  | C | 2028 | CRP | 3300000
Henryville Sidewalk | 3180 | TBD | PE | 2027 | PROTECT | 3229 |  | Federal Funding Not Yet Authorized | No update
|  |  | PE | 2028 | PROTECT | 22109
|  |  | C | 2029 | PROTECT | 520661
Clarksville
Blackiston Mill Road Phase 2 | 2389 | 1700724 | C | 2023 | STBG-MPO | 2108480 | 2023-02-23 | Federal Funding Authorized | Construction is underway. Project is currently on-schedule
Clarksville Montgomery Avenue / Jeffersonville 9th Street Multimodal Improvements | 2541 | 1801597 | C | 2023 | TA-MPO | 688981 | 2023-05-23 | Federal Funding Authorized | Construction is underway. Project is currently on-schedule
|  |  | C | 2023 | CRRSAA | 964459 |  |  | Construction is underway. Project is currently on-schedule
Riverside Drive Reconstruction | 2393 | 1700725 | C | 2023 | STBG-MPO | 134029 | 2023-09-23 | Federal Funding Not Yet Authorized | Letting September 2023
Progress Way Improvements | 3018 | TBD | ROW | 2024 | STBG | 300000 | 2023-10-24 | Federal Funding Authorized | ROW is being surveyed and plans for requiring is underway. |  | Needs to move to 2025
|  |  | U | 2025 | STBG | 700000 | 2023-08-25 | Federal Funding Not Yet Authorized | Future Phase | Likely needs to move to FY27
|  |  | C | 2026 | STBG | 1817926 | 2023-08-26 | Federal Funding Not Yet Authorized | Future Phase
Stansifer Avenue Streetscape Improvements | 3019 | TBD | PE | 2025 | STBG | 323000 | 2023-08-24 | Federal Funding Not Yet Authorized | Future Phase | Likely will need to shift phases out 1 year each. Wait until more sure schedule is discussed by INDOT and Clarksville
|  |  | ROW | 2026 | STBG | 80000 | 2023-08-25 | Federal Funding Not Yet Authorized | Future Phase
|  |  | C | 2027 | STBG | 3597000 | 2023-08-26 | Federal Funding Not Yet Authorized | Future Phase
Floyd County
Bridge 51 (Blackiston Mill Road) Replacement Project | 1558 | 1700788 | ROW | 2024 | STBG-MPO | 1200000 | 2023-12-23 | Federal Funding Not Yet Authorized | Submitted Environmental documentation for approval. Waiting response from INDOT
|  |  | C | 2026 | STBG-MPO | 3606183 | 2023-07-25 | Federal Funding Not Yet Authorized | Waiting for environmental approval to start ROW acquistion
Charlestown Road Corridor Complete Streets | 2128 | 1400550 | ROW | 2023 | CMAQ-MPO | 150000 | Completed | Phase Completed
|  |  | C | 2024 | CMAQ-MPO | 1095942 | 2023-02-23 | Federal Funding Not Yet Authorized | Will be requesting Phasing of Project | Changes scheduled for Amendment 4 | Phase II scheduled for 2026 Estimated Total Project Cost of: $1,842,692
Floyd County Transit and Multi-Modal Planning Study | 3009 | 2100002 | Planning | 2023 | STBG-MPO | 250000 | Completed | Phase Completed
New Albany
Mount Tabor (Phase 2) | 309 | 0710808, 2000188 | PE | 2023 | STBG-MPO | 301760 | 2023-10-22 |  | Our consultant is working on the PE Phase and communicating with us accordingly.
|  |  | U | 2024 | STBG-MPO | 640000 | 2023-11-23
|  |  | C | 2025 | STBG-MPO | 3672000 | 2023-01-25
E. Main Street from State Street Intersection to E. 5th Street Intersection | 2392 | 1700730 | PE | 2023 | STBG-MPO | 34700 | 2023-04-23 |  | This amount has been reimbursed from INDOT so this PO has been expended.
|  |  | C | 2023 | STBG-MPO | 748324 | 2023-01-23 |  | Construction is progressing and nearing completion.
State Street Congestion Mitigation Planning Study | 3010 | 2100002 | Plannning | 2022 | PL-MPO | 240000 | 2023-08-23 |  | This project is complete.
Graybrook Lane Extension | 3102 | TBD | PE | 2025 | STBG | 357109 | TBD |  | The RFP for this project needs finalized.
|  |  | ROW | 2027 | STBG | 439200 | TBD
|  |  | U | 2028 | STBG | 80000 | TBD
|  |  | C | 2029 | STBG | 2074949 | TBD
Intersection of E. Spring St. & Beharrell Ave. | 3136 | TBD | PE | 2025 | HSIP | 252000 | TBD |  | The RFP for this project needs finalized.
|  |  | ROW | 2027 | HSIP | 400000 | TBD
|  |  | C | 2028 | HSIP | 1932000 | TBD