## Sheet1
Kentucky Progress Report Summary Fall 2023
Sponsor | Project | KIPDA ID | STATE ID | Phase | Fiscal Year (2023 - 2026 Only) | Program | MPO Dedicated Federal Funds | Actual or Estimated Date of Authorization | Project Phase Status | Progress Since Last Meeting
Jeffersontown | Bluegrass Commerce Park Bicycle/Pedestrian Trail Phase II | 2084 | 05-543.00 | Construction | 2023 | STBG-MPO | 1510000 | Est. 1/1/2024 | Federal Funding Not Yet Authorized | Completing final D5 comments prior to seeking authorization
Jeffersontown | Galene Drive/Sprowl Road Collector Extension | 3113 | ? | Planning | 2023 | STBG-MPO | 264000 | Est. 5/1/2024 | Federal Funding Not Yet Authorized | This is a new project. Plan to request Planning Funds Dec. 2023
|  |  |  | Design | 2024 | STBG-MPO | 440000
|  |  |  | ROW | 2025 | STBG-MPO | 880000
|  |  |  | Utilities | 2026 | STBG-MPO | 440000
|  |  |  | Construction | 2027 | STBG-MPO | 4400000
Jeffersontown | Good Samaritan Bicycle & Pedestrian Trail Connector | 2082 | 05-486.00 | Construction | 2023 | STBG-MPO | 1460000 | Est. July 2024 | Federal Funding Not Yet Authorized | Working with D5 to re-review orginal approvals post COVID
Jeffersontown | Patti Lane Sidewalk Safety Improvement | 2385 | 5-3219.00 | Construction | 2023 | TA-MPO | 744344 | 2023-01-23 | Federal Funding Authorized | Moving to advertise for Construction Spring 2024
Jeffersontown | Ruckriegel Parkway Sidewalk Improvement | 2619 | 5-198.00 | Construction | 2023 | STBG-MPO | 529008 | Est. July 2024 | Federal Funding Not Yet Authorized | Working with D5 to re-review orginal approvals post COVID
Jeffersontown | Watterson Trail Signalized Improvements | 3110 | ? | Design | 2023 | STBG-MPO | 132000 | Est. Feb. 2024 | Federal Funding Not Yet Authorized | This is a new project. Plan to request Design Spring 20024. Might merge with existing Watterson Trail Streetscape P2 | According to the PMG, the initial design phase of a project must be obligated in the year it was programmed in the TIP
|  |  |  | Construction | 2024 | STBG-MPO | 880000
Jeffersontown | Watterson Trail Phase 2 | 1583 | 05-00518.00 | Utilities | 2023 | STBG-MPO | 352000 | Est. Spring 2024 | Federal Funding Not Yet Authorized | Currently in the R/W Phase. Once complete will seek Utility Phase
|  |  |  | Construction | 2024 | STBG-MPO | 1232000
Jeffersontown | Billtown-Eastvie w Collector Extension | 3111 |  | Design | 2024 | STBG-MPO | 352000 | Est. July 2024 | Federal Funding Not Yet Authorized | This is a new project. Plan to request Design Funds Feb 2024
|  |  |  | Construction | 2026 | STBG-MPO | 660000
Middletown | Wetherby Avenue | 2229 | 05-03222.00 | ROW | 2023 | TA | 107659 | 2023-04-24 | Federal Funding Not Yet Authorized | Still in Design phase working out gas line conflicts. ROW phase not begun yet
|  |  |  | ROW | 2023 | STBG-State | 52341 | 2023-04-24 | Federal Funding Not Yet Authorized | NA - Still in Design phase.
|  |  |  | Utilities | 2024 | TA | 160000 | 2023-04-24 | Federal Funding Not Yet Authorized | NA - Still in Design phase.
|  |  |  | Construction | 2025 | TA | 410569 | 2023-12-24 | Federal Funding Not Yet Authorized | NA - Still in Design phase.
Middletown | Bliss Avenue | 2228 | 05-03221.00 | Utilities | 2024 | TA | 80000 | 2023-04-24 | Federal Funding Not Yet Authorized | NA - Still in Design phase.
|  |  |  | Construction | 2025 | TA | 400000 | 2023-12-24 |  | NA - Still in Design phase.
Mount Washington | Historic Multi-Use Trail Segment C | 2479 | 05-03216.00 | Design | 2023 | STBG-MPO | 79172 | Estimate 2023 | Federal Funding Not Yet Authorized | Final Design Plans submitted for review to KYTC ; Lighting plans submitted to LG&E
|  |  |  | ROW | 2023 | STBG-MPO | 281000 | Estimate 2023 | Federal Funding Not Yet Authorized | Right of Way to begin October 2023
|  |  |  | Construction | 2024 | STBG-MPO | 1676642 | Estimate 2024 | Federal Funding Not Yet Authorized | no change
|  |  |  | Construction | 2024 | TA-MPO | 870787 | Estimate 2024 | Federal Funding Not Yet Authorized | no change
|  |  |  | Construction | 2024 | STBG-State | 118000 | Estimate 2024 | Federal Funding Not Yet Authorized | no change
Oldham County | KY 329 | 1877 | 05-00542.00 | Utilities | 2023 | STBG-MPO | 37000 |  |  | KYTC has taken over project for all phases beyond Design
|  |  |  | Construction | 2023 | STBG-MPO | 3800000 | authorized 7/17/2023 | Federal Funding Authorized | Project was awarded to MAC for Construction on 6/30/2023
Oldham County | KY 393 Trail (Mattingly/Old LaGrange Road Trail) | 2981 | TBD | Design | 2023 | STBG-MPO | 222000 | estimated 9/15/2023 | Federal Funding Not Yet Authorized | Authorization for Design funds requested by D5 on 8/24/2023
|  |  |  | ROW | 2024 | STBG-MPO | 139000 | estimated 9/15/2024 | Federal Funding Not Yet Authorized
|  |  |  | Utilities | 2025 | STBG-MPO | 139000 | estimated 9/15/2025 | Federal Funding Not Yet Authorized
|  |  |  | Construction | 2026 | STBG-MPO | 500000 | estimated 9/15/2026 | Federal Funding Not Yet Authorized
Oldham County | LaGrange Underpass West of LaGrange | 321 | 05-00434.00 | Design | 2023 | STBG-MPO | 160000 | estimated Spring 2025 | Federal Funding Not Yet Authorized | KYTC has taken over the project. Waiting on CSX.
|  |  |  | Utilities | 2023 | STBG-MPO | 3895000 | estimated Spring 2025 | Federal Funding Not Yet Authorized | Project has been prioritized after KY 393 project for utility relocation.
|  |  |  | Construction | 2023 | STBG-MPO | 10500000 | estimated Spring 2025 | Federal Funding Not Yet Authorized | KYTC hopes will go to construction in immediately following KY 393.
Oldham County | Old LaGrange Road Improvements Oldham County Bicycle & Pedestrian Trail | 2175 | 05-00410.01 | Right of Way | 2023 | STBG-MPO | 214676 | estimated 12/1/2023 | Federal Funding Not Yet Authorized | Delayed feedback from Utility complanies delayed ROW plans.
|  |  |  | Right of Way | 2023 | STBG-State | 340324 | estimated 12/1/2023 | Federal Funding Not Yet Authorized | ROW plans are completed and waiting on approval from D5
|  |  |  | Utilities | 2024 | STBG-MPO | 750000 | estimated 12/1/2024 | Federal Funding Not Yet Authorized
|  |  |  | Construction | 2025 | STBG-MPO | 500000 | estimated 12/1/2025 | Federal Funding Not Yet Authorized
Oldham County | KY 22/Clore Lane Intersection Improvements | 3141 |  | Design | 2024 | STBG-MPO | 188889 | estimated March 2024 | Federal Funding Not Yet Authorized
|  |  |  | ROW | 2025 | STBG-MPO | 733333 | estimated March 2025 | Federal Funding Not Yet Authorized
|  |  |  | Utilities | 2026 | STBG-MPO | 622222 | estimated March 2026 | Federal Funding Not Yet Authorized
|  |  |  | Construction | 2027 | STBG-MPO | 1888889 | estimated March 2027 | Federal Funding Not Yet Authorized
Oldham County | Kenwood Road | 2615 |  | Design | 2024 | STBG-MPO | 325000 | authorized 8/16/2023 | Federal Funding Authorized | Design funds have been obligated.
|  |  |  | ROW | 2025 | STBG-MPO | 490000 | estimated July 2025 | Federal Funding Not Yet Authorized
|  |  |  | Utilities | 2026 | STBG-MPO | 664063 | estimated July 2026 | Federal Funding Not Yet Authorized
|  |  |  | Construction | 2027 | STBG-MPO | 2003125 | estimated July 2027 | Federal Funding Not Yet Authorized
University of Louisville | 2nd Street / 3rd Street / Museum Drive Intersection and Brandeis Avenue Pedestrian Improvements | 2982 | 5-581 | Design | 2023 | STBG-MPO | 225000 | Actual 2023 | Federal Funding Authorized | Evaluation of alternatives ; Traffic Study
|  |  |  | Utilities | 2023 | STBG-MPO | 1105280 | Estimate 2024 | Federal Funding Not Yet Authorized
|  |  |  | Construction | 2023 | STBG-MPO | 2960000 | Estimated 2024 | Federal Funding Not Yet Authorized
University of Louisville | University of Louisville Pedestrian Improvements - Lighting | 2225 | 05-3218.00 | Design | 2023 | STBG-MPO | 15260 | Actual 2023 | Federal Funding Authorized | MOA request submitted to KYTC ; Once approved will begin
|  |  |  | Construction | 2024 | STBG-MPO | 589640 | Estimated 2024 | Federal Funding Not Yet Authorized
University of Louisville | University of Louisville Pedestrian Improvements - ADA Curb Cuts & Ramps | 2585 | 05-3220.00 | Design | 2023 | STBG-MPO | 45878 | Actual 2023 | Federal Funding Authorized | MOA request submitted to KYTC ; Once approved will begin
|  |  |  | Construction | 2024 | STBG-MPO | 534568 | Estimated 2024 | Federal Funding Not Yet Authorized
KYTC | English Station Rd. | 188 | 05-00353.00 | Construction | 2023 2024 | STBG-MPO | 6408000 | 2023-08-24 | Federal Funding Not Yet Authorized | R/W cleared. Utility coordination in progress.
KYTC | KY 1931 | 2214 | 05-00536.00 | Right of Way | 2023 2024 | STBG-MPO | 1220000 | 2023-08-24 | Federal Funding Not Yet Authorized | R/W cleared. Utility & RR coordination in progress.
|  |  |  | Construction | 2025 | STBG-MPO | 10780000 | 2023-08-25 | Federal Funding Not Yet Authorized | Construction schedule dependent on utility relocations.
KYTC | US 42 | 1271 | 05-00441.00 | Right of Way | 2023 | STBG-MPO | 180000 | 2023-03-22 | Federal Funding Authorized | R/W cleared. Utility relocation authorized.
|  |  |  | Construction | 2023 2025 | STBG-MPO | 5020000 | 2023-08-25 | Federal Funding Not Yet Authorized | Construction schedule impacted by delay in utility relocations.
KYTC | KY 2055 | 3042 | 5-80110.00 | Design | 2023 2024 | STBG-MPO | 120000 | 2023-01-24 | Federal Funding Not Yet Authorized | New to TIP | According to the PMG, the initial design phase of a project must be obligated in the year it was programmed in the TIP
|  |  |  | ROW | 2024 2025 | STBG-MPO | 24000 | 2023-11-24 | Federal Funding Not Yet Authorized | New to TIP
|  |  |  | Utilities | 2025 | STBG-MPO | 24000 | 2023-11-24 | Federal Funding Not Yet Authorized | New to TIP
|  |  |  | Construction | 2026 | STBG-MPO | 120000 | 2023-11-25 | Federal Funding Not Yet Authorized | New to TIP
KYTC | Reconnecting West Louisville to the Ohio Riverfront throughout the Riverside Expressway (I-64) Corridor | 3067 | TBD | Planning | 2023 | STBG-MPO | 600000 | 2023-07-31 | Federal Funding Authorized | RFP to be issued in September 2023 for a Planning Study
KYTC | KY 1065 | 436 | TBD | Planning | 2023 2024 | STBG-MPO | 200000 | 2023-04-24 | Federal Funding Not Yet Authorized | New to TIP
KYTC | KY 1932 Chenoweth Lane | 213 | 05-00531.00 | Construction | 2024 | STBG-MPO | 1940000 | 2023-08-24 | Federal Funding Not Yet Authorized | R/W cleared. Utility relocation underway.
KYTC | US 42 Safety and Mobility Improvements from the Harrods Creek Bridge to River Road | 230 |  | Design | 2024 | STBG-MPO | 800000 | 2023-12-23 | Federal Funding Not Yet Authorized | New to TIP
|  |  |  | ROW | 2025 | STBG-MPO | 664000 |  | Federal Funding Not Yet Authorized | New to TIP
|  |  |  | Utilities | 2026 | STBG-MPO | 2080000 |  | Federal Funding Not Yet Authorized | New to TIP
|  |  |  | Construction | 2027 | STBG-MPO | 6008000 |  | Federal Funding Not Yet Authorized | New to TIP
KYTC | KY 2050 | 2114 |  | Design | 2024 | STBG-MPO | 280000 | 2023-12-23 | Federal Funding Not Yet Authorized | New to TIP
|  |  |  | ROW | 2025 | STBG-MPO | 44000 |  | Federal Funding Not Yet Authorized | New to TIP
|  |  |  | Utilities | 2026 | STBG-MPO | 128000 |  | Federal Funding Not Yet Authorized | New to TIP
|  |  |  | Construction | 2027 | STBG-MPO | 1728000 |  | Federal Funding Not Yet Authorized | New to TIP
Louisville Metro | AB Sawyer Greenway Shared Use Path | 1662 | 5-529.00 | Construction | 2023 | STBG-MPO | 3450000 | 2023-06-24 | Federal Funding Not Yet Authorized | Metro reviewing construction plans and cross sections with revisions for floodplain fill mitigation. Anticipating permit approvals by 1/31/24, with PDC submittal to KYTC in February 2024. Anticipate it will take 4 months for KYTC to approve authorization = June 2024. | Phase shift needed to FFY 2024
Louisville Metro | Baxter/Bardstown Premium Transportation Corridor - Section 1 | 1353 | ? | Design | 2023 | STBG-MPO | 177750 | 2023-12-23 | Federal Funding Not Yet Authorized | Preparing Attachment A to submit to KYTC. | Phase shift needed to FFY 2024
|  |  |  | Construction | 2025 | STBG-MPO | 2200000 | 2023-09-24 | Federal Funding Not Yet Authorized | Phase is on schedule.
Louisville Metro | Bicycle & Pedestrian Education, Encouragement, Enforcement & Evaluation | 337 | 5-965.15 | Program | 2023+ | STBG-MPO | 120000 | 2023-10-22 | Phase Completed | FFY 2023 - Submitted final invoices to KYTC.
FFY 2024 - Preparing Attachment A to submit to KYTC and authorize ASAP in the new FFY.
Louisville Metro | Cannons Lane | 2239 | 5-3212.00 | Construction | 2023 | STBG-MPO | 1000000 | 2023-03-23 | Federal Funding Authorized | Waiting on Construction MOA Signatures from KYTC and approval of the PDC Checklist.
Louisville Metro | Cooper Chapel Rd. Phase 3 | 223 | 05-00404.01 | Design | 2023 | STBG-MPO | 45400 | 2023-11-23 | Federal Funding Not Yet Authorized | Preparing Attachment A to submit to KYTC. | Phase shift needed to FFY 2024
|  |  |  | Right of Way | 2023 | STBG-MPO | 800000 | 2023-11-23 | Federal Funding Not Yet Authorized | Will likely need a cost increase Awaiting source deeds to be separated from title reports for ROW Revision Memo. Update: Metro submitted source deeds on 8/14/23 - BKE | Phase shift needed to FFY 2024.
Possible cost increase needed - will submit in late Sept.
|  |  |  | Utilities | 2025 | STBG-MPO | 1500000 | 2023-10-24 | Federal Funding Not Yet Authorized | MSD to determine if a number of forcemains need to be lowered, will need a finalized agreement with LWC, and still awaiting word back from LG&E regarding relocations.
|  |  |  | Construction | 2025 | STBG-MPO | 16000000 | 2023-12-24 | Federal Funding Not Yet Authorized | Phase is on schedule.
Louisville Metro | Hikes Lane Rehabilitation | 2897 | 5-583.00 | Construction | 2023 | STBG-MPO | 6720000 | 2023-02-23 | Federal Funding Authorized | In Construction. Change Order 1 under review.
Louisville Metro | I-65 | 224 | 05-00378.10 | Design | 2023 | STBG-MPO | 265000 | 2023-11-22 | Federal Funding Authorized | PL&G selected Alt 1A interim (4 lane). Final PL&G Meeting Minutes on 8/2.
|  |  |  | Utilities | 2026 | STBG-MPO | 640000 | 2023-01-27 | Federal Funding Not Yet Authorized | Phase is on schedule.
Louisville Metro | Kentuckiana Air Education | 369 | 5-244.00 | Program | 2023+ | STBG-MPO | 200000 | 2023-09-23 | Federal Funding Not Yet Authorized | The KYTC contract for KAIRE is in the routing process for signatures. That authorization includes two years of funding—FY22 and FY23.
Louisville Metro | Main Street / Story Avenue Intersection | 2388 | 5-561.00 | Design | 2023 | STBG-MPO | 25000 | 2023-03-23 | Federal Funding Authorized | Revised JI plans submitted 7/11. Working with Central Office Traffic on review of revised signal plans. Plan revisions being made to move strain pole to SUE location.
|  |  |  | Construction | 2024 | STBG-MPO | 3365319 | 2023-01-24 | Federal Funding Not Yet Authorized | Phase is on schedule.
Louisville Metro | Newburg road Sidewalk | 2898 | 05-03041.00 | Construction | 2023 | TA-MPO | 611000 | 2023-10-23 | Federal Funding Not Yet Authorized | Attachment A submited to KYTC on 9/5/2023. Expect it will take at least 1 month for KYTC to approve authorization. | Phase shift is likely needed to FFY 2024
Louisville Metro | North Hubbards Ln. | 384 | 5-479.00 | Construction | 2023 | STBG-MPO | 3740000 | 2023-10-24 | Federal Funding Not Yet Authorized | Included in Amendment 4 to move Construction to FFY 2025. | Phase shift to FFY 2025 is already in progress via Amendment 4.
Louisville Metro | Northeast Louisville Loop MET, Section 2 Beckley Station to Bircham Rd. | 2269 | 5-3030.20 | Utilities | 2023 | STBG-MPO | 280000 | 2023-12-23 | Federal Funding Not Yet Authorized | Metro awaiting final approval for R/W Certification. AECOM submitted the requested source deeds to KYTC on 7-13-23. | Phase shift needed to FFY 2024
|  |  |  | Construction | 2023 | STBG-MPO | 1800000 | 2023-12-23 | Federal Funding Not Yet Authorized | Metro awaiting final approval for R/W Certification. AECOM submitted the requested source deeds to KYTC on 7-13-23. | Phase shift needed to FFY 2024
Louisville Metro | Northeast Louisville Loop MET, Section 4 Beckley Creek Park to Eastwood Cutoff | 2271 | 5-3030.40 | Right of Way | 2023 | STBG-MPO | 350000 | 2023-09-23 | Federal Funding Not Yet Authorized | AECOM submitted "stamped" R/W plans to KYTC D-5 on 7-31-23. Brian Eaton submitted these plans to KYTC CO in order to get approval for R/W acquistion funds.
|  |  |  | Utilities | 2027 | STBG-MPO | 220000 | 2023-10-26 | Federal Funding Not Yet Authorized | Phase is on schedule.
Louisville Metro | Olmsted Parkways Multi-Use Path System Section 1 | 2622 | 05-03709.00 | Construction | 2023 | STBG-MPO | 2200000 | 2023-09-24 | Federal Funding Not Yet Authorized | NEPA review underway for Section 1 to advance to ROW phase. Awaiting KYTC determination for authorization of additional requested Design phase funds programmed in FY23 to keep D phase open. Metro continuing research into RR ROW claims before completing Construction Agreement with Norfolk Southern. | Phase shift needed to FFY 2024
Louisville Metro | Olmsted Parkways Multi-Use Path System Section 3 | 2624 | 5-3709.00 | Design | 2023 | STBG-MPO | 100000 | 2023-09-23 | Federal Funding Not Yet Authorized | Authorization request sent to KYTC in January 2023, still pending because NEPA needs to be reviewed for whole 8 miles of combined projects (5-3709 and 5-506). Field walk with SHPO and DEA held 8/31/2023 to further the NEPA process.
|  |  |  | ROW | 2026 | STBG-MPO | 942000 | 2023-10-25 | Federal Funding Not Yet Authorized | Working to meet all milestones so we can begin ROW in Q1 of FFY2026.
Louisville Metro | Olmsted Parkways Multi-Use Path System Section 6 | 2627 | 5-506.00 | Design | 2023 | STBG-MPO | 532435 | 2023-09-23 | Federal Funding Not Yet Authorized | [Same comment as Section 3]
Authorization request sent to KYTC in January 2023, still pending because NEPA needs to be reviewed for whole 8 miles of combined projects (5-3709 and 5-506). Field walk with SHPO and DEA held 8/31/2023 to further the NEPA process.
|  |  |  | ROW | 2024 | STBG-MPO | 500000 | 2023-07-24 | Federal Funding Not Yet Authorized | Awaiting local match to be included in LMG's FY25 budget.
Louisville Metro | Olmsted Parkways Multi-Use Path System Section 7 | 2628 | 5-506.00 | Design | 2023 | STBG-MPO | 416195 | 2023-09-23 | Federal Funding Not Yet Authorized | [Same comment as Section 3]
Authorization request sent to KYTC in January 2023, still pending because NEPA needs to be reviewed for whole 8 miles of combined projects (5-3709 and 5-506). Field walk with SHPO and DEA held 8/31/2023 to further the NEPA process.
|  |  |  | ROW | 2024 | STBG-MPO | 484000 | 2023-07-24 | Federal Funding Not Yet Authorized | Awaiting local match to be included in LMG's FY25 budget.
Louisville Metro | Olmsted Parkways Multi-Use Path System Section 8 | 2629 | 5-506.00 | Design | 2023 | STBG-MPO | 259119 | 2023-09-23 | Federal Funding Not Yet Authorized | [Same comment as Section 3]
Authorization request sent to KYTC in January 2023, still pending because NEPA needs to be reviewed for whole 8 miles of combined projects (5-3709 and 5-506). Field walk with SHPO and DEA held 8/31/2023 to further the NEPA process.
Louisville Metro | Olmsted Parkways Multi-Use Path System Section 9 | 2630 | 5-506.00 | Design | 2023 | STBG-MPO | 252251 | 2023-09-23 | Federal Funding Not Yet Authorized | [Same comment as Section 3]
Authorization request sent to KYTC in January 2023, still pending because NEPA needs to be reviewed for whole 8 miles of combined projects (5-3709 and 5-506). Field walk with SHPO and DEA held 8/31/2023 to further the NEPA process.
|  |  |  | Construction | 2027 | STBG-MPO | 2000000 | 2023-10-26 | Federal Funding Not Yet Authorized | Phase is on schedule.
Louisville Metro | One-Way Street Conversion to Two-Way Phase 1 | 1809 | 5-470.00 | Utilities | 2023 | STBG-MPO | 220000 | 2023-05-23 | Federal Funding Authorized | Performing SUE work and bid Jefferson in August.
|  |  |  | Construction | 2024 | STBG-MPO | 1650000 | 2023-11-23 | Federal Funding Not Yet Authorized | Phase is on schedule.
Louisville Metro | River Road | 163 | 5-91.02 | Utilities | 2024 | STBG-MPO | 2000000 | 2023-10-23 | Federal Funding Not Yet Authorized | Utility relocations began on 7/17/2023. Change Order 1 under review by KYTC.
|  |  |  | Construction | 2024 | STBG-State | 4784907 | 2023-01-24 | Federal Funding Not Yet Authorized | Letting date planned for February 2024.
|  |  |  | Construction | 2024 | STBG-MPO | 15729715 | 2023-01-24 | Federal Funding Not Yet Authorized | Letting date planned for February 2024.
Louisville Metro | River Road Multi-Modal Improvements | 2540 | 5-3217.00 | Construction | 2024 | TA-MPO | 2200000 | 2023-09-23 | Federal Funding Not Yet Authorized | KYTC OLP to process supplement 2. PDC submitted for final approval in January 2023.
Louisville Metro | Stony Brook Drive Sidewalk Connector | 2594 | 05-571.00 | Construction | 2023 | STBG-MPO | 300000 | 2023-11-23 | Federal Funding Not Yet Authorized | KYTC reviewed Bid Proposal Doc. Metro to update Bid Proposal. Planning to submit Attachment A week of 9/11/2023. Expect it will take at least 1 month for KYTC to authorize. | Phase shift is likely needed to FFY 2024
Louisville Metro | East Market Street Streetscape Improvements | 2064 | 05-8703.00 | Construction | 2024 | STBG-MPO | 8700000 | 2023-01-24 | Federal Funding Not Yet Authorized | Phase is on schedule. Design will be complete soon.
Coordinating with FHWA for expedited review of encroachment permit (within I-65 R/W). Reviewing and commenting on submittals to be used for FHWA permit application. Completing review of Joint Inspection submittals (review complete now and comments have been sent). Commenting on Joint Inspection minutes. Reviewing proposals to perform SUE work (for proposed signal strain poles).
Louisville Metro | Buechel Bank Road | 381 | 5-8001.00 | Construction | 2024 | STBG-MPO | 6005000 | 2023-11-23 | Federal Funding Not Yet Authorized | Requesting relocation plans & estimates from LG&E.
Louisville Metro | Northeast Louisville Loop MET, Section 3 Bircham Rd. to Beckley Creek Park | 2270 | 05-03030.30 | Design | 2024 | STBG-MPO | 445000 | 2023-10-23 | Federal Funding Not Yet Authorized | NTP provided to AECOM to begin bridge inspection of the historic bridge.
|  |  |  | ROW | 2025 | STBG-MPO | 636000 | 2023-10-24 | Federal Funding Not Yet Authorized | Phase is on schedule.
Louisville Metro | Olmsted Parkways Multi-Use Path System Section 2 | 2623 |  | ROW | 2024 | STBG-MPO | 1451000 | 2023-07-24 | Federal Funding Not Yet Authorized | Awaiting local match to be included in LMG's FY25 budget.
|  |  |  | Utilities | 2026 | STBG-MPO | 100000 | 2023-09-26 | Federal Funding Not Yet Authorized | Phase is on schedule.
Louisville Metro | Downtown Traffic Signal Upgrades | 3127 |  | Design | 2024 | STBG-MPO | 312000 | 2023-11-23 | Federal Funding Not Yet Authorized | Phase is on schedule.
|  |  |  | Construction | 2025 | STBG-MPO | 3420000 | 2023-10-24 | Federal Funding Not Yet Authorized | Phase is on schedule.
Louisville Metro | River Road Extension | 1338 |  | Construction | 2024 | STBG-MPO | 9600000 | 2023-01-24 | Federal Funding Not Yet Authorized | Redesign for UG transmission line underway
Louisville Metro | Blanton Lane Sidewalk | 2920 | 05-03004.00 | ROW | 2024 | TA-MPO | 240000 | 2023-01-24 | Federal Funding Not Yet Authorized | Post JI - R/W plans sent to KYTC for any comments on 7/12/2023. | Cost increase needed - will submit in late Sept.
This project needs a cost increase. Need the total to = $576,000 (federal + KYTC oversight + local)
|  |  |  | Construction | 2025 | TA-MPO | 1159200 | 2023-01-25 | Federal Funding Not Yet Authorized | Timeline would be pushed back if not granted cost increase for ROW.
Louisville Metro | Crums Lane Sidewalk Phase 1 | 2896 | 05-03011.00 | ROW | 2024 | TA-MPO | 88978 | 2023-01-24 | Federal Funding Not Yet Authorized | Determining if we need a cost increase for ROW.
PL&G meeting with D5 to be scheduled in September.
|  |  |  | Construction | 2026 | TA-MPO | 1100000 | 2023-10-25 | Federal Funding Not Yet Authorized | Phase is on schedule.
Louisville Metro | Gagel Avenue Sidewalk | 2921 | 05-03040.00 | ROW | 2024 | TA-MPO | 176000 | 2023-01-24 | Federal Funding Not Yet Authorized | Determining if we need a cost increase for ROW.
Final plans including ROW plans to be submitted by end of August (by Consultant) for Metro/KYTC review
|  |  |  | Construction | 2026 | TA-MPO | 1400000 | 2023-10-25 | Federal Funding Not Yet Authorized | Phase is on schedule.
Louisville Metro | Louisville Loop Shared Use Path - McNeely Lake Segment | 2539 | 05-03034.00 | Construction | 2024 | TA-MPO | 2315000 | 2023-09-24 | Federal Funding Not Yet Authorized | Currently delayed by NEPA review - pending completion in late spring 2024 (glade cress report).
Project team continuing coordination with MSD sewer project; also finalizing fee proposals for BA and archaeology updates on redesigned section. Continuing pursuit of easement dedication on apartment property.
TA-State application submitted on 8/15/23 to fully fund construction of both McNeely Lake segments.
Louisville Metro | Dodge Gap Jefferson Memorial Forest - Louisville Loop Shared Use Path | 2087 | 05-00523.00 | ROW | 2024 | CRP-MPO | 111000 | 2023-03-25 | Federal Funding Not Yet Authorized | The geotech team is waiting on structural drawings to incorporate into report before submittal for KYTC review/comments/concurrence. Updated archaeological investigation report will be submitted to KYTC for review/concurrence by 8/11/23. | Phase shift needed to FFY 2024
Only 2 parcels expected for ROW.
|  |  |  | Utilities | 2027 | CRP-MPO | 25000 | 2023-10-26 | Federal Funding Not Yet Authorized | Phase is on schedule.
Louisville Metro | Northeast Louisville Loop Section II (Eastwood Cut-off) | 2116 | 05-00525.00 | Design | 2024 | CRP-MPO | 32000 | 2023-01-24 | Federal Funding Not Yet Authorized | Working concurrently with KYTC's 5-8952.0 project.
Awaiting meeting minutes from 5-8952.0 JI (held on 4-26-23) to determine any possible utility relocations that impact 5-525.0.
|  |  |  | ROW | 2024 | CRP-MPO | 5000 | 2023-01-24 | Federal Funding Not Yet Authorized | Phase is on schedule.
|  |  |  | Utilities | 2024 | CRP-MPO | 39000 | 2023-01-24 | Federal Funding Not Yet Authorized | Phase is on schedule.
|  |  |  | Construction | 2025 | CRP-MPO | 782000 | 2023-10-24 | Federal Funding Not Yet Authorized | Phase is on schedule.
Louisville Metro | Ohio River Levee Trail Phase III | 1109 | 05-00505.00 | Construction | 2024 | CRP-MPO | 6463000 | 2023-09-24 | Federal Funding Not Yet Authorized | Currently in ROW. There are several parcels that might need to go to condemnation. Currently unsure of schedule for Construction. Not ready to do a phase shift at this time.
Louisville Metro | Pond Creek Jefferson Memorial Forest - Louisville Loop Shared Use Path | 2086 | 05-00522.00 | ROW | 2024 | CRP-MPO | 1499301 | 2023-02-24 | Federal Funding Not Yet Authorized | Metro is preparing Attachment A for request for authorization of FY24 ROW phase funding to be submitted in October 2024. Estimated month of authorization = how long it will take KYTC to process = February 2024. Project team completing ROW plans revisions.
|  |  |  | ROW | 2025 | CRP-MPO | 500699 | 2023-10-24 | Federal Funding Not Yet Authorized | We didn't request ROW split into two years, therefore we will want the next round of ROW funds ASAP.
|  |  |  | Utilities | 2027 | CRP-MPO | 55000 | 2023-10-26 | Federal Funding Not Yet Authorized | Phase on schedule.
Projects shown have at least 1 project phase of MPO-dedicated funding in either 2023 or 2024