## Sheet 1
Indiana Progress Report Summary Fall 2024
Clark County
Project | KIPDA ID | STATE ID | Phase | Fiscal Year | Program | MPO Dedicated Federal Funds Programmed in TIP | Project Phase Status | Actual or Estimated Date of Authorization | Federal Funding Amount Authorized (if Applicable) | Progress In Past Quarter
CR 403 and Stacy Road Intersection Improvements* | 2549 | 1802805 | PE | 2020 | HSIP-MPO | 283500 |  | 2019-09-01
|  |  | U | 2024 | HSIP-MPO | 134029 | Federal Funding Authorized | 2024-05-01 | 229680
|  |  | C | 2024 | HSIP-MPO | 2147735 | Federal Funding Authorized | 2024-05-01 | 2002399 | Pe-construction meeting held on 8-13. Contractor plans to start Oct 1, to remove trees. IAW is still not out of the way.
Jeff Charlestown Pike Improvements | 3177 | 2301301 | ROW | 2027 | Locally Funded |  |  | N/A | N/A | Four properties have not yet been cleared. Tree removal will begin Oct-1 mending property acquisition. Construction to start later this year
|  |  | C | 2028 | CRP | 3300000 | Federal Funding Not Yet Authorized |  | N/A
Henryville Sidewalk | 3180 | 2301302 | PE | 2027 | PROTECT | 3229 | Federal Funding Not Yet Authorized |  | N/A | LOI are to be submitted by Sept-2024. Design may start later this year
|  |  | PE | 2028 | PROTECT | 22109 | Federal Funding Not Yet Authorized |  | N/A
|  |  | C | 2029 | PROTECT | 520661 | Federal Funding Not Yet Authorized |  | N/A
Clarksville
Project | KIPDA ID | STATE ID | Phase | Fiscal Year | Program | MPO Dedicated Federal Funds Programmed in the TIP | Project Phase Status | Actual or Estimated Date of Authorization | Federal Funding Amount Authorized (If Applicable) | Progress
Progress Way Improvements | 3018 | 2300582 | ROW | 2025 | STBG | 300000 |  |  |  | RFP's have been received and will score them this week.
|  |  | U | 2027 | STBG | 700000 | Federal Funding Not Yet Authorized |  | N/A
|  |  | C | 2027 | STBG | 1817926 | Federal Funding Not Yet Authorized |  | N/A
Stansifer Avenue Streetscape Improvements | 3019 | 2301311 | PE | 2025 | STBG | 323000 |  |  |  | We are currently working with the top scorer on a contract.
|  |  | ROW | 2027 | STBG | 80000 | Federal Funding Not Yet Authorized |  | N/A
|  |  | C | 2029 | STBG | 3597000 | Federal Funding Not Yet Authorized |  | N/A
Riverside Drive Reconstruction | 2393 | 1700725 | - | 2023 | - | - | Federal Funding Authorized | - | - | Construction is underway and on schedule.
Floyd County
Project | KIPDA ID | STATE ID | Phase | Fiscal Year | Program | MPO Dedicated Federal Funds Programmed in the TIP | Project Phase Status | Actual or Estimated Date of Authorization | Federal Funding Amount Authorized (If Applicable) | Progress
Bridge 51 (Blackiston Mill Road) Replacement Project | 1558 | 1700788 | PE | 2024 | STBG-MPO | 202688 | Federal Funding Authorized | 2024-03-02 | 202688 | Ongoing R/W services, all appraisals and review appraisals complete, Statement of Just Compensation complete, tracking utility coordination
|  |  | ROW | 2024 | STBG-MPO | 997312 | Federal Funding Authorized | 2024-05-08 | 997312 | Offer letters have been issued. Currently in 30 day reply period
|  |  | C | 2026 | STBG-MPO | 3606183 | Federal Funding Not Yet Authorized | 2025-07-01 | N/A | Submittals on schedule for July, 2025 letting.
Charlestown Road Corridor Complete Street Multi Use Trail | 2128 | 1400550 | CE | 2025 | HSIP-State | 317925
|  |  | C | 2025 | HSIP-State | 3325811
New Albany
Project | KIPDA ID | STATE ID | Phase | Fiscal Year | Program | MPO Dedicated Federal Funds Programmed in the TIP | Project Phase Status | Actual or Estimated Date of Authorization | Federal Funding Amount Authorized (If Applicable) | Progress
Mount Tabor Road | 309 | 2000188 | U | 2024 | STBG | 640000 | Federal Funding Not Yet Authorized |  |  |  | KIPDA's understanding of total CN cost estimate is $2 million
|  |  | C | 2025 | STBG | 3672000 | Federal Funding Not Yet Authorized | 2025-01-01 | N/A |  | KIPDA's understanding of total CN cost estimate is $5.6 million | current split of remaining STBG funds is 46% federal and 54% local for U and C phases
Graybrook Lane Extension | 3102 | 2301317 | PE | 2025 | STBG | 357109 | Federal Funding Not Yet Authorized | TBD | N/A | The RFP was posted on 8/26/24 with proposals being due on 9/23/24
|  |  | ROW | 2027 | STBG | 439200 | Federal Funding Not Yet Authorized | TBD | N/A
|  |  | U | 2028 | STBG | 80000 | Federal Funding Not Yet Authorized | TBD | N/A
|  |  | C | 2029 | STBG | 2074949 | Federal Funding Not Yet Authorized | TBD | N/A
Intersection of E. Spring St. & Beharrell Ave. | 3136 | 2301550 | PE | 2025 | HSIP | 252000 | Federal Funding Not Yet Authorized | TBD | N/A | The RFP was posted on 8/26/24 with proposals being due on 9/23/24
|  |  | ROW | 2027 | HSIP | 400000 | Federal Funding Not Yet Authorized | TBD | N/A
|  |  | C | 2028 | HSIP | 1932000 | Federal Funding Not Yet Authorized | TBD | N/A