## Sheet1
Project | KIPDA ID | STATE ID | Phase | Fiscal Year | Program | MPO Dedicated Federal Funds Programmed in the TIP | Project Phase Status | Actual or Estimated Date of Authorization | Federal Funding Amount Authorized (If Applicable) | Progress
New Albany
Graybrook Lane Extension | 3102 | 2301310 | PE | 2025 | Group III | 357109
|  |  | ROW | 2030 | STBG | 439200 | Federal Funding Not Yet Authorized | TBD | N/A |  | Admin Mod 1
|  |  | U | TBD | STBG | 80000 | Federal Funding Not Yet Authorized | TBD | N/A |  | Admin Mod 1
Intersection of E. Spring St. & Beharrell Ave. | 3136 | 2301550 | PE | 2026 | HSIP | 252000 | Federal Funding Not Yet Authorized | TBD | N/A | The City is re-releasing the RFP soon.
|  |  | ROW | 2027 | HSIP | 400000 | Federal Funding Not Yet Authorized | TBD | N/A
|  |  | C | 2029 | HSIP | 1932000 | Federal Funding Not Yet Authorized | TBD | N/A
Slate Run Road Phase II | 3369 | 2401854 | PE | 2026 | Group III | 200000 |  | TBD |  | The City is requesting the PO from INDOT soon. | Admin Mod 1
|  |  | ROW | 2027 | TA-MPO | 402940 | Federal Funding Not Yet Authorized | TBD | N/A
|  |  | ROW | 2028 | TA-MPO | 1293060 | Federal Funding Not Yet Authorized | TBD | N/A
|  |  | CE | 2030 | TA-MPO | 400000 | Federal Funding Not Yet Authorized | TBD | N/A
|  |  | CN | 2030 | CRP-MPO | 4080000 | Federal Funding Not Yet Authorized | TBD | N/A
Clark County
CR 403 and Stacy Road Intersection Improvements* | 2549 | 1802805 | PE | 2020 | HSIP-MPO | 283500 |  | 2019-09-01
|  |  | U | 2024 | HSIP-MPO | 134029 | Federal Funding Authorized | 2024-05-01 | 229680 | Construction of th enorth half of the roundabout is nearly complete. Traffic has been moved to the north half while contractor works on the south half. Contractor has until Dec to complete but should be complete by October. All good for now.
|  |  | C | 2024 | HSIP-MPO | 2147735 | Federal Funding Authorized | 2024-05-01 | 2002399
Henryville Sidewalk | 3180 | 2301302 | PE | 2025 | PROTECT | 144000 | Federal Funding Authorized |  | 144000 | Engineering desing is more than 50% complete. Amendment to the design contract is still being finalized. Clark County has agreed to the work and the amount but are still trying to get amendment into INDOT format.
|  |  | PE | 2026 | Group III | 100000 |  |  |  | Additional $100,000 funds will be used for amendment work. Design should be complete by end of the year. Contract could be ready for letting fiscal year 2026 but funds will be availbale 2031.
|  |  | C | 2029 | PROTECT | 520661 | Federal Funding Not Yet Authorized |  | N/A
|  |  | U | 2031 | INDOT Funds | 45000 | Federal Funding Not Yet Authorized |  | N/A
|  |  | CE | 2031 | INDOT Funds | 140400 | Federal Funding Not Yet Authorized |  | N/A
|  |  | CN | 2031 | INDOT Funds | 1072373 | Federal Funding Not Yet Authorized |  | N/A
Small Structure Inventory Study | 3330 | 2401845 | Planning | 2025 | Group III | 200000 |  |  |  | NTP has been issued. Contractor to start in August.
CR-311 and Sellersburg Improvements | 3364 | 2401840 | PE | 2026 | Group III | 600000 | Federal Funding Authorized |  |  | County has received $600,000 for design. Requesting additional funds for design. Consultant selected NTP has not been issued. County is working on an agreement with Sellersburg to help with construction.
|  |  | ROW | 2028 | CMAQ-MPO | 500000 | Federal Funding Not Yet Authorized
|  |  | ROW | 2029 | CMAQ-MPO | 500000 | Federal Funding Not Yet Authorized
|  |  | U | 2030 | CMAQ-MPO | 500000 | Federal Funding Not Yet Authorized
Memphis Blue Lick Roadway Improvements | 3365 | 2401839 | Planning | 2026 | Group III | 100000 |  |  |  | County has selected Consultant. Contract has not been finalized.
Clarksville
Progress Way Improvements | 3018 | 2300582 | ROW | 2025 | STBG | 300000 | Federal Funding Authorized |  | 69815 | Work in progress
|  |  | U | 2027 | STBG | 700000 | Federal Funding Not Yet Authorized |  | N/A
|  |  | CE | 2027 | STBG | 336000 | Federal Funding Not Yet Authorized |  | N/A
|  |  | C | 2027 | STBG | 3200000 | Federal Funding Not Yet Authorized |  | N/A
Riverside Drive Reconstruction (Only fill out "Project Phase Status" Column & "Progress" Column) | 2393 | 1700725 | - | 2023 | - | - | Federal Funding Authorized | - | - | INDOT is reviewing a request to place a "suspension" on this project while working on the flood control issues.
Floyd County
Bridge 51 (Blackiston Mill Road) Replacement Project | 1558 | 1700788 | PE | 2024 | STBG-MPO | 202688 | Federal Funding Authorized | 2024-03-02 | 202688
|  |  | ROW | 2024 | STBG-MPO | 997312 | Federal Funding Authorized | 2024-05-08 | 997312
|  |  | CE | 2026 | STBG-MPO | 480000 | Federal Funding Not Yet Authorized |  | N/A | Negotiating Contract with Procured Firm
|  |  | CN | 2026 | STBG-MPO | 4095243 | Federal Funding Not Yet Authorized |  | N/A | Final Tracing submitted, letting date October 8.
Bridge 38 - (Baylor Wissman) Replacement | 3366 | 2401834 | PE | 2026 | Group III | 360000 |  |  |  | INDOT LPA Contract Complete, LPA Consultant Contract Complete, FMIS Request Submitted, Awating PO & NTP
|  |  | ROW | 2027 | STBG-MPO | 32000 | Federal Funding Not Yet Authorized
|  |  | CE | 2029 | STBG-MPO | 276000 | Federal Funding Not Yet Authorized
|  |  | CN | 2029 | STBG-MPO | 1852000 | Federal Funding Not Yet Authorized
Baylor Wissman Hilltop | 3367 | 2401835 | PE | 2026 | Group III | 161481 |  |  |  | INDOT LPA Contract Complete, LPA Consultant Contract Complete, FMIS Request Submitted, Awating PO & NTP
|  |  | ROW | 2029 | HSIP-MPO | 256460 | Federal Funding Not Yet Authorized
|  |  | CE | TBD | HSIP-MPO | 257620 | Federal Funding Not Yet Authorized
|  |  | CN | TBD | HSIP-MPO | 833320 | Federal Funding Not Yet Authorized
Highway 150 Break Highlander Point | 3368 | 2401836 | PE | 2026 | Group III | 315000 |  |  |  | INDOT LPA Contract Complete, LPA Consultant Contract Complete, FMIS Request Submitted, Awating PO & NTP
|  |  | CE | 2028 | STBG-MPO | 402029 | Federal Funding Not Yet Authorized
|  |  | CN | 2028 | STBG-MPO | 2680191 | Federal Funding Not Yet Authorized
Charlestown Road Corridor Complete Street Multi Use Trail | 2128 | 1400550 | CE | 2025 | HSIP-State | 435494
|  |  | CE | 2025 | HSIP-MPO | 264937 | Federal Funding Authorized
|  |  | C | 2025 | HSIP-State | 2903293 |  |  |  | In progress, current delay due to discovered utility conflict. Resolution pending.