## Progress Report Summary
Project | KIPDA ID | STATE ID | Phase | Fiscal Year | Program | MPO Dedicated Federal Funds | Actual or Estimated Date of Authorization | Project Phase Status | Phase Shift History | Progress Since Last Meeting (3/25) | Need a phase shift? (Yes or No) | If so, what fiscal year will you need to shift to? (Be cognicent of your "Phase Shift History")
Louisville Metro
AB Sawyer Greenway Shared Use Path | 1662 | 5-529.00 | Construction | 2025 | STBG-MPO | 3555600 |  |  | Unlimited - ROW or U previously obligated | ROW property notifications underway | Yes | 2026
Bicycle & Pedestrian Education, Encouragement, Enforcement & Evaluation | 337 | 5-965.15 | Program | 2025+ | STBG-MPO | 120000 |  |  | None
Cooper Chapel Rd. Phase 3 | 223 | 05-404.01 | Design | 2024 | STBG-MPO | 45400 |  | Federal Funding Authorized | Unlimited - ROW or U previously obligated | Working on proposal for U phase activity - force main relocation | Yes | U Phase - FY26
|  |  | Right of Way | 2024 | STBG-MPO | 800000 |  | Federal Funding Authorized | Unlimited - ROW or U previously obligated | ROW is ongoing | No
|  |  | Utilities | 2025 | STBG-MPO | 2098000 |  |  | Unlimited - ROW or U previously obligated |  | Yes | 2026
|  |  | Construction | 2027 | STBG-MPO | 18153600 |  | Federal Funding Not Yet Authorized | Unlimited - ROW or U previously obligated |  | No
I-65/Brook St Ramp | 224 | 05-378.10 | Utilities | 2026 | STBG-MPO | 640000 |  | Federal Funding Not Yet Authorized | 2 Phase Shifts Approved - next will require phase shift exception request approval | Per KYTC, waiting for the 2026 Highway plan to see if the project has funding. If funding is included in the plan an RFP will be drafted. (7/10/2025 KD) | No
Kentuckiana Air Education | 369 | 5-244.00 | Program | 2025+ | STBG-MPO | 200000 |  |  | None
Main Street / Story Avenue Intersection | 2388 | 5-561.00 | Construction | 2024 | STBG-MPO | 3365319 | 2024-05-13 | Federal Funding Authorized |  | Construction mostly complete; closeout of punchlist items | No
North Hubbards Ln. | 3233 | 5-479.10 | Construction | 2025 | STBG-MPO | 5809589 |  |  | Unlimited - ROW or U previously obligated | Metro received the signed LWC Agreement on 8-7-25. Gresham Smith to submit final construction plans to Metro for review prior to submittal to KYTC. | Yes | 2026
Northeast Louisville Loop MET, Section 2 Beckley Station to Bircham Rd. | 2269 | 5-3030.20 | Construction | 2025 | STBG-MPO | 2080000 | 2025-02-17 | Federal Funding Authorized | Unlimited - ROW or U previously obligated | Construction beginning 8/18/2025. | No
Olmsted Parkways Multi-Use Path System Section 1 | 2622 | 5-3709.00 | Construction | 2025 | STBG-MPO | 2750000 |  |  | Unlimited - ROW or U previously obligated | ROW Plans submitted to KYTC 8/5/2025. TIP Amendment to access CMAQ funds will not be finalized until October 2025. | Yes | 2026
Olmsted Parkways Multi-Use Path System Section 3 | 2624 | 5-3709.00 | Design | 2025 | STBG-MPO | 111111 |  |  | Unlimited - ROW or U previously obligated | ROW Plan revisions are ongoing. Submittal ETA August 2025 to KYTC for review. | No
|  |  | ROW | 2026 | STBG-MPO | 942000 |  | Federal Funding Not Yet Authorized | Unlimited - ROW or U previously obligated | • ROW Phase anticipated FY26. | No
Olmsted Parkways Multi-Use Path System Section 6 | 2627 | 5-506.60 | ROW | 2025 | STBG-MPO | 500000 |  |  | Unlimited - ROW or U previously obligated | Submitted ROW Plans Revision on 7/30/2025. ROW Phase funding request anticipated by: 09/2025. | No
Olmsted Parkways Multi-Use Path System Section 7 | 2628 | 5-506.70 | ROW | 2025 | STBG-MPO | 484000 |  |  | Unlimited - ROW or U previously obligated | Submitted ROW Plans Revision on 7/30/2025. ROW Phase funding request anticipated by: 09/2025. | No
One-Way Street Conversion to Two-Way Phase 1 | 1809 | 5-470.00 | Design | 2025 | STBG-MPO | 219900 |  | Federal Funding Authorized | Unlimited - ROW or U previously obligated | 8/11/25 Kick-off meeting held July 25; Design underway; 7th and 8th St conversions to be done by Summer 2026 for TARC's onstreet transfer station | No
|  |  | Construction | 2026 | STBG-MPO | 10874000 |  | Federal Funding Not Yet Authorized | Unlimited - ROW or U previously obligated | C phase authorization anticipated FY26 | No
River Road Widening to Zorn Ave | 163 | 5-91.02 | Utilities | 2024 | STBG-MPO | 2800000 | 2023-12-20 | Federal Funding Authorized | Unlimited - ROW or U previously obligated |  | No
|  |  | Construction | 2025 | STBG-State | 4784907 |  |  | Unlimited - ROW or U previously obligated | Bid Document being reviewed by KyTC and plans are being revised to include revised typical section. | Yes | 2026
|  |  | Construction | 2025 | STBG-MPO | 14929715 |  |  | Unlimited - ROW or U previously obligated |  | Yes | 2026
River Road Multi-Modal Improvements | 2540 | 5-3217.00 | Construction | 2024 | TA-MPO | 2200000 | 2023-12-20 | Federal Funding Authorized |  | Construction in Progress - project completion is progressing toward a September finish date. | No
Stony Brook Drive Sidewalk Connector | 2594 | 5-571.00 | Construction | 2025 | STBG-MPO | 562000 |  |  | Unlimited - ROW or U previously obligated | Waiting for Construction Agreement to be Authorized by KYTC. | No
East Market Street Streetscape Improvements | 2064 | 5-8703.00 | Construction | 2024 | STBG-MPO | 8700000 | 2024-02-28 | Federal Funding Authorized |  | Construction continues - anticipating completion in November. | No
Buechel Bank Road | 381 | 5-8001.00 | Construction | 2025 | STBG-MPO | 6005000 |  | Federal Funding Not Yet Authorized | 1 Phase Shift Approved | Metro requesting add'l U phase funds for relocating the OH Electric and required tree removal. Once Metro obtains the signed agreement, a request for U funds will be submitted to KYTC. | Yes | Utilities FY2026 Construction FY2027
Northeast Louisville Loop MET, Section 3 Bircham Rd. to Beckley Creek Park | 2270 | 5-3030.30 | Design | 2025 | STBG-MPO | 445000 |  |  | 1 Phase Shift Approved | Design Fee Proposal forthcoming. that will include various bridge alternatives, no ETA at this time. | Yes | 2026
|  |  | ROW | 2026 | STBG-MPO | 636000 |  | Federal Funding Not Yet Authorized | 1 Phase Shift Approved |  | TBD
Olmsted Parkways Multi-Use Path System Section 2 | 2623 | 5-3709.00 | ROW | 2025 | STBG-MPO | 1451000 |  |  | Unlimited - ROW or U previously obligated | ROW Plan review with Metro is in progress. Submittal ETA August 2025 to KYTC for review. | Yes | 2026
|  |  | Utilities | 2026 | STBG-MPO | 100000 |  | Federal Funding Not Yet Authorized | Unlimited - ROW or U previously obligated | • Utilities Phase anticipated 2026. | No
River Road Extension | 1338 | 5-512.00 | Construction | 2026 | STBG-MPO | 9600000 |  |  | Unlimited - ROW or U previously obligated | Metro reviewed AECOM’s updated Final Drainage Folder submittal on 8-12-25 and submitting to KYTC for their review and approval; Metro scheduling internal meeting to address air rights and transition PM duties | Likely | 2027
Blanton Lane Sidewalk | 2920 | 5-3004.00 | ROW | 2025 | TA-MPO | 506880 | 2024-06-24 | Federal Funding Authorized | None | KYTC approved award of ROW acquisition contract to Lochner. PO has been issued and Lochner has started the work--as of 7/23/2025 | No
|  |  | Construction | 2026 | TA-MPO | 1159200 |  | Federal Funding Not Yet Authorized | 1 Phase Shift Approved |  | No
Crums Lane Sidewalk Phase 1 | 2896 | 5-3011.00 | ROW | 2025 | TA-MPO | 352978 | 2025-04-01 | Federal Funding Authorized | Unlimited - ROW or U previously obligated | Received NTP for ROW. Coordinating with KYTC-ROW to award of ROW acquisition contract to Lochner. | No
|  |  | Construction | 2026 | TA-MPO | 596120 |  | Federal Funding Not Yet Authorized | Unlimited - ROW or U previously obligated |  | No
Gagel Avenue Sidewalk | 2921 | 5-3040.00 | ROW | 2024 | TA-MPO | 440000 | 2024-02-28 | Federal Funding Authorized | None | KYTC approved award of ROW acquisition contract to Lochner. PO has been issued and Lochner has started the work--as of 7/23/2025. | No
|  |  | Construction | 2026 | TA-MPO | 1400000 |  | Federal Funding Not Yet Authorized | 1 Phase Shift Approved |  | No
Louisville Loop Shared Use Path - McNeely Lake Segment | 2539 | 5-3034.00 | Design | 2025 | TA-MPO | 242689 |  |  | None | Waiting on MOA agreement from KYTC for D phase funds- request on 6/30/2025. USACE permitting documentation ongoing - requested update on 7/9/2025. | Probably No
|  |  | Design | 2025 | STBG-MPO | 350000 |  |  | None
|  |  | Construction | 2027 | TA-MPO | 5040000 |  |  | 2 Phase Shifts Approved - next will require phase shift exception request approval | • Construction Phase anticipated by: FY27.
Bernheim Lane Sidewalk and Road Reconfiguration | 2895 | 5-3002.00 | Construction | 2025 | TA-MPO | 688000 | 2025-02-01 | Federal Funding Authorized | Unlimited - ROW or U previously obligated | Construction commencing; A recommendation to award contract to Libs Paving has been submitted to KYTC. Awaiting KYTC approval to proceed with contract execution. | No
Dodge Gap Jefferson Memorial Forest - Louisville Loop Shared Use Path | 2087 | 5-523.00 | Design | 2025 | CRP-MPO | 98354 |  |  |  | ROW plans: Gresham has established existing parcel lines so that ROW acquisition requirements can be determined. Additional funding: Project team will resubmit additional Design Scope/Fee proposal per KYTC comments. Metro will request a Time Extension for the project; current End Date is 9/30/25. Project team contemplates JI meeting for early September. | No
|  |  | ROW | 2025 | CRP-MPO | 111000 |  |  | 1 Phase Shift Approved |  | Yes | 2026
|  |  | Utilities | 2027 | CRP-MPO | 25000 |  | Federal Funding Not Yet Authorized | None | • Utilities Phase anticipated FY27. | No
Northeast Louisville Loop Section II (Eastwood Cut-off) | 2116 | 5-525.00 | Design | 2024 | CRP-MPO | 32000 | 2024-09-16 | Federal Funding Authorized | Unlimited - ROW or U previously obligated | • Let to construction with KYTC's 5-8952 project on 1/23/2025. KYTC is responsible for Construction Phase. | No
|  |  | Construction | 2025 | CRP-MPO | 826000 |  | Federal Funding Not Yet Authorized | Unlimited - ROW or U previously obligated | KYTC is leading construction oversight and is awaiting for LG&E to relocate utilities before construction can begin., anticipated late August | No
Ohio River Levee Trail Phase III | 1109 | 5-505.00 | Design | 2025 | CRP-MPO | 220000 |  |  | Unlimited - ROW or U previously obligated | Metro ROW Revision 1 - awaiting concurrence from KYTC; Project team developing scope/fee for NEPA reevaluations and additional Design phase scope/fee in order to request programmed FY25 Design phase funds. | Probably Yes
|  |  | Construction | 2025 | CRP-MPO | 6463000 |  | Federal Funding Not Yet Authorized | Unlimited - ROW or U previously obligated |  | Yes | 2026
Pond Creek Jefferson Memorial Forest - Louisville Loop Shared Use Path | 2086 | 5-522.00 | Design | 2024 | STBG-MPO | 135000 | 2024-07-09 | Federal Funding Authorized | None
|  |  | ROW | 2025 | CRP-MPO | 2000000 |  | Federal Funding Not Yet Authorized | 1 Phase Shift Approved | ROW Plans awaiting concurrence from KYTC. | No
|  |  | Utilities | 2027 | CRP-MPO | 55000 |  | Federal Funding Not Yet Authorized | None | • Utilities Phase anticipated FY27. | No
Westport Road Sidewalk through I-265 Interchange | 3121 | 5-598 | Design | 2025 | CRP-MPO | 45000 |  | Federal Funding Authorized | None | Final Design; Awaiting answers from KYTC Traffic regarding pedestrian crossings. | No
|  |  | Construction | 2026 | CRP-MPO | 895000 |  | Federal Funding Not Yet Authorized | None |  | No
Medora Jefferson Memorial Forest (IMF) - Louisville Loop Shared Use Path | 2092 | 5-524.00 | Construction | 2026 | TA-MPO | 4305000 |  | Federal Funding Not Yet Authorized | Unlimited - ROW or U previously obligated | Time Extension request submitted 8/4/2025. ROW phase activities continue. | No | C phase currently programmed in 2026
Jeffersontown
Bluegrass Commerce Park Bicycle/Pedestrian Trail Phase II | 2084 | 05-543.00 | Construction | 2025 | STBG-MPO | 2130000 | 2025-05-01 | Federal Funding Authorized | Unlimited - ROW or U previously obligated | MOA being executed. | no
Galene Drive/Sprowl Road Collector Extension | 3113 |  | Planning | 2026 | STBG-MPO | 264000 | 2026-01-01 | Federal Funding Not Yet Authorized | 1 Phase Shift Approved | no change | no
|  |  | Design | 2027 | STBG-MPO | 440000 |  | Federal Funding Not Yet Authorized | 1 Phase Shift Approved
|  |  | ROW | 2028 | STBG-MPO | 880000 |  | Federal Funding Not Yet Authorized | 1 Phase Shift Approved
|  |  | Utilities | 2029 | STBG-MPO | 440000 |  | Federal Funding Not Yet Authorized | None
|  |  | Construction | 2029 | STBG-MPO | 4400000 |  | Federal Funding Not Yet Authorized | None
Good Samaritan Bicycle & Pedestrian Trail Connector | 2082 | 05-486.00 | Construction | 2026 | STBG-MPO | 1460000 | 2026-06-01 | Federal Funding Not Yet Authorized | 3 Phase Shifts Approved - next will result in removal of MPO dedicated funds from the TIP | Working to address reivsed design issues. | no
Ruckriegel Parkway Sidewalk Improvement | 2619 | 5-198.00 | Construction | 2025 | STBG-MPO | 529008 |  | Federal Funding Not Yet Authorized | 2 Phase Shifts Approved - next will require phase shift exception request approval | No progress | yes | Need to confirm
Watterson Trail Signalized Improvements | 3110 |  | Design | 2025 | STBG-MPO | 132000 |  | Federal Funding Not Yet Authorized | 1 Phase Shift Approved | No progress | yes | Need to confirm
|  |  | Construction | 2026 | STBG-MPO | 880000 |  | Federal Funding Not Yet Authorized | 1 Phase Shift Approved | n/a
Watterson Trail Phase 2 | 1583 | 05-518.00 | Utilities | 2025 | STBG-MPO | 352000 | 2026-01-01 | Federal Funding Not Yet Authorized | Unlimited - ROW or U previously obligated | Still in R/W phase finishing acquition | no
|  |  | Construction | 2026 | STBG-MPO | 1232000 | 2026-01-01 | Federal Funding Not Yet Authorized | Unlimited - ROW or U previously obligated
Billtown-Eastvie w Collector Extension | 3111 |  | Design | 2026 | STBG-MPO | 310000 | 2026-01-01 | Federal Funding Not Yet Authorized | None | no change | no
|  |  | ROW | 2027 | STBG-MPO | 176000 |  | Federal Funding Not Yet Authorized | None | n/a | no
|  |  | Utilities | 2028 | STBG-MPO | 528000 |  | Federal Funding Not Yet Authorized | None | n/a | no
|  |  | Construction | 2029 | STBG-MPO | 660000 |  | Federal Funding Not Yet Authorized | None | n/a | no
Taylorsville Road Shared Use Path | 3109 |  | Design | 2025 | CRP-MPO | 132000 | 2026-06-26 | Federal Funding Not Yet Authorized | None | no change | no
|  |  | Construction | 2027 | CRP-MPO | 792000 | 2027-06-01 | Federal Funding Not Yet Authorized | None | n/a
KYTC
English Station Rd. | 188 | 5-353.00 | Construction | 2025 | STBG-MPO | 11368000 |  |  | Unlimited - ROW or U previously obligated | Requesting addit $2.8M U FY26 funds. C Letting est January 2026 | Yes | C from 25 to 26. Add $2.8M 26 U funds
KY 1931 Dixie Hwy to Doss HS | 2214 | 5-536.00 | Right of Way | 2025 | STBG-MPO | 1220000 |  |  | Unlimited - ROW or U previously obligated | Working on last parcel- railroad agreement. | Yes | R from 25 to 26
|  |  | Construction | 2025 | STBG-MPO | 10780000 |  | Federal Funding Not Yet Authorized | Unlimited - ROW or U previously obligated | Letting est Nov 2026 | Yes | C from 25 to 26
US 42 Jeff/Oldham Line to Ridgemoor Dr | 1271 | 5-441.00 | Design | 2025 | STBG-MPO | 448000 | 2025-07-01 |  | Unlimited - ROW or U previously obligated | D funds authorized July 2025 | no
|  |  | Utilities | 2025 | STBG-MPO | 1520000 |  |  | Unlimited - ROW or U previously obligated | Developing Utility Relocation Agreements and Schedule est start late 2026 | Yes | U from 25 to 26
|  |  | Construction | 2025 | STBG-MPO | 5020000 |  | Federal Funding Not Yet Authorized | Unlimited - ROW or U previously obligated | Consultant being hired to update plans for letting. Prev consultant closed office | Yes | C from 25 to 26
KY 2055 Mt Holly sidewalk | 3042 | 5-80110.00 | Design | 2024 | STBG-MPO | 120000 | 2024-08-30 |  | 1 Phase Shift Approved | Design funds authorized 8/30/24. | no
|  |  | ROW | 2025 | STBG-MPO | 24000 |  |  | 1 Phase Shift Approved | 6 mo delayed start in design phase caused similar delay in ROW start. | Yes | R from 25 to 26
|  |  | Utilities | 2025 | STBG-MPO | 24000 |  |  | None | 6 mo delayed start in design phase caused similar delay in Utility start. | Yes | U from 25 to 26
|  |  | Construction | 2026 | STBG-MPO | 120000 |  | Federal Funding Not Yet Authorized | None | Design underway. Letting date not set yet | No
KY 1065 Outer Loop | 436 | 5-80203.00 | Planning | 2024 | STBG-MPO | 200000 | 2024-09-16 | Federal Funding Authorized | 1 Phase Shift Approved | P funds authorized 9/16/24 | no
|  |  | Planning | 2025 | STBG-MPO | 150000 | 2025-05-01 | Federal Funding Authorized |  | P funds authorized 5/15/25 | no
KY 1932 Chenoweth Lane | 213 | 5-531.00 | Construction | 2025 | STBG-MPO | 3696000 | Aug 6 2025 |  | Unlimited - ROW or U previously obligated | Authorized and awarded to construction 8/6/25 $5,680,176 (80% SLO $4,544,141) | no
US 42 Safety and Mobility Improvements from the Harrods Creek Bridge to River Road | 230 | 5-972.00 | Design | 2024 | STBG-MPO | 928000 | 2024-02-28 | Federal Funding Authorized | None | Design funds authorized 2/28/24. | no
|  |  | ROW | 2025 | STBG-MPO | 664000 |  |  | None | Delayed design start. ROW start est Spring/Summer 2026 | Yes | R from 25 to 26
|  |  | Utilities | 2026 | STBG-MPO | 2080000 |  | Federal Funding Not Yet Authorized | None |  | no
|  |  | Construction | 2027 | STBG-MPO | 6008000 |  | Federal Funding Not Yet Authorized | None |  | no
KY 2050 Herr Lane | 3069 | 5-80200.00 | Design | 2024 | STBG-MPO | 335200 | 2024-03-13 | Federal Funding Authorized | None | Design funds authorized 3/13/24. | no
|  |  | ROW | 2025 | STBG-MPO | 44000 |  |  | None | ROW delayed 6 mo because of 6 mo delayed start in Design phase | Yes | R from 25 to 26
|  |  | Utilities | 2026 | STBG-MPO | 128000 |  | Federal Funding Not Yet Authorized | None |  | no
|  |  | Construction | 2027 | STBG-MPO | 1728000 |  | Federal Funding Not Yet Authorized | None |  | no
KY 864 Beulah Church Rd | 1879 | 5-481.00 | Construction | 2025 | STBG-MPO | 17288000 |  |  | Unlimited - ROW or U previously obligated | C letting delayed to Fall 26 because of delays in Utility relocation | Yes | C from 25 to 26
Mt. Washington
Historic Multi-Use Trail Segment C | 2479 | 5-3216.00 | Construction | 2025 | STBG-MPO | 2330799 | 2026-12-01 | Federal Funding Not Yet Authorized | Unlimited - ROW or U previously obligated | ROW under purchase. 1 parcel may need to go to condemnation. | Y | 2026
|  |  | Construction | 2025 | STBG-State | 118000 | 2026-12-01 | Federal Funding Not Yet Authorized | Unlimited - ROW or U previously obligated | ROW under purchase. 1 parcel may need to go to condemnation. | Y | 2026
Oldham County
Mattingly/Old LaGrange Rd Trail | 2981 | 5-589.00 | ROW | 2026 | STBG-MPO | 139000 |  | Federal Funding Not Yet Authorized | 2 Phase Shifts Approved - next will require phase shift exception request approval |  | No
|  |  | Utilities | 2027 | STBG-MPO | 139000 |  | Federal Funding Not Yet Authorized | 2 Phase Shifts Approved - next will require phase shift exception request approval |  | No
|  |  | Construction | 2028 | STBG-MPO | 500000 |  | Federal Funding Not Yet Authorized | 2 Phase Shifts Approved - next will require phase shift exception request approval |  | No
LaGrange Underpass West of LaGrange | 321 | 5-434.00 | Utilities | 2025 | STBG-MPO | 3100000 |  |  | Unlimited - ROW or U previously obligated | utility relocation underway | No
|  |  | Construction | 2025 | STBG-MPO | 11455000 |  |  | Unlimited - ROW or U previously obligated | Potential Oct. 2025 letting | No
Old LaGrange Road Improvements Oldham County Bicycle & Pedestrian Trail | 2175 | 5-410.01 | Right of Way | 2024 | STBG-MPO | 239676 | 2024-09-16 | Federal Funding Authorized |  | 01/08/2025 - NTP for R Phase, 08/21/2025 - Notice of Acquisition Letters sent, Completed Title Reports, and began appraisals. | No
|  |  | Right of Way | 2024 | STBG-State | 340324 | 2024-09-16 | Federal Funding Authorized |  | 01/08/2025 - NTP for R Phase, 08/21/2025 - Notice of Acquisition Letters sent, Completed Title Reports, and began appraisals. | No
|  |  | Utilities | 2025 | STBG-MPO | 750000 |  |  | Unlimited - ROW or U previously obligated | Reasonable (not aggressive) estimate for utilties April 2026 | No
|  |  | Construction | 2026 | STBG-MPO | 1458383 |  | Federal Funding Not Yet Authorized | Unlimited - ROW or U previously obligated |  | No
KY 22/Clore Lane Intersection Improvements | 3141 | 5-596.00 | Design | 2024 & 2025 | STBG-MPO | 336000 | 2024-04-19 | Federal Funding Authorized | None | July 1, 2025 – Teams meeting to discuss Phase 2 (Geotech and Structures). Provided cost to design culvert extension. July 11th - submitted Design Executive Summary. July 17th - KYTC will be structure design and geotech. July 18th - submitted revised Phase 2 design fee. | No
|  |  | ROW | 2025 | STBG-MPO | 733333 |  |  | None |  | No
|  |  | Utilities | 2026 | STBG-MPO | 622222 |  | Federal Funding Not Yet Authorized | None |  | No
|  |  | Construction | 2028 | STBG-MPO | 1888889 |  | Federal Funding Not Yet Authorized | None |  | No
Kenwood Road | 2615 | 5-588.00 | Design | 2024 | STBG-MPO | 325000 | Authorized 8/16/2023 | Federal Funding Authorized | None | Design Executive Summary (DES) approved and signed. Environmental studies (historic and noise) are anticipated to be complete in October. | No
|  |  | ROW | 2025 | STBG-MPO | 490000 |  |  | None |  | No
|  |  | Utilities | 2026 | STBG-MPO | 664063 |  | Federal Funding Not Yet Authorized | None |  | No
|  |  | Construction | 2027 | STBG-MPO | 2003125 |  | Federal Funding Not Yet Authorized | None |  | No
University of Louisville
2nd Street / 3rd Street / Museum Drive Intersection and Brandeis Avenue Pedestrian Improvements | 2982 | 5-581.00 | Design | 2025 | STBG-MPO | 225000 | 2025-09-01 | Federal Funding Not Yet Authorized | 2 Phase Shifts Approved - next will require phase shift exception request approval | Approval to enter phase 2 design | No
|  |  | Utilities | 2026 | STBG-MPO | 57280 | 2026-05-01 | Federal Funding Not Yet Authorized | 3 Phase Shifts Approved - next will result in removal of MPO dedicated funds from the TIP | None | No
|  |  | Construction | 2026 | STBG-MPO | 4008000 | 2026-05-01 | Federal Funding Not Yet Authorized | 3 Phase Shifts Approved - next will result in removal of MPO dedicated funds from the TIP | None | No
University of Louisville Pedestrian Improvements - Lighting | 2225 | 5-3218.00 | Construction | 2024 | STBG-MPO | 589640 | 2024-09-01 | Federal Funding Authorized |  | Advertised 2 times. Both came back with no acceptable bids. Will combine with ADA | No
University of Louisville Pedestrian Improvements - ADA Curb Cuts & Ramps | 2585 | 5-3220.00 | Construction | 2025 | STBG-MPO | 534568 | 2025-08-15 | Federal Funding Authorized |  | Combining with Lighting to advertise in August | No