## Sheet1
TOWN OF CLARKSVILLE
Project | KIPDA ID | STATE ID | Phase | Fiscal Year | Program | MPO Dedicated Federal Funds Programmed in the TIP | Project Phase Status | Actual or Estimated Date of Authorization | Federal Funding Amount Authorized (If Applicable) | Progress
Progress Way Improvements | 3018 | 2300582 | ROW | 2025 | STBG | 300000 | Federal Funding Authorized |  | 69815 | Offers for all 10 parcels have been sent out.
|  |  | U | 2027 | STBG | 700000 | Federal Funding Not Yet Authorized |  | N/A |  | Cost Estimate?
|  |  | CE | 2027 | STBG | 336000 | Federal Funding Not Yet Authorized |  | N/A | The project design was returned by INDOT with comments. JTL is working on these changes to resubmit. INDOT changed the letting date from March 2026 to December 2026.
|  |  | C | 2027 | STBG | 3200000 | Federal Funding Not Yet Authorized |  | N/A
Riverside Drive Reconstruction (Only fill out "Project Phase Status" Column & "Progress" Column) | 2393 | 1700725 | - | 2023 | - | - | Federal Funding Authorized | - | - | Project is on hold with INDOT until flood control gate is installed.
CLARK COUNTY
Project | KIPDA ID | STATE ID | Phase | Fiscal Year | Program | MPO Dedicated Federal Funds Programmed in TIP | Project Phase Status | Actual or Estimated Date of Authorization | Federal Funding Amount Authorized (if Applicable) | Progress In Past Quarter
CR 403 and Stacy Road Intersection Improvements* | 2549 | 1802805 | PE | 2020 | HSIP-MPO | 283500 |  | 2019-09-01
|  |  | U | 2024 | HSIP-MPO | 134029 | Federal Funding Authorized | 2024-05-01 | 229680 | Construction is complete. Will have to finish paper work to close project.
|  |  | C | 2024 | HSIP-MPO | 2147735 | Federal Funding Authorized | 2024-05-01 | 2002399
Henryville Sidewalk | 3180 | 2301302 | PE | 2025 | PROTECT | 144000 | Federal Funding Authorized |  | 144000
|  |  | PE | 2026 | Group III | 100000
[9 empty] | N/A | Amendment No.2 has been signed. Project on schedule and on budget | ROW phase to be funded by INDOT
|  |  | U | 2031 | INDOT Funds | 45000 | Federal Funding Not Yet Authorized |  | N/A
|  |  | CE | 2031 | INDOT Funds | 140400 | Federal Funding Not Yet Authorized |  | N/A
|  |  | CN | 2031 | INDOT Funds | 1072373 | Federal Funding Not Yet Authorized |  | N/A
Small Structure Inventory Study | 3330 | 2401845 | Planning | 2025 | Group III | 200000 |  |  |  | Field work 50-70% complete. Project scheduled to be complete mid-summer 2026
CR-311 and Sellersburg Improvements | 3364 | 2401840 | PE | 2026 | Group III | 600000 | Federal Funding Authorized
|  |  | PE | 2026 | CMAQ-MPO | 142733 | Federal Funding Not Yet Authorized |  | N/A
|  |  | ROW | 2028 | CMAQ-MPO | 500000 | Federal Funding Not Yet Authorized |  | N/A | MOU to be signed by Sellersburg and County in January 2026. Field work has started | KIPDA NOTE: Project has been approved as eligible for CMAQ funds. Pending Amendment 2 approval in the TIP in January.
|  |  | ROW | 2029 | CMAQ-MPO | 500000 | Federal Funding Not Yet Authorized |  | N/A
|  |  | U | 2030 | CMAQ-MPO | 500000 | Federal Funding Not Yet Authorized |  | N/A
Memphis Blue Lick Roadway Improvements | 3365 | 2401839 | Planning | 2026 | Group III | 100000 |  |  |  | Contract with StructurePoint is being prepared. Scope of project will be finalized with schedule in February 2026
CITY OF NEW ALBANY
Project | KIPDA ID | STATE ID | Phase | Fiscal Year | Program | MPO Dedicated Federal Funds Programmed in the TIP | Project Phase Status | Actual or Estimated Date of Authorization | Federal Funding Amount Authorized (If Applicable) | Progress
Graybrook Lane Extension | 3102 | 2301310 | PE | 2025 |  | 357109
|  |  | ROW | 2030 | STBG | 439200 | Federal Funding Not Yet Authorized |  | N/A
|  |  | U | TBD | TBD | 80000 |  |  | N/A | KIPDA NOTE: No federal funding for this phase at this time
|  |  | C | TBD | TBD | 2074949 |  |  |  | KIPDA NOTE: No federal funding for this phase at this time
Intersection of E. Spring St. & Beharrell Ave. | 3136 | 2301550 | PE | 2026 | HSIP | 252000 | Federal Funding Not Yet Authorized |  | N/A | RFP was approved, we are in process of getting the consultant contract approved/signed
|  |  | ROW | 2027 | HSIP | 400000 | Federal Funding Not Yet Authorized |  | N/A
|  |  | C | 2029 | HSIP | 1932000 | Federal Funding Not Yet Authorized |  | N/A
Slate Run Road Phase II | 3369 | 2401854 | PE | 2026 | Group III | 200000 |  |  |  | We have requested the PO from INDOT for this phase
|  |  | ROW | 2027 | TA-MPO | 402940 | Federal Funding Not Yet Authorized |  | N/A
|  |  | ROW | 2028 | TA-MPO | 1033060 | Federal Funding Not Yet Authorized |  | N/A
|  |  | CE | 2030 | TA-MPO | 400000 | Federal Funding Not Yet Authorized |  | N/A
|  |  | CN | 2030 | CRP-MPO | 4080000 | Federal Funding Not Yet Authorized |  | N/A
FLOYD COUNTY
Project | KIPDA ID | STATE ID | Phase | Fiscal Year | Program | MPO Dedicated Federal Funds Programmed in the TIP | Project Phase Status | Actual or Estimated Date of Authorization | Federal Funding Amount Authorized (If Applicable) | Progress
Bridge 51 (Blackiston Mill Road) Replacement Project | 1558 | 1700788 | PE | 2024 | STBG-MPO | 202688 | Federal Funding Authorized | 2024-03-02 | 202688
|  |  | ROW | 2024 | STBG-MPO | 997312 | Federal Funding Authorized | 2024-05-08 | 997312
|  |  | CE | 2026 | STBG-MPO | 675891 | Federal Funding Authorized | 2025-12-11
|  |  | CN | 2026 | STBG-MPO | 5632428 | Federal Funding Authorized | 2025-12-11 |  | Letting occurred Dec. 10, Low bid was $8,348,999. INDOT has invoiced County for match, payment by end of January
|  |  | CN | 2026 | Local Bridge | 1669799 | Federal Funding Authorized | 2025-12-18
Bridge 38 - (Baylor Wissman) Replacement | 3366 | 2401835 | PE | 2026 | Group III | 360000 |  |  |  | No progess last quarter, NTP and PO received early January.
|  |  | ROW | 2027 | STBG-MPO | 32000 | Federal Funding Not Yet Authorized
|  |  | CE | 2029 | STBG-MPO | 276000 | Federal Funding Not Yet Authorized
|  |  | CN | 2029 | STBG-MPO | 1852000 | Federal Funding Not Yet Authorized
Baylor Wissman Hilltop | 3367 | 2401834 | PE | 2026 | Group III | 161481 |  |  |  | No progess last quarter, NTP and PO received early January.
|  |  | ROW | 2029 | HSIP-MPO | 256460 | Federal Funding Not Yet Authorized |  |  |  | KIPDA NOTE: This project needs to get HSIP approval from INDOT. KIPDA will work with the county for application submission
|  |  | CE | TBD | TBD | 257620 | Federal Funding Not Yet Authorized
|  |  | CN | TBD | TBD | 833320 | Federal Funding Not Yet Authorized
Highway 150 Break Highlander Point | 3368 | 2401836 | PE | 2026 | Group III | 315000 |  |  |  | No progess last quarter, NTP and PO received early January.
|  |  | CE | 2028 | STBG-MPO | 402029 | Federal Funding Not Yet Authorized
|  |  | CN | 2028 | STBG-MPO | 2680191 | Federal Funding Not Yet Authorized
Charlestown Road Corridor Complete Street Multi Use Trail | 2128 | 1400550 | CE | 2025 | HSIP-State | 435494 |  |  |  | Project about 2 weeks from completion, shut down for winter.
|  |  | CE | 2025 | HSIP-MPO | 264937 | Federal Funding Authorized
|  |  | C | 2025 | HSIP-State | 2903293