## LMG Updates 2026-02
LOUISVILLE METRO
Project | KIPDA ID | STATE ID | Phase | Fiscal Year | Program | MPO Dedicated Federal Funds | Actual or Estimated Date of Authorization | Project Phase Status | Phase Shift History | Progress Since Last Meeting (8/25) | Need a phase shift? (Yes or No) | If so, what fiscal year will you need to shift to? (Be cognicent of your "Phase Shift History")
AB Sawyer Greenway Shared Use Path | 1662 | 5-529.00 | Construction | 2026 | STBG-MPO | 3555600 |  |  | Unlimited - ROW or U previously obligated | Compiling items for PDS checklist; Ongoing coordination with KY Div of Water; Conditional letter of map revision (CLOMR) submitted to Kentucky Divison of Water. Awaiting their approval. | Likely | 2027
Bicycle & Pedestrian Education, Encouragement, Enforcement & Evaluation | 337 | 5-965.15 | Program | 2026+ | STBG-MPO | 150000 |  |  | None |  | No | n/a
Cooper Chapel Rd. Phase 3 | 223 | 05-404.01 | Design | 2024 | STBG-MPO | 65080 |  | Federal Funding Authorized | Unlimited - ROW or U previously obligated | Metro DOT submitted a fee proposal (HDR) to KYTC for add'l design for review and approval on 2-9-26; KYTC is currently reviewing the proposal. KYTC working on the audit for the project Right-of-Way Certification; U phase likely to be pushed to FY27 | No | n/a
|  |  | Right of Way | 2024 | STBG-MPO | 779400 |  | Federal Funding Authorized | Unlimited - ROW or U previously obligated |  | No | n/a | KIPDA Comment: Where are we at on ROW aquisition?
|  |  | Utilities | 2026 | STBG-MPO | 2098000 |  |  | Unlimited - ROW or U previously obligated |  | Likely | 2027
|  |  | Construction | 2027 | STBG-MPO | 18153600 |  | Federal Funding Not Yet Authorized | Unlimited - ROW or U previously obligated |  | Likely | 2028
I-65/Brook St Ramp | 224 | 05-378.10 & 05-80521.00 | Utilities | 2026 | STBG-MPO | 640000 |  | Federal Funding Not Yet Authorized | 2 Phase Shifts Approved - next will require phase shift exception request approval | Anticipate KYTC will takeover this project; Still awaiting Highway Plan to see if project recveives funds. | Likely |  | KIPDA Comment: Still waiting to see if this project receives any funds via the KYTC six-year highway plan. If not, then we may need to make some decisions about this project before the upcoming CFP.
Kentuckiana Air Education | 369 | 5-244.00 | Program | 2025+ | STBG-MPO | 200000 |  |  | None
North Hubbards Ln. | 3233 | 5-479.10 | Construction | 2026 | STBG-MPO | 5809589 |  |  | Unlimited - ROW or U previously obligated | Final Plans and cost estimate submitted by Gresham Smith to KYTC for approval on 2-24-26. Metro DOT submitted an application for the required Encroachment Permit to KYTC on 2-24-26. Metro DOT awaiting a fee proposal from Michael Baker for Construction Inspection Services. | No
Northeast Louisville Loop MET, Section 2 Beckley Station to Bircham Rd. | 2269 | 5-3030.20 | Construction | 2025 | STBG-MPO | 2080000 | 2025-02-17 | Federal Funding Authorized | Unlimited - ROW or U previously obligated | Construction still in progress with a contractual completion date of 7-31-26. AECOM/Metro DOT submitted a design change for review to KYTC on 2-24-26. The change is required in order to avoid impact to an existing steel strain pole that was placed along the trail route after the plans had been finalized. | No | n/a
Olmsted Parkways Multi-Use Path System Section 1 | 2622 | 5-3709.00 | Construction | 2026 | STBG-MPO | 2750000 |  |  | Unlimited - ROW or U previously obligated | Metro awaiting MOA for additional Section 3 STBG Design funds, Section 1 ROW funds, and Section 2 ROW funds. Draft MOA is in process at KYTC CO. | Yes | 2027
Olmsted Parkways Multi-Use Path System Section 2 | 2623 | 5-3709.00 | ROW | 2026 | STBG-MPO | 1451000 |  |  | Unlimited - ROW or U previously obligated | Metro awaiting MOA for Section 2 ROW funds. Draft MOA is in process at KYTC CO.
|  |  | Utilities | 2026 | STBG-MPO | 100000 |  | Federal Funding Not Yet Authorized | Unlimited - ROW or U previously obligated
Olmsted Parkways Multi-Use Path System Section 3 | 2624 | 5-3709.00 | Design | 2025 | STBG-MPO | 111111 |  |  | Unlimited - ROW or U previously obligated | Metro awaiting MOA for additional STBG Design funds - tied to authorization of ROW funds for Sections 1-2; ROW Plan revisions are ongoing; Draft MOA is in process at KYTC CO. |  |  | KIPDA Comment: Need to shift these design funds to FY26 in the TIP. Please submit an expedited project application so we can get that done. May have already authorized these funds on 1.8.26. We just need to update that in the TIP.
|  |  | ROW | 2026 | STBG-MPO | 942000 |  | Federal Funding Not Yet Authorized | Unlimited - ROW or U previously obligated |  | Likely | 2027
Olmsted Parkways Multi-Use Path System Section 4 | 2625 | 5-506.00 | ROW | 2026 | STBG-MPO | 1977000 |  |  | Unlimited - ROW or U previously obligated | ROW plan submitted to KYTC. Review expected to be complete April 2026. | No
|  |  | Utilities | 2027 | STBG-MPO | 100000 |  | Federal Funding Not Yet Authorized | Unlimited - ROW or U previously obligated
Olmsted Parkways Multi-Use Path System Section 5 | 2626 | 5-506.00 | ROW | 2027 | STBG-MPO | 2146000 |  | Federal Funding Not Yet Authorized | Unlimited - ROW or U previously obligated | ROW plan revisions ongoing; expect submittal to KYTC for review in May 2026; ROW funds unavailable until FY27 | No | n/a
Olmsted Parkways Multi-Use Path System Section 6 | 2627 | 5-506.60 | ROW | 2025 | STBG-MPO | 53600 | 9.5.25 | Federal Funding Authorized | Unlimited - ROW or U previously obligated | Funds just recently authorized for ROW; ROW kick-off on 2/12/26 | No | n/a
|  |  | Utilities | 2027 | STBG-MPO | 515200
Olmsted Parkways Multi-Use Path System Section 7 | 2628 | 5-506.70 | ROW | 2025 | STBG-MPO | 111200 | 9.5.25 | Federal Funding Authorized | Unlimited - ROW or U previously obligated | ROW kickoff meeting with KYTC D5 at Louisville Metro was held on 2/12/26. | No | n/a
|  |  | Utilities | 2027 | STBG-MPO | 145200
One-Way Street Conversion to Two-Way Phase 1 | 1809 | 5-470.00 | Design | 2025 | STBG-MPO | 80000 | 5.29.25 | Federal Funding Authorized | Unlimited - ROW or U previously obligated | Currently refining design submitted by HDR. 7th and 8th Sts coordinating with TARC and PARC to refine striping plan ahead of new on-street transit station; 7th/8th likely to be one bid package in Spring 2026; remaining corridors will be a separate bid package anticipated Fall 2026 | no | n/a
|  |  | Construction | 2026 | STBG-MPO | 10874000 |  | Federal Funding Not Yet Authorized | Unlimited - ROW or U previously obligated |  | tbd
River Road Widening to Zorn Ave | 163 | 5-91.02 | Utilities | 2024 | STBG-MPO | 2800000 | 2023-12-20 | Federal Funding Authorized | Unlimited - ROW or U previously obligated | Finalizing project development checklist; construction authorization process to begin soon after. Metro and River Road Business Association have reached an agreement to delay construction until after Derby to minimize disruptions. | No | n/a
|  |  | Construction | 2026 | STBG-State | 4784907 |  |  | Unlimited - ROW or U previously obligated |  | No | n/a
|  |  | Construction | 2026 | STBG-MPO | 18929715 |  |  | Unlimited - ROW or U previously obligated |  | No | n/a
River Road Multi-Modal Improvements | 2540 | 5-3217.00 | Construction | 2024 | TA-MPO | 2200000 | 2023-12-20 | Federal Funding Authorized |  |  | No | n/a
|  |  | Construction | 2026 | STBG-MPO | 400000 |  | Federal Funding Authorized |  | Electrical has been installed as of 2/10/2026. Awaiting final invoice which will closeout project. | No | n/a
Stony Brook Drive Sidewalk Connector | 2594 | 5-571.00 | Construction | 2026 | STBG-MPO | 562000 |  |  | Unlimited - ROW or U previously obligated | Project dvelopment checklist has been finished; awaiting KYTC plan review. | No | n/a
East Market Street Streetscape Improvements | 2064 | 5-8703.00 | Construction | 2024 | STBG-MPO | 8700000 | 2024-02-28 | Federal Funding Authorized |  | In the process of project closeout. Minor sidewalk repairs and tree maintenance to be repaired throughout spring 2026. | No | n/a
Buechel Bank Road | 381 | 5-8001.00 | Utilities | 2026 | STBG-MPO | 1600000 |  | Federal Funding Not Yet Authorized | None | Metro DOT provided NTP to LG&E on 2-13-26 regarding the overhead electric work. LWC was given NTP on 2-13-26 to aquire the needed easements for the waterline relocation work that will be completed by the roadway contractor. Gresham Smith was given NTP on 2-13-26 for additional design services. | No | n/a
|  |  | Construction | 2027 | STBG-MPO | 6005000 |  |  | 2 Phase Shifts Approved - next will require phase shift exception request approval |  | tbd
Northeast Louisville Loop MET, Section 3 Bircham Rd. to Beckley Creek Park | 2270 | 5-3030.30 | Design | 2026 | STBG-MPO | 445000 |  |  | 2 Phase Shifts Approved - next will require phase shift exception request approval | AECOM revising a fee proposal for the bridge and trail design, though awaiting on guidance from KYTC regarding the hours needed for the NEPA re-evaluation. |  |  | KIPDA Comment: KIPDA staff would not recommend a phase shift exception request for this design phase. Needs to get authorized this year or funding should be shifted to other project needs within KIPDA's funding program
|  |  | ROW | 2026 | STBG-MPO | 636000 |  | Federal Funding Not Yet Authorized | 1 Phase Shift Approved |  | likely | 2027
|  |  | Utilities | 2027 | STBG-MPO | 20000 |  | Federal Funding Not Yet Authorized | None |  | tbd
|  |  | Construction | 2029 | STBG-MPO | 3200000 |  | Federal Funding Not Yet Authorized | None |  | No | n/a
River Road Extension | 1338 | 5-512.00 | Construction | 2026 | STBG-MPO | 9600000 |  |  | Unlimited - ROW or U previously obligated | Metro DOT still awaiting final documentation from MSD regarding the need for a Floodplain Variance. AECOM working on the required 408 Permit. Metro DOT still awaiting guidance from KYTC/FHWA regarding "air-rights". | Yes | 2027
Reimagine 9th Street | 2733 | 5-80250.00 | Construction | 2026 | STBG-MPO | 3896000 |  |  | None | Chestnut/Muhammad Ali OWTW - Signal work and signage installation continuing. Descision was made to mill and resurface existing corridor with CPF funds. Working on admin and amendment to adjust project descriptions and create new projects; Reimagine 9th Street - Final plans completion scheduled for May 2026. |  |  | KIPDA COMMENT: This project obviously has other funding, but I have only listed KIPDA's MPO-dedicated funding portion here
Blanton Lane Sidewalk | 2920 | 5-3004.00 | ROW | 2025 | TA-MPO | 506880 | 2024-06-24 | Federal Funding Authorized | Unlimited - ROW or U previously obligated | Acquisition process underway | No | n/a
|  |  | Construction | 2026 | TA-MPO | 1159200 |  |  | Unlimited - ROW or U previously obligated |  | likely | 2027
Crums Lane Sidewalk Phase 1 | 2896 | 5-3011.00 | ROW | 2025 | TA-MPO | 352978 | 2025-04-01 | Federal Funding Authorized | Unlimited - ROW or U previously obligated | Acquisition process underway | No | n/a
|  |  | Construction | 2026 | TA-MPO | 596120 |  |  | Unlimited - ROW or U previously obligated |  | likely | 2027
Gagel Avenue Sidewalk | 2921 | 5-3040.00 | ROW | 2024 | TA-MPO | 440000 | 2024-02-28 | Federal Funding Authorized | Unlimited - ROW or U previously obligated | Acquisition process underway | No | n/a
|  |  | Construction | 2026 | TA-MPO | 1400000 |  |  | Unlimited - ROW or U previously obligated |  | likely | 2027
Louisville Loop Shared Use Path - McNeely Lake Segment | 2539 | 5-3034.00 | Design | 2025 | TA-MPO | 242689 | 8.25.25 | Federal Funding Authorized | None | Metro awaiting MOA for additional STBG Design funds. Next meeting w/OLP scheduled for 3/16/26. Next progress meeting is 4/2/2026. | No | n/a
|  |  | Design | 2025 | STBG-MPO | 350000 | 8.25.25 | Federal Funding Authorized | None |  | No | n/a
|  |  | Construction | 2027 | TA-MPO | 5040000 |  |  | 2 Phase Shifts Approved - next will require phase shift exception request approval |  | tbd
Bernheim Lane Sidewalk and Road Reconfiguration | 2895 | 5-3002.00 | Construction | 2025 | TA-MPO | 688000 | 2025-02-01 | Federal Funding Authorized | Unlimited - ROW or U previously obligated | Construction complete; Walkthrough inspection to be scheduled in late March 2026 | No | n/a
Dodge Gap Jefferson Memorial Forest - Louisville Loop Shared Use Path | 2087 | 5-523.00 | Design | 2025 | CRP-MPO | 98354 | 9.22.25 | Federal Funding Authorized |  | Metro received MOA for add'l design services in Jan 2026; reviewed and commented on preliminary structures submittal; Parks is negotiating removal of wetlands easement from parcel needed for stream project (that does NOT impact or involve the Loop project) that will allow the stream project to advance through Design phase. | No | n/a
|  |  | ROW | 2026 | CRP-MPO | 111000 |  |  | 2 Phase Shifts Approved - next will require phase shift exception request approval |  | Likely | 2027
|  |  | Utilities | 2027 | CRP-MPO | 25000 |  | Federal Funding Not Yet Authorized | None |  | tbd
Northeast Louisville Loop Section II (Eastwood Cut-off) | 2116 | 5-525.00 | Design | 2024 | CRP-MPO | 32000 | 2024-09-16 | Federal Funding Authorized | Unlimited - ROW or U previously obligated |  | No | n/a
|  |  | Construction | 2025 | CRP-MPO | 826000 | 2.11.25 | Federal Funding Authorized | Unlimited - ROW or U previously obligated | Start of construction for 5-525 and 5-8952 is late February 2026; Louisville Paving has begun preliminary work on this project. | No | n/a | Only authorized $480,000 of CRP funds. Extra funds remaining with project until next CFP.
Ohio River Levee Trail Phase III | 1109 | 5-505.00 | Design | 2026 | CRP-MPO | 220000 |  |  | Unlimited - ROW or U previously obligated | Metro resubmitted ROW Revision 2 on 2/18/26 to KYTC for review; Metro continues negotiating Additional Design scope/fee with consultant. Metro anticipates submitting Additional Design scope/fee proposal in mid March 2026. | No | n/a
|  |  | Construction | 2026 | CRP-MPO | 6463000 |  |  | Unlimited - ROW or U previously obligated |  | likely | 2027
Pond Creek Jefferson Memorial Forest - Louisville Loop Shared Use Path | 2086 | 5-522.00 | Design | 2024 | STBG-MPO | 135000 | 2024-07-09 | Federal Funding Authorized | Unlimited - ROW or U previously obligated |  | No | n/a
|  |  | ROW | 2025 | CRP-MPO | 680000 | 8.28.25 | Federal Funding Authorized | Unlimited - ROW or U previously obligated | ROW phase activities are underway - kickoff in Jan 2026; Consultant team submitted Stage II final bridge plans; team forecasts final plans submittal by late April 2026. | No | n/a
|  |  | Utilities | 2027 | CRP-MPO | 55000 |  | Federal Funding Not Yet Authorized | Unlimited - ROW or U previously obligated |  | tbd
Westport Road Sidewalk through I-265 Interchange | 3121 | 5-598.00 | Design | 2025 | CRP-MPO | 45000 | 2.28.25 | Federal Funding Authorized | None | D5 Traffic plans to set up a meeting with Central Office and the Metro project team to discuss ped crossing treatments. | No | n/a
|  |  | Construction | 2026 | CRP-MPO | 895000 |  | Federal Funding Not Yet Authorized | None | Program Management corrected funding authorization from STBG to CRP funds. | tbd
Medora Jefferson Memorial Forest (IMF) - Louisville Loop Shared Use Path | 2092 | 5-524.00 | Construction | 2026 | TA-MPO | 4305000 |  | Federal Funding Not Yet Authorized | Unlimited - ROW or U previously obligated | ROW phase is still ongoing. | likely | 2027
Northeast Louisville Loop MET Section 4 Beckley Creek Park to Eastwood Cuttoff | 2271 | 5-3030.40 | Construction | 2026 | STBG-MPO | 1103520 |  | Federal Funding Not Yet Authorized | Unlimited - ROW or U previously obligated | Metro DOT still awaiting the mortgage release for Parcel 33 in order to submit for R/W Certification.
Ohio River Valley NE Bike/Ped Improvements Phase 1 (Louisville Loop) | 2979 | 5-3036.00 | Construction | 2026 | STBG-MPO | 640000 |  |  | None | AECOM preparing plans for a Joint Inspection Meeting for the trailhead/parking lot portion of the project. Metro DOT submitted application for Clearinghouse Letter on 2-4-26. 2. Metro DOT finalizing a submittal to LWC documenting past correspondences and decisions regarding the trail on LWC property. 3. Metro DOT received the fully executed Supplemental MOA #3 and NTP for the Wayfinding/Signage specs and design updates. | no | n/a
|  |  | Construction | 2029 | CRP-MPO | 3760000 |  | Federal Funding Not Yet Authorized | None |  | no | n/a
Ohio River Valley NE Bike/Ped Improvements Phase II (Louisville Loop) | 2980 | 5-584.00 | ROW | 2026 | CRP-MPO | 88000 |  |  | None | Project team held Phase II Design kickoff meeting with KYTC D5 on 2/6/26. Next progress meeting scheduled on 3/17/26. | tbd | 2027
|  |  | Utilities | 2026 | CRP-MPO | 28000 |  |  | None |  | tbd | 2027
|  |  | Construction | 2028 | CRP-MPO | 2696000 |  | Federal Funding Not Yet Authorized | None
Dixie Highway Streetscape - Maple to Garland | 3308 | 5-478.81 | ROW | 2026 | CRP-MPO | 48000 |  |  | 1 Phase Shift Approved | Final plans including signal design revised and re-sent to D5 for review /approval Awaiting Authorization of ROW phase/funds - submitted to OLP 10/16/25 | no | n/a
|  |  | Construction | 2026 | CRP-MPO | 1743000 |  |  | None |  | Yes | 2027
South Hubbards Lane | 3024 | 5-479.20 | Construction | 2027 | TA-MPO | 500000 |  | Federal Funding Not Yet Authorized | None | Continued effort: Gresham Smith to begin design after Section 1 plans are reviewed and approved by KYTC for the PDC. | No | n/a
BULLITT COUNTY
Project | KIPDA ID | STATE ID | Phase | Fiscal Year (2023 - 2026) | Program | MPO Dedicated Federal Funds | Actual or Estimated Date of Authorization | Project Phase Status | Phase Shift History | Progress Since Last Meeting | Need a phase shift? (Yes or No) | If so, what fiscal year will you need to shift to? (Be cognicent of your "Phase Shift History")
US 31E to KY 2706 | 3414 |  | Planning | 2026 | STBG-MPO | 200000 |  |  | None | In process of selecting engineering firm | no | n/a
KYTC
Project | KIPDA ID | STATE ID | Phase | Fiscal Year (2023 - 2026 Only) | Program | MPO Dedicated Federal Funds | Actual or Estimated Date of Authorization | Project Phase Status | Phase Shift History | Progress Since Last Meeting | Need a phase shift? (Yes or No) | If so, what fiscal year will you need to shift to? (Be cognicent of your "Phase Shift History")
English Station Rd. | 188 | 5-353.00 | Design | 2026 | STBG-MPO | 256000 | 2026-03-11 | Federal Funding Authorized | Unlimited - ROW or U previously obligated | preparing plans for 10/22/26 letting | no
|  |  | Utilities | 2026 | STBG-MPO | 2800000 |  |  | Unlimited - ROW or U previously obligated | Early U relocation underway. Expect to authorize these U funds with C phase | no
|  |  | Construction | 2026 | STBG-MPO | 11368000 |  | Federal Funding Not Yet Authorized | Unlimited - ROW or U previously obligated | 10/22/26 letting anticipated | no
KY 1931 Dixie Hwy to Doss HS | 2214 | 5-536.00 | Right of Way | 2026 | STBG-MPO | 1220000 |  |  | Unlimited - ROW or U previously obligated | All ROW clear except rail - still working and may need these addit. ROW funds | no
|  |  | Construction | 2028 | STBG-MPO | 10780000 |  | Federal Funding Not Yet Authorized | Unlimited - ROW or U previously obligated | Clearing/coordinating with Utilities now. Marathon Gas may require added U funds for facility encasement. No letting date established yet | no
US 42 Jeff/Oldham Line to Ridgemoor Dr | 1271 | 5-441.00 | Design | 2025 | STBG-MPO | 448000 | 2025-07-10 06:00 | Federal Funding Authorized | Unlimited - ROW or U previously obligated | Design funds authorized 7.10.25 | no
|  |  | Utilities | 2026 | STBG-MPO | 1520000 |  |  | Unlimited - ROW or U previously obligated | New design consultant hired 2025 - new estimate and final plans being developed. | no
|  |  | Construction | 2028 | STBG-MPO | 5020000 |  | Federal Funding Not Yet Authorized | Unlimited - ROW or U previously obligated | New design consultant hired 2025 - new estimate and final plans being developed. | no
KY 2055 Mt Holly sidewalk | 3042 | 5-80110.00 | Design | 2024 | STBG-MPO | 120000 | 2024-08-30 |  | 1 Phase Shift Approved | Design funds authorized 8/30/24. Additional D funds will be requested Spring 2026 for final design - $212,000 fed SLO | no
|  |  | ROW | 2026 | STBG-MPO | 24000 |  |  | 2 Phase Shift Approved |  | no
|  |  | Utilities | 2026 | STBG-MPO | 24000 |  |  | 1 Phase Shift Approved |  | no
|  |  | Construction | 2026 | STBG-MPO | 120000 |  | Federal Funding Not Yet Authorized | None | Additional C funds will be requested Spring 2026 - $870,000 fed SLO | no
KY 1065 Outer Loop | 436 | 5-80203.00 | Planning | 2024 | STBG-MPO | 200000 | 2024-09-16 | Federal Funding Authorized | 1 Phase Shift Approved | Study to conclude Fall 2026 | no
|  |  | Planning | 2025 | STBG-MPO | 150000 | 2025-05-01 | Federal Funding Authorized |  | Study to conclude Fall 2026 | no
KY 1932 Chenoweth Lane | 213 | 5-531.00 | Construction | 2025 | STBG-MPO | 3696000 | 2025-08-01 | Federal Funding Authorized | Unlimited - ROW or U previously obligated | Authorized 12/22/25 $3,696,000 SLO C phase | no
US 42 Safety and Mobility Improvements from the Harrods Creek Bridge to River Road | 230 | 5-972.00 | Design | 2024 | STBG-MPO | 800000 | 2024-02-28 | Federal Funding Authorized | None | Design funds authorized 2/28/24. | no
|  |  | Design | 2026 | STBG-MPO | 128000 |  |  |  | Addit D auth request underway Spring 2026 $128,000 SLO | no
|  |  | ROW | 2026 | STBG-MPO | 664000 |  |  | None | Update to ROW funding needed - addit $3,624,000 fed SLO 2026 | no
|  |  | Utilities | 2026 | STBG-MPO | 2080000 |  | Federal Funding Not Yet Authorized | None | Update to U funding needed - addit $1,776,000 fed SLO 2026 | no
|  |  | Construction | 2027 | STBG-MPO | 6008000 |  | Federal Funding Not Yet Authorized | None | Update to C funding needed - addit $4,664,000 fed SLO 2027 | no
KY 2050 Herr Lane | 3069 | 5-80200.00 | Design | 2024 | STBG-MPO | 335200 | 2024-03-13 | Federal Funding Authorized | None | Design funds authorized 3/13/24. | no
|  |  | ROW | 2026 | STBG-MPO | 44000 |  |  | 1 Phase Shift Approved | Update to ROW funding needed - addit $420,000 fed SLO 2026 | no
|  |  | Utilities | 2026 | STBG-MPO | 128000 |  |  | None | Update to U funding needed - addit $1,496,000 fed SLO 2026 | no
|  |  | Construction | 2027 | STBG-MPO | 1728000 |  | Federal Funding Not Yet Authorized | None | Update to C funding needed - addit $560,000 fed SLO 2027 | no
KY 864 Beulah Church Rd | 1879 | 5-481.00 | Design | 2026 | STBG-MPO | 250000 |  |  | Unlimited - ROW or U previously obligated | Addit D auth request underway Spring 2026 $250,000 SLO | no
|  |  | Utilities | 2026 | STBG-MPO | 200000 |  |  | Unlimited - ROW or U previously obligated | Addit U auth request underway Spring 2026 $200,000 SLO | no
|  |  | Construction | 2026 | STBG-MPO | 17288000 |  |  | Unlimited - ROW or U previously obligated | Letting est 6/25/2026 | no
Oldham County
Project | KIPDA ID | STATE ID | Phase | Fiscal Year (2023 - 2026) | Program | MPO Dedicated Federal Funds | Actual or Estimated Date of Authorization | Project Phase Status | Phase Shift History | Progress Since Last Meeting | Need a phase shift? (Yes or No) | If so, what fiscal year will you need to shift to? (Be cognicent of your "Phase Shift History")
Mattingly/Old LaGrange Rd Trail | 2981 | 5-589.00 | Design | 2026 | STBG-MPO | 260000 |  |  |  | Proposed Manhours were submitted by AECOM to KYTC on 06/16/25. Donna Hardin - Disrict 5 EC advised NEPA approval is pending completion of Section 106 by KYTC DEA on 02/13/26
|  |  | ROW | 2026 | STBG-MPO | 139000 |  |  | 2 Phase Shifts Approved - next will require phase shift exception request approval
|  |  | Utilities | 2027 | STBG-MPO | 139000 |  | Federal Funding Not Yet Authorized | 2 Phase Shifts Approved - next will require phase shift exception request approval
|  |  | Construction | 2028 | STBG-MPO | 500000 |  | Federal Funding Not Yet Authorized | 2 Phase Shifts Approved - next will require phase shift exception request approval
LaGrange Underpass West of LaGrange | 321 | 5-434.00 | Design | 2026 | STBG-MPO | 120000 |  |  | Unlimited - ROW or U previously obligated
|  |  | Utilities | 2025 | STBG-MPO | 1012000 | 2025-07-01 | Federal Funding Authorized | Unlimited - ROW or U previously obligated |  | no
|  |  | Utilities | 2026 | STBG-MPO | 2088000 |  |  | Unlimited - ROW or U previously obligated | ongoing
|  |  | Construction | 2026 | STBG-MPO | 22625000 |  |  | Unlimited - ROW or U previously obligated | Construction Documents advertised for March 26, 2026 construction letting
Old LaGrange Road Improvements Oldham County Bicycle & Pedestrian Trail | 2175 | 5-410.01 | Right of Way | 2024 | STBG-MPO | 239676 | 2024-09-16 | Federal Funding Authorized | Unlimited - ROW or U previously obligated | ROW acquisition on-going | no
|  |  | Right of Way | 2024 | STBG-State | 340324 | 2024-09-16 | Federal Funding Authorized | Unlimited - ROW or U previously obligated | ROW acquisition on-going | no
|  |  | Utilities | 2026 | STBG-MPO | 750000 |  |  | Unlimited - ROW or U previously obligated
|  |  | Construction | 2026 | STBG-MPO | 1458383 |  |  | Unlimited - ROW or U previously obligated
KY 22/Clore Lane Intersection Improvements | 3141 | 5-596.00 | Design | 2024 | STBG-MPO | 188889 | 2024-04-19 | Federal Funding Authorized | None | Phase 1 Design is complete (April 2025) and a preferred alternative selected.
|  |  | Design | 2026 | STBG-MPO | 196569 |  |  |  | Phase 2: Geotechnical staking and drilling occurred in December 2025. Final surveys to be performed in February 2026.
|  |  | ROW | 2026 | STBG-MPO | 733333 |  |  | 1 Phase Shift Approved
|  |  | Utilities | 2026 | STBG-MPO | 622222 |  |  | None
|  |  | Construction | 2028 | STBG-MPO | 1888889 |  | Federal Funding Not Yet Authorized | None
Kenwood Road | 2615 | 5-588.00 | Design | 2024 | STBG-MPO | 325000 | Authorized 8/16/2023 | Federal Funding Authorized | None | Environmental Document (CE Level 1) Complete | no
|  |  | ROW | 2026 | STBG-MPO | 490000 |  |  | 1 Phase Shift Approved
|  |  | Utilities | 2026 | STBG-MPO | 664063 |  |  | None
|  |  | Construction | 2027 | STBG-MPO | 2003125 |  | Federal Funding Not Yet Authorized | None
University of Louisville
Project | KIPDA ID | STATE ID | Phase | Fiscal Year (2023 - 2026) | Program | MPO Dedicated Federal Funds | Actual or Estimated Date of Authorization | Project Phase Status | Phase Shift History | Progress Since Last Meeting | Need a phase shift? (Yes or No) | If so, what fiscal year will you need to shift to? (Be cognicent of your "Phase Shift History")
2nd Street / 3rd Street / Museum Drive Intersection and Brandeis Avenue Pedestrian Improvements | 2982 | 5-581.00 | Design | 2025 | STBG-MPO | 272800 | 2025-10-01 | Federal Funding Authorized | 2 Phase Shifts Approved - next will require phase shift exception request approval | Awaiting on Approval to begin. MOA signed in January 2026. Have received approval from KYTC via letter agreement on 2.26.26; U of L working on an amended agreement | No |  | These design funds were obligated on 10.21.25
|  |  | Utilities | 2026 | STBG-MPO | 480000 |  | Federal Funding Not Yet Authorized | 3 Phase Shifts Approved - next will result in removal of MPO dedicated funds from the TIP | No progress, awaiting phase 2 design approval. | No
|  |  | Construction | 2026 | STBG-MPO | 4112000 |  | Federal Funding Not Yet Authorized | 3 Phase Shifts Approved - next will result in removal of MPO dedicated funds from the TIP | No progress, awaiting phase 2 design approval. | No
University of Louisville Pedestrian Improvements - Lighting | 2225 | 5-3218.00 | Construction | 2024 | STBG-MPO | 589640 | 2024-09-01 | Federal Funding Authorized |  | Under Construction | No |  | Obligated $440,000
University of Louisville Pedestrian Improvements - ADA Curb Cuts & Ramps | 2585 | 5-3220.00 | Construction | 2025 | STBG-MPO | 534568 | 2025-03-25 | Federal Funding Authorized |  | Under Construction | No |  | Obligated $536,000 on 3.19.25
Jeffersontown
Project | KIPDA ID | STATE ID | Phase | Fiscal Year (2023 - 2026 Only) | Program | MPO Dedicated Federal Funds | Actual or Estimated Date of Authorization | Project Phase Status | Phase Shift History | Progress Since Last Meeting | Need a phase shift? (Yes or No) | If so, what fiscal year will you need to shift to? (Be cognicent of your "Phase Shift History")
Bluegrass Commerce Park Bicycle/Pedestrian Trail Phase II | 2084 | 05-543.00 | Construction | 2025 | STBG-MPO | 2130000 |  | Federal Funding Authorized | Unlimited - ROW or U previously obligated |  | no
Galene Drive/Sprowl Road Collector Extension | 3113 |  | Planning | 2026 | STBG-MPO | 264000 | Possible Removal- Meeting with Mayor |  | 1 Phase Shift Approved
|  |  | Design | 2027 | STBG-MPO | 440000 | Possible Removal- Meeting with Mayor | Federal Funding Not Yet Authorized | 1 Phase Shift Approved |  | no
|  |  | ROW | 2028 | STBG-MPO | 880000 | Possible Removal- Meeting with Mayor | Federal Funding Not Yet Authorized | 1 Phase Shift Approved |  | no
|  |  | Utilities | 2029 | STBG-MPO | 440000 | Possible Removal- Meeting with Mayor | Federal Funding Not Yet Authorized | None |  | no
|  |  | Construction | 2029 | STBG-MPO | 4400000 | Possible Removal- Meeting with Mayor | Federal Funding Not Yet Authorized | None |  | no
Good Samaritan Bicycle & Pedestrian Trail Connector | 2082 | 05-486.00 | Construction | 2026 | STBG-MPO | 1460000 | 2026-07-01 |  | 3 Phase Shifts Approved - next will result in removal of MPO dedicated funds from the TIP | Working to get utilities relocated outside of project. Construction Funds only | no
Ruckriegel Parkway Sidewalk Improvement | 2619 | 05-198.00 | Construction | 2027 | STBG-MPO | 529008 | 2027-02-01 | Federal Funding Not Yet Authorized | 2 Phase Shifts Approved - next will require phase shift exception request approval | Advancing Design Review with D5 | no
Watterson Trail Phase 2 | 1583 | 05-518.00 | Utilities | 2026 | STBG-MPO | 352000 | 2027-01-27 |  | Unlimited - ROW or U previously obligated | About complete with R/W Phase. Utility Phase might be combinded with Construction Phase | yes | 2027-05-01
|  |  | Construction | 2026 | STBG-MPO | 1232000 | 2027-07-01 |  | Unlimited - ROW or U previously obligated |  | yes | 2027-05-01
Billtown-Eastvie w Collector Extension | 3111 |  | Design | 2026 | STBG-MPO | 310000 | 2026-08-01 | Federal Funding Not Yet Authorized | None | none. Plan to request Design Funds summer 2026 | no
|  |  | ROW | 2027 | STBG-MPO | 176000 | 2027-08-01 | Federal Funding Not Yet Authorized | None |  | no
|  |  | Utilities | 2028 | STBG-MPO | 528000 |  | Federal Funding Not Yet Authorized | None |  | no
|  |  | Construction | 2029 | STBG-MPO | 1056000 |  | Federal Funding Not Yet Authorized | None |  | no
Middletown
Project | KIPDA ID | STATE ID | Phase | Fiscal Year (2023 - 2026) | Program | MPO Dedicated Federal Funds | Actual or Estimated Date of Authorization | Project Phase Status | Phase Shift History | Progress Since Last Meeting | Need a phase shift? (Yes or No) | If so, what fiscal year will you need to shift to? (Be cognicent of your "Phase Shift History")
South Madison Avenue | 2320 | 5-3214.00 | Construction | 2026 | STBG-MPO | 438344 | Estimated Fall 2026 | Federal Funding Not Yet Authorized | None | Construction plans are currently under review by the Louisville Metro Permitting Division. The City of Middletown is preparing a maintenance agreement confirming responsibility for long-term sidewalk maintenance. | No | n/a
Mt. Washington
Project | KIPDA ID | STATE ID | Phase | Fiscal Year (2023 - 2026) | Program | MPO Dedicated Federal Funds | Actual or Estimated Date of Authorization | Project Phase Status | Phase Shift History | Progress Since Last Meeting | Need a phase shift? (Yes or No) | If so, what fiscal year will you need to shift to? (Be cognicent of your "Phase Shift History")
Historic Multi-Use Trail Segment C | 2479 | 5-3216.00 | Construction | 2026 | STBG-MPO | 3169814 |  |  | Unlimited - ROW or U previously obligated | Still purchasing right of way. We are attempting to find a solution for the drainage at the end property as well as a few condemnation cases. | No
|  |  | Construction | 2026 | STBG-State | 118000 |  |  | Unlimited - ROW or U previously obligated | Still purchasing right of way | No
TARC
Project | KIPDA ID | STATE ID | Phase | Fiscal Year | Program | MPO Dedicated Federal Funds | Actual or Estimated Date of Authorization | Project Phase Status | Phase Shift History | Progress Since Last Meeting | Need a phase shift? (Yes or No) | If so, what fiscal year will you need to shift to? (Be cognicent of your "Phase Shift History")
Bus Stop Improvements at Transit Node Eastern Parkway and Preston/Shelby Street | 3129 |  | Design | 2026 | STBG-MPO | 50000 | 2026-09-30 | Federal Funding Not Yet Authorized | None | TrAMS Application 1105-2026-1 created and in progress |  |  | funds flexed to FTA/TARC
|  |  | Construction | 2026 | CRP-MPO | 121165 | 2026-09-30 | Federal Funding Not Yet Authorized | None | TrAMS Application 1105-2026-1 created and in progress |  |  | funds flexed to FTA/TARC
Bus Stop and Access Improvements - M. Ali and Chestnut Street Corridor, KY | 3137 |  | PE | 2026 | CRP-MPO | 100000 | 2026-09-30 | Federal Funding Not Yet Authorized | None | TrAMS Application 1105-2026-1 created and in progress |  |  | funds flexed to FTA/TARC
|  |  | Construction | 2026 | STBG-MPO | 84512 | 2026-09-30 | Federal Funding Not Yet Authorized | None | TrAMS Application 1105-2026-1 created and in progress |  |  | funds flexed to FTA/TARC
|  |  | Construction | 2026 | CRP-MPO | 138375 | 2026-09-30 | Federal Funding Not Yet Authorized | None | TrAMS Application 1105-2026-1 created and in progress |  |  | funds flexed to FTA/TARC
Louisville Downtown Transit Center Study | 3403 |  | Planning | 2025 | STBG-MPO (IN) | 100000 | 2026-02-02 | Obligated as KY-2026-001 | None | Three sites selected for assessment; project team meetings with contracted engineering firm begun. |  |  | Funds flexed to FTA/TARC
[5 empty] | STBG-MPO (KY) | 400000 | [6 empty] | Funds flexed to FTA/TARC
Louisville Downtown Transit Center | 3416 |  | Design | 2027 | STBG-MPO (KY) | 1000000 | 2027-03-30 | Federal Funding Not Yet Authorized | None | Awaiting planning study completion