## Current TIP Projects - Indiana
State | KIPDA ID # | State ID/DES# | Sponsor Agency | Project Name | Project Description | County/Counties | Open to Public | Ongoing Project | Justification | Parent Project | Group ID | Total Project Cost | Total Cost Programmed in TIP | Phase | Year | Federal | State/Local | Total | Federal Funding Category | Project Status | TIP
Indiana | 309 | 2000188 | New Albany | Mt. Tabor Road | Phase I - Reconstruct as a two lane road (no additional lanes) from Grantline Road to just west of Klerner Lane intersection including new full depth pavement section, stabilization of adjacent hillsides to arrest slides, slightly narrower reconstructed travel lanes, curb/gutter/drainage system installation, and provision of sidewalks on each side separated from the curb/gutter by a 5' grass strip. Phase II - Klerner Lane to Charlestown Road is forthcoming and will include the same improvements as above. A new intersection control at the Klerner Lane intersection will be part of this phase, including new crosswalks. | Floyd | 2031 | FALSE | Where Mt. Tabor Road is very near Rail/Slate Run Creek, this project will preserve the road by stabilizing the creek embankments and to continue to provide vehicular access to the elementary school at Mt. Tabor Road and Grantline Road and shopping areas at each end of Mt. Tabor Road. Sidewalks will provide pedestrian access for the first time along this road. Travel lane width will be slightly reduced. This project will add a school flasher, upgrade the signal at Grant Line Road, and add audible pedestrian signals. |  |  | 13468719 | 13468719 | C | 2025 | 3672000 | 918000 | 4590000 | STBG-MPO | Active | TRUE
Indiana | 542 |  | Floyd County Board of Commissioners | Old Vincennes Road Reconstruction Phase 3 | Phase 3 of Reconstruction of Old Vincennes Road from south of Luther Road to US 150 in Floyds Knobs. Reconstruction includes widening of lanes/shoulders, drainage infrastructure, and reduction of unsafe sight lines. Improvement of intersections at Schrieber Road with turn lanes, and reconfiguration at Duffy Road/Highlander Point Drive. | Floyd | 2030 | FALSE | Old Vincennes Road is the main route from US 150 to Floyd Central High School and Highland Hills Middle School. This section is also used for one of Floyd County's main commercial nodes, Highlander Point. Current infrastructure does not meet growing needs of area. |  |  | 5000000 | 2032677 | CN | 2025 | 0 | 2032677 | 2032677 | Local | Active | TRUE
Indiana | 1558 | 1700788 | Floyd County | Replacement of Bridge 51 | Replacement of Bridge 51 over Silver Creek and reconstruction of approaches on Blackiston Mill Road. Total project length is approximately 0.312 miles. | Clark, Floyd | 2027 | FALSE | The proposed replacement bridge will be approximately 250 feet long, with 700 foot approaches. Bridge 51 carries Blackiston Mill Road over Silver Creek and currently serves as a critical link between the City of New Albany and the Town of Clarksville. The bridge structure itself is the responsibility of Floyd County, with the northern approach being in the City of New Albany and the southern approach in the Town of Clarksville and Clark County. In our 2018 Bridge Inspection Report, Bridge 51 scored a 39.2 Sufficiency Rating. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 11397323 | 11397323 | CN | 2026 | 5632428 | 1408107 | 7040535 | STBG-MPO | Active | TRUE
Indiana | 1558 | 1700788 | Floyd County | Replacement of Bridge 51 | Replacement of Bridge 51 over Silver Creek and reconstruction of approaches on Blackiston Mill Road. Total project length is approximately 0.312 miles. | Clark, Floyd | 2027 | FALSE | The proposed replacement bridge will be approximately 250 feet long, with 700 foot approaches. Bridge 51 carries Blackiston Mill Road over Silver Creek and currently serves as a critical link between the City of New Albany and the Town of Clarksville. The bridge structure itself is the responsibility of Floyd County, with the northern approach being in the City of New Albany and the southern approach in the Town of Clarksville and Clark County. In our 2018 Bridge Inspection Report, Bridge 51 scored a 39.2 Sufficiency Rating. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 11397323 | 11397323 | CE | 2026 | 675891 | 168973 | 844864 | STBG-MPO | Active | TRUE
Indiana | 1558 | 1700788 | Floyd County | Replacement of Bridge 51 | Replacement of Bridge 51 over Silver Creek and reconstruction of approaches on Blackiston Mill Road. Total project length is approximately 0.312 miles. | Clark, Floyd | 2027 | FALSE | The proposed replacement bridge will be approximately 250 feet long, with 700 foot approaches. Bridge 51 carries Blackiston Mill Road over Silver Creek and currently serves as a critical link between the City of New Albany and the Town of Clarksville. The bridge structure itself is the responsibility of Floyd County, with the northern approach being in the City of New Albany and the southern approach in the Town of Clarksville and Clark County. In our 2018 Bridge Inspection Report, Bridge 51 scored a 39.2 Sufficiency Rating. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 11397323 | 11397323 | ROW | 2026 | 158348 | 39587 | 197935 | Bridge | Active | TRUE
Indiana | 1558 | 1700788 | Floyd County | Replacement of Bridge 51 | Replacement of Bridge 51 over Silver Creek and reconstruction of approaches on Blackiston Mill Road. Total project length is approximately 0.312 miles. | Clark, Floyd | 2027 | FALSE | The proposed replacement bridge will be approximately 250 feet long, with 700 foot approaches. Bridge 51 carries Blackiston Mill Road over Silver Creek and currently serves as a critical link between the City of New Albany and the Town of Clarksville. The bridge structure itself is the responsibility of Floyd County, with the northern approach being in the City of New Albany and the southern approach in the Town of Clarksville and Clark County. In our 2018 Bridge Inspection Report, Bridge 51 scored a 39.2 Sufficiency Rating. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 11397323 | 11397323 | CN | 2026 | 1046771 | 261693 | 1308464 | Bridge | Active | TRUE
Indiana | 1558 | 1700788 | Floyd County | Replacement of Bridge 51 | Replacement of Bridge 51 over Silver Creek and reconstruction of approaches on Blackiston Mill Road. Total project length is approximately 0.312 miles. | Clark, Floyd | 2027 | FALSE | The proposed replacement bridge will be approximately 250 feet long, with 700 foot approaches. Bridge 51 carries Blackiston Mill Road over Silver Creek and currently serves as a critical link between the City of New Albany and the Town of Clarksville. The bridge structure itself is the responsibility of Floyd County, with the northern approach being in the City of New Albany and the southern approach in the Town of Clarksville and Clark County. In our 2018 Bridge Inspection Report, Bridge 51 scored a 39.2 Sufficiency Rating. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 11397323 | 11397323 | PE | 2027 | 11274 | 2818 | 14092 | STBG-MPO | Active | TRUE
Indiana | 2128 | 1400550, 1800900 | Floyd County Board of Commissioners | Charlestown Road Corridor Complete Streets - Multi-Use Trail | Multi-use trail to connect County Line Road to Lewis Endres Parkway. Project is an approximately 1.5 mile pedestrian-bike trail that connects several large neighborhoods to commercial and recreational nodes along Charlestown Road. Also, the facility provides a safe mode of transportation for bike and pedestrian travel. | Floyd | 2024 | FALSE | This project has already been approved. This request is to split the project into Phases. Phase one will construct a section of trail from Sunset Drive to Chapel Lane and include the construction of a pedestrian bridge. Phase two which will be constructed in the future will connect Chapel Lane to County Line Road. Updated Project Justification. |  |  | 5132608 | 5132608 | CE | 2025 | 317925 | 35325 | 353250 | HSIP-ST | Active | TRUE
Indiana | 2128 | 1400550, 1800900 | Floyd County Board of Commissioners | Charlestown Road Corridor Complete Streets - Multi-Use Trail | Multi-use trail to connect County Line Road to Lewis Endres Parkway. Project is an approximately 1.5 mile pedestrian-bike trail that connects several large neighborhoods to commercial and recreational nodes along Charlestown Road. Also, the facility provides a safe mode of transportation for bike and pedestrian travel. | Floyd | 2024 | FALSE | This project has already been approved. This request is to split the project into Phases. Phase one will construct a section of trail from Sunset Drive to Chapel Lane and include the construction of a pedestrian bridge. Phase two which will be constructed in the future will connect Chapel Lane to County Line Road. Updated Project Justification. |  |  | 5132608 | 5132608 | CN | 2025 | 3325811 | 0 | 3325811 | HSIP-ST | Active | TRUE
Indiana | 2314 | 1593192 | INDOT | US 31 | Construct a bridge deck overlay on US 31, 1.94 miles south of IN 160 over Caney Fork. | Clark | 2028 | FALSE | Bridge deck overlay. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 1599047 | 1599047 | CN | 2028 | 1135238 | 283809 | 1419047 | STBG-ST | Active | TRUE
Indiana | 2390 | 1700727 | New Albany | Charlestown Road (from Hedden Court to Genung Drive) | The project begins at Hedden Court and proceeds northerly for 0.31 miles to Genung Drive. The project involves the construction of curb and gutter with sidewalk and a storm sewer system. 6' wide attached sidewalks are planned. The pavement would be milled overlaid/widened to provide a maximum of 33' of pavement width. The pavement width will provide one lane in each direction with a two-way left turn lane. The project is likely to involve phase construction with the shifting of traffic. The existing paved travel lanes/shoulders allow for traffic to be shifted while maintaining a safe distance to work zone for storm sewer construction, curb and gutter and sidewalk construction. The Project includes the following Phases: 1. Preliminary Engineering/Right-of-way Engineering; 2. Right-of Way Acquisition; 3. Utilities; and 4. Construction. The Project provides connections to an Elementary School, a N-hood Center, urban residential neighborhoods and nearby commercial and industrial uses. | Floyd | 2028 | FALSE | The City has constructed a 3-lane section and sidewalks along most all of Charlestown Road with the exception of this 1,600+' section lying between Hedden Court and Genung Drive This final section of Charlestown Road lies in a fully urbanized area and includes nearby Fairmont Elementary and the Fairmont (Rauch) Neighborhood Center. Much of this corridor lies in a HUD-designated lower income area and is identified as a KIPDA Title VI-EJ Area. Several years ago, the City developed a neighborhood park for Fairmont Elementary School and fully rehabilitated the neighborhood center using CDBG funds. Charlestown Road Improvement including the provision of sidewalks is listed in the City's Comp Plan Year 2020. This segment is also listed as #14 on the KIPDA Region's Top 20 IN High Crash Segments and is also listed as a KIPDA bike/ped Priority Corridor. This is a compelling segment to provide sidewalks and to provide for left-turning vehicles.It benefits low income households and improves ADA accessibility. |  |  | 2541873 | 373000 | PE | 2027 | 0 | 373000 | 373000 | Local | Active | TRUE
Indiana | 2393 | 1700725 | Clarksville | Riverside Drive | Reconstruct Riverside Drive from the town limits to Ashland Park, including sidewalks and parking on both sides of roadway, and an elevated cycle track on the south side of roadway. 0.25 miles. | Clark | 2026 | FALSE | Reconstruction of the existing roadway, improving the safety of the corridor and improving pedestrian and bicycle facilities. |  |  | 10866966 | 10866966 | CN | 2025 | 500000 | 125000 | 625000 | STBG-MPO | Active | TRUE
Indiana | 2487 | 1700111 | INDOT | US 31 | Pavement replacement on US 31, 1.53 miles north of IN 60 (Foothill Road) to 3.28 miles north of IN 60. | Clark | 2025 | FALSE | Pavement replacement. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 14244633 | 14244663 | CN | 2025 | 10155284 | 2538821 | 12694105 | STBG-ST | Active | TRUE
Indiana | 2492 | 1600750 | INDOT | I-65 | Replace superstructure on I-65, 2.68 miles south of IN 160 over Blue Lick Creek WBL. | Clark | 2026 | FALSE | Superstructure replacement. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 2592500 | 2592500 | CN | 2025 | 2018250 | 224250 | 2242500 | NHPP | Active | TRUE
Indiana | 2492 | 1600750 | INDOT | I-65 | Replace superstructure on I-65, 2.68 miles south of IN 160 over Blue Lick Creek WBL. | Clark | 2026 | FALSE | Superstructure replacement. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 2592500 | 2592500 | U | 2025 | 22500 | 2500 | 25000 | NHPP | Active | TRUE
Indiana | 2493 | 1600744 | INDOT | I-65 | Replace superstructure on I-65, 2.68 miles south of IN 160 over Blue Lick Creek NBL. | Clark | 2026 | FALSE | Superstructure replacement. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 2720600 | 2720600 | CN | 2025 | 2018250 | 224250 | 2242500 | NHPP | Active | TRUE
Indiana | 2493 | 1600744 | INDOT | I-65 | Replace superstructure on I-65, 2.68 miles south of IN 160 over Blue Lick Creek NBL. | Clark | 2026 | FALSE | Superstructure replacement. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 2720600 | 2720600 | U | 2025 | 22500 | 2500 | 25000 | NHPP | Active | TRUE
Indiana | 2494 | 1700207 | INDOT | I-64 | Replace superstructure on I-64, EB 00.73 miles east of US 150 at Quarry Road. | Floyd | 2028 | FALSE | Superstructure replacement. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 4395111 | 4395111 | CN | 2026 | 3461500 | 384611 | 3846111 | NHPP | Active | TRUE
Indiana | 2494 | 1700207 | INDOT | I-64 | Replace superstructure on I-64, EB 00.73 miles east of US 150 at Quarry Road. | Floyd | 2028 | FALSE | Superstructure replacement. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 4395111 | 4395111 | CE | 2026 | 90000 | 10000 | 100000 | NHPP | Active | TRUE
Indiana | 2494 | 1700207 | INDOT | I-64 | Replace superstructure on I-64, EB 00.73 miles east of US 150 at Quarry Road. | Floyd | 2028 | FALSE | Superstructure replacement. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 4395111 | 4395111 | U | 2026 | 31500 | 3500 | 35000 | NHPP | Active | TRUE
Indiana | 2495 | 1700205 | INDOT | I-64 | Bridge deck replacement on I-64, WBL 1.63 miles west of US 150 at IN 62/IN 64 EB/WB. | Floyd | 2030 | FALSE | Bridge deck replacement. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 6198999 | 6198999 | U | 2025 | 31500 | 3500 | 35000 | NHPP | Active | TRUE
Indiana | 2495 | 1700205 | INDOT | I-64 | Bridge deck replacement on I-64, WBL 1.63 miles west of US 150 at IN 62/IN 64 EB/WB. | Floyd | 2030 | FALSE | Bridge deck replacement. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 6198999 | 6198999 | PE | 2025 | 135000 | 15000 | 150000 | NHPP | Active | TRUE
Indiana | 2496 | 1700206 | INDOT | I-64 | Replace superstructure on I-64, eastbound lanes 1.63 miles west of US 150 over IN 62/IN 64 eastbound/westbound. | Floyd | 2030 | FALSE | Superstructure replacement. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 3937356 | 3937356 | U | 2025 | 31500 | 3500 | 35000 | NHPP | Active | TRUE
Indiana | 2496 | 1700206 | INDOT | I-64 | Replace superstructure on I-64, eastbound lanes 1.63 miles west of US 150 over IN 62/IN 64 eastbound/westbound. | Floyd | 2030 | FALSE | Superstructure replacement. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 3937356 | 3937356 | PE | 2025 | 135000 | 15000 | 150000 | STBG-ST | Active | TRUE
Indiana | 2513 | 1800721 | INDOT | I-64 at I-265 Bridge Deck Overlay #1 | Bridge rehabilitation project consisting of a bridge deck overlay on I-64. Location is 02.20 miles east of US 150 at I-265 EB ramp to I-64 EB. | Floyd | 2028 | FALSE | Bridge deck overlay |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 8643163 | 7806134 | CN | 2026 | 7025521 | 780613 | 7806134 | NHPP | Active | TRUE
Indiana | 2514 | 1702617 | INDOT | I-64 at I-265 Bridge Deck Overlay #2 | Bridge rehabilitation project consisting of a bridge deck overlay on I-64. Located at 2.11 miles east of US 150, I-64 WB at I-64 EB ramp to I-265 EB. | Floyd | 2028 | FALSE | Bridge deck overlay. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 7453360 | 7453360 | CN | 2026 | 6708024 | 745336 | 7453360 | NHPP | Active | TRUE
Indiana | 2515 | 1702614 | INDOT | I-64 Cherry Street Bridge Deck Overlay | Bridge rehabilitation project consisting of a bridge deck overlay on I-64, located .085 miles west of IN 111 over Cherry Street. | Floyd | 2028 | FALSE | Bridge deck overlay. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 1632397 | 1632397 | CN | 2026 | 1361157 | 151240 | 1512397 | NHPP | Active | TRUE
Indiana | 2520 | 1800405 | INDOT | US 150 Bridge Painting Over I-64 Westbound | Bridge painting on US 150 located 08.81 miles east of IN 335 over I-64 Westbound lane. | Floyd | 2027 | FALSE | Bridge painting. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 551917 | 551917 | CN | 2026 | 417534 | 104383 | 521917 | STBG-ST | Active | TRUE
Indiana | 2541 | 1801597 | Clarksville | Jeffersonville 9th Street/Clarksville Montgomery Avenue Multimodal Connection | Design and construction of multimodal connection between Jeffersonville and Clarksville's Arts Districts, underneath I-65 along Montgomery Avenue and 9th Street. The design will include new sidewalks, bicycle paths, lighting, and other aesthetic amenities. Project length is 0.64 miles. | Clark | 2024 | FALSE | The construction of I-65 has created a significant barrier to community connectivity between Jeffersonville and Clarksville in the Southern Indiana region. In an effort to recreate the connectivity once enjoyed by this area, both communities intend to partner in order to provide a safe, attractive bicycle and pedestrian connection for residents in each community. There are very few alternative transportation options available connecting these two communities, due to restrictions created by the interstate corridor. Citizens and visitors will have a safe route provided to them to cross between communities and Arts and Cultural Districts without using motorized transportation. in conjunction with other projects that Jeffersonville and Clarksville are undertaking, this improvement will provide an additional path to the Ohio River Greenway. |  |  | 2964000 | 2927680 | C | 2025 | 14407 | 3602 | 18009 | TA-MPO | Active | TRUE
Indiana | 2588 | 1600733 | INDOT | I-65 Bridge Deck Replacement | Bridge deck replacement on I-65, 01.81 mile south of IN 160 over Caney Fork South Bound lane. | Clark | 2026 | FALSE | Bridge deck replacement project on I-65 in Clark County. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 2269886 | 2269886 | CN | 2025 | 1822397 | 202489 | 2024886 | NHPP | Active | TRUE
Indiana | 2616 | 1700135 | INDOT | Widening of I-65 | Widen I-65 from 4 to 6 lanes from 0.25 miles south of Biggs Road (RP 16+42) in Clark County to Scottsburg (RP 29.49). | Clark | 2028 | FALSE | The purpose of this project is to address the safety concern of the wet spots, remove the stripped HMA pavement, replace the existing underdrain system, and improve the subgrade beneath the pavement and construct added travel lanes in this portion of I-65. |  |  | 229063409 | 229063409 | PE | 2025 | 6209140 | 689904 | 6899044 | NHPP | Active | TRUE
Indiana | 2616 | 1700135 | INDOT | Widening of I-65 | Widen I-65 from 4 to 6 lanes from 0.25 miles south of Biggs Road (RP 16+42) in Clark County to Scottsburg (RP 29.49). | Clark | 2028 | FALSE | The purpose of this project is to address the safety concern of the wet spots, remove the stripped HMA pavement, replace the existing underdrain system, and improve the subgrade beneath the pavement and construct added travel lanes in this portion of I-65. |  |  | 229063409 | 229063409 | CE | 2025 | 17383251 | 1931472 | 19314723 | NHPP | Active | TRUE
Indiana | 2616 | 1700135 | INDOT | Widening of I-65 | Widen I-65 from 4 to 6 lanes from 0.25 miles south of Biggs Road (RP 16+42) in Clark County to Scottsburg (RP 29.49). | Clark | 2028 | FALSE | The purpose of this project is to address the safety concern of the wet spots, remove the stripped HMA pavement, replace the existing underdrain system, and improve the subgrade beneath the pavement and construct added travel lanes in this portion of I-65. |  |  | 229063409 | 229063409 | CN | 2025 | 42406900 | 4711878 | 47118778 | NHPP | Active | TRUE
Indiana | 2616 | 1700135 | INDOT | Widening of I-65 | Widen I-65 from 4 to 6 lanes from 0.25 miles south of Biggs Road (RP 16+42) in Clark County to Scottsburg (RP 29.49). | Clark | 2028 | FALSE | The purpose of this project is to address the safety concern of the wet spots, remove the stripped HMA pavement, replace the existing underdrain system, and improve the subgrade beneath the pavement and construct added travel lanes in this portion of I-65. |  |  | 229063409 | 229063409 | PE | 2026 | 126423 | 14047 | 140470 | NHPP | Active | TRUE
Indiana | 2616 | 1700135 | INDOT | Widening of I-65 | Widen I-65 from 4 to 6 lanes from 0.25 miles south of Biggs Road (RP 16+42) in Clark County to Scottsburg (RP 29.49). | Clark | 2028 | FALSE | The purpose of this project is to address the safety concern of the wet spots, remove the stripped HMA pavement, replace the existing underdrain system, and improve the subgrade beneath the pavement and construct added travel lanes in this portion of I-65. |  |  | 229063409 | 229063409 | CE | 2026 | 135000 | 15000 | 150000 | NHPP | Active | TRUE
Indiana | 2616 | 1700135 | INDOT | Widening of I-65 | Widen I-65 from 4 to 6 lanes from 0.25 miles south of Biggs Road (RP 16+42) in Clark County to Scottsburg (RP 29.49). | Clark | 2028 | FALSE | The purpose of this project is to address the safety concern of the wet spots, remove the stripped HMA pavement, replace the existing underdrain system, and improve the subgrade beneath the pavement and construct added travel lanes in this portion of I-65. |  |  | 229063409 | 229063409 | CN | 2026 | 63950158 | 7105573 | 71055731 | NHPP | Active | TRUE
Indiana | 2616 | 1700135 | INDOT | Widening of I-65 | Widen I-65 from 4 to 6 lanes from 0.25 miles south of Biggs Road (RP 16+42) in Clark County to Scottsburg (RP 29.49). | Clark | 2028 | FALSE | The purpose of this project is to address the safety concern of the wet spots, remove the stripped HMA pavement, replace the existing underdrain system, and improve the subgrade beneath the pavement and construct added travel lanes in this portion of I-65. |  |  | 229063409 | 229063409 | CN | 2027 | 67133866 | 7459318 | 74593184 | NHPP | Active | TRUE
Indiana | 2722 | 1900343 | INDOT | US 31 at Wolf Run | Bridge replacement on US 31, 00.20 mile north of IN 160 at Wolf Run. | Clark | 2031 | FALSE | Bridge replacement, concrete. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 2073993 | 1899311 | ROW | 2025 | 5760 | 1440 | 7200 | STBG-ST | Active | TRUE
Indiana | 2722 | 1900343 | INDOT | US 31 at Wolf Run | Bridge replacement on US 31, 00.20 mile north of IN 160 at Wolf Run. | Clark | 2031 | FALSE | Bridge replacement, concrete. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 2073993 | 1899311 | U | 2026 | 56000 | 14000 | 70000 | STBG-ST | Active | TRUE
Indiana | 2722 | 1900343 | INDOT | US 31 at Wolf Run | Bridge replacement on US 31, 00.20 mile north of IN 160 at Wolf Run. | Clark | 2031 | FALSE | Bridge replacement, concrete. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 2073993 | 1899311 | PE | 2026 | 88000 | 22000 | 110000 | STBG-ST | Active | TRUE
Indiana | 2727 | 2400021 | APCD | Kentuckiana Air Education 2025 | Kentuckiana Air Education (KAIRE) is an air pollution prevention and awareness program that will increase public awareness of the impacts individual choices can have on local air quality. | Clark, Floyd | 2025 | FALSE | KAIRE works to encourage voluntary air quality changes through community involvement, increasing public awareness of the impacts individual choices can have on local air quality. | 370 |  | 250000 | 250000 | Operations | 2025 | 200000 | 50000 | 250000 | CMAQ-MPO | Active | TRUE
Indiana | 2731 | 2400021 | KIPDA | KIPDA Regional Rideshare Program - Indiana FY 2025 | The KIPDA Regional Rideshare Program provides ride-matching services, employer-based and regional ridesharing, vanpool subscription services, promotional activities to support ride-sharing, which includes carpooling, vanpooling, taking transit, walking, telecommuting, and bikepooling. This also includes program evaluation and administration. | Clark, Floyd | 2025 | FALSE | To reduce congestion, improve air quality, and promote sustainability. | 56 |  | 158750 | 158750 | Operations | 2025 | 127000 | 31750 | 158750 | STBG-MPO | Active | TRUE
Indiana | 2836 | 1902768 | Clark County | Clark County Bridge 413 | Clark County Bridge 413 is located over abandoned railroad tracks that have been removed and converted to a pedestrian path. The bridge will be rehabilitated with a rigid deck overlay and reinforced concrete bridge approach slabs. Following construction, Clark County will relinquish the structure to the Town of Clarksville. | Clark | 2027 | FALSE | The Clark County Bridge 413 is located on Brown's Station Way over an abandoned CSX line. Brown's Station Way is classified as a freeway. The latest round on inspections identified the surface of Bridge 413 as "poor" and improvements were recommended. According to the latest bridge design codes a bridge located on a freeway must have 8-10 foot shoulders on either side of the throughway. Bridge 413 does not have shoulders. Any improvements to the bridge should include adding shoulders to the bridge. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 4672650 | 4672650 | U | 2026 | 258000 | 64500 | 322500 | Bridge | Active | TRUE
Indiana | 2836 | 1902768 | Clark County | Clark County Bridge 413 | Clark County Bridge 413 is located over abandoned railroad tracks that have been removed and converted to a pedestrian path. The bridge will be rehabilitated with a rigid deck overlay and reinforced concrete bridge approach slabs. Following construction, Clark County will relinquish the structure to the Town of Clarksville. | Clark | 2027 | FALSE | The Clark County Bridge 413 is located on Brown's Station Way over an abandoned CSX line. Brown's Station Way is classified as a freeway. The latest round on inspections identified the surface of Bridge 413 as "poor" and improvements were recommended. According to the latest bridge design codes a bridge located on a freeway must have 8-10 foot shoulders on either side of the throughway. Bridge 413 does not have shoulders. Any improvements to the bridge should include adding shoulders to the bridge. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 4672650 | 4672650 | CE | 2026 | 387000 | 96750 | 483750 | Bridge | Active | TRUE
Indiana | 2836 | 1902768 | Clark County | Clark County Bridge 413 | Clark County Bridge 413 is located over abandoned railroad tracks that have been removed and converted to a pedestrian path. The bridge will be rehabilitated with a rigid deck overlay and reinforced concrete bridge approach slabs. Following construction, Clark County will relinquish the structure to the Town of Clarksville. | Clark | 2027 | FALSE | The Clark County Bridge 413 is located on Brown's Station Way over an abandoned CSX line. Brown's Station Way is classified as a freeway. The latest round on inspections identified the surface of Bridge 413 as "poor" and improvements were recommended. According to the latest bridge design codes a bridge located on a freeway must have 8-10 foot shoulders on either side of the throughway. Bridge 413 does not have shoulders. Any improvements to the bridge should include adding shoulders to the bridge. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 4672650 | 4672650 | CN | 2026 | 2580000 | 645000 | 3225000 | Bridge | Active | TRUE
Indiana | 2845 | 2000301 | INDOT | US 31 Bridge Deck Overlay | Bridge rehabilitation project on US 31 constructing a bridge deck overlay over Silver Creek, 00.87 miles south of SR 60. | Clark | 2027 | FALSE | To repair and correct the structural deficiencies of the bridge and prolong the life of the structure. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 2389476 | 2372666 | RR | 2025 | 91200 | 22800 | 114000 | STBG-ST | Active | TRUE
Indiana | 2845 | 2000301 | INDOT | US 31 Bridge Deck Overlay | Bridge rehabilitation project on US 31 constructing a bridge deck overlay over Silver Creek, 00.87 miles south of SR 60. | Clark | 2027 | FALSE | To repair and correct the structural deficiencies of the bridge and prolong the life of the structure. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 2389476 | 2372666 | CN | 2026 | 1702933 | 425733 | 2128666 | STBG-ST | Active | TRUE
Indiana | 2847 | 1900366 | INDOT | US 150 at Old Vincennes Road | Intersection Improvement with added turn lanes at intersection of US 150 and Old Vincennes Road, 0.5 miles west of I-64. | Floyd | 2026 | FALSE | To allow for gaps for vehicles turning from Old Vincennes Road to US 150 and from eastbound US 150 to Old Vincennes Road in such a manner that traffic on US 150 does not significantly queue. |  |  | 3680347 | 3334858 | CN | 2025 | 2578758 | 644690 | 3223448 | NHPP | Active | TRUE
Indiana | 2847 | 1900366 | INDOT | US 150 at Old Vincennes Road | Intersection Improvement with added turn lanes at intersection of US 150 and Old Vincennes Road, 0.5 miles west of I-64. | Floyd | 2026 | FALSE | To allow for gaps for vehicles turning from Old Vincennes Road to US 150 and from eastbound US 150 to Old Vincennes Road in such a manner that traffic on US 150 does not significantly queue. |  |  | 3680347 | 3334858 | PE | 2025 | 39780 | 4420 | 44200 | HSIP-ST | Active | TRUE
Indiana | 2847 | 1900366 | INDOT | US 150 at Old Vincennes Road | Intersection Improvement with added turn lanes at intersection of US 150 and Old Vincennes Road, 0.5 miles west of I-64. | Floyd | 2026 | FALSE | To allow for gaps for vehicles turning from Old Vincennes Road to US 150 and from eastbound US 150 to Old Vincennes Road in such a manner that traffic on US 150 does not significantly queue. |  |  | 3680347 | 3334858 | U | 2025 | 17600 | 4400 | 22000 | STBG-ST | Active | TRUE
Indiana | 2848 | 2000145 | INDOT | I-64 WB Over Yenowine Road | Bridge deck overlay project on I-64 WB bridge over Yenowine Road, 0.40 miles west of SR 64. | Floyd | 2030 | FALSE | Bridge rehabilitation project constructing an overlay to correct and repair the deficiencies to maintain and prolong the life of the bridge structure. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 1664376 | 1664376 | PE | 2025 | 9000 | 1000 | 10000 | NHPP | Active | TRUE
Indiana | 2848 | 2000145 | INDOT | I-64 WB Over Yenowine Road | Bridge deck overlay project on I-64 WB bridge over Yenowine Road, 0.40 miles west of SR 64. | Floyd | 2030 | FALSE | Bridge rehabilitation project constructing an overlay to correct and repair the deficiencies to maintain and prolong the life of the bridge structure. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 1664376 | 1664376 | U | 2025 | 9000 | 1000 | 10000 | NHPP | Active | TRUE
Indiana | 2852 | 2000357 | INDOT | SR 111 | Construct a bridge deck overlay over Middle Creek, 1.25 miles south of SR 62. | Floyd | 2026 | FALSE | To perform a rehabilitation project on SR 111 and extend the life of the bridge asset. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 1630850 | 1630850 | U | 2025 | 8000 | 2000 | 10000 | STBG-ST | Active | TRUE
Indiana | 2852 | 2000357 | INDOT | SR 111 | Construct a bridge deck overlay over Middle Creek, 1.25 miles south of SR 62. | Floyd | 2026 | FALSE | To perform a rehabilitation project on SR 111 and extend the life of the bridge asset. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 1630850 | 1630850 | CN | 2026 | 1145560 | 286390 | 1431950 | STBG-ST | Active | TRUE
Indiana | 2857 | 2000326 | INDOT | I-265 EB Bridge Over State Street NB/SB | Bridge deck overlay on I-265 eastbound bridge over State Street northbound/southbound. | Floyd | 2028 | FALSE | To correct the deficiencies in the wearing surface and deck and prolong the life of the bridge structure. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 2320775 | 2320775 | CN | 2026 | 1971698 | 219077 | 2190775 | NHPP | Active | TRUE
Indiana | 2858 | 2000324 | INDOT | I-265 WB Over State Street | Bridge deck overlay on I-265 westbound over State Street northbound/southbound. | Floyd | 2028 | FALSE | To correct the deficiencies of the existing bridge deck and maintain and prolong the structural life of the bridge. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 1137693 | 728825 | CN | 2026 | 538943 | 59882 | 598825 | NHPP | Active | TRUE
Indiana | 2859 | 2000323 | INDOT | I-265 Bridge Over State Street EB Ramp C | Bridge deck overlay on I-265 over State Street northbound/southbound, 0.84 miles east of I-64 (Ramp C, EB). | Floyd | 2028 | FALSE | To correct the deficiencies of the bridge deck and maintain and prolong the structure integrity of the bridge. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 2130000 | 2130000 | CN | 2026 | 1800000 | 200000 | 2000000 | NHPP | Active | TRUE
Indiana | 2899 | 1900162 | INDOT | I-64 Added Travel Lanes | Added travel lanes project on I-64 from US 150 to just north of Cherry Street with additional pavement rehabilitation extending to Main Street. Project also includes added lanes on I-265 from I-64 to north of State Street and improvements to the interchanges of I-64 at US 150 and I-265. | Floyd | 2028 | FALSE | To improve traffic congestion and accessibility. |  |  | 328553910 | 328553910 | U | 2025 | 0 | 106000 | 106000 | State | Active | TRUE
Indiana | 2899 | 1900162 | INDOT | I-64 Added Travel Lanes | Added travel lanes project on I-64 from US 150 to just north of Cherry Street with additional pavement rehabilitation extending to Main Street. Project also includes added lanes on I-265 from I-64 to north of State Street and improvements to the interchanges of I-64 at US 150 and I-265. | Floyd | 2028 | FALSE | To improve traffic congestion and accessibility. |  |  | 328553910 | 328553910 | ROW | 2025 | 0 | 10000 | 10000 | State | Active | TRUE
Indiana | 2899 | 1900162 | INDOT | I-64 Added Travel Lanes | Added travel lanes project on I-64 from US 150 to just north of Cherry Street with additional pavement rehabilitation extending to Main Street. Project also includes added lanes on I-265 from I-64 to north of State Street and improvements to the interchanges of I-64 at US 150 and I-265. | Floyd | 2028 | FALSE | To improve traffic congestion and accessibility. |  |  | 328553910 | 328553910 | PE | 2025 | 0 | 11583350 | 11583350 | State | Active | TRUE
Indiana | 2899 | 1900162 | INDOT | I-64 Added Travel Lanes | Added travel lanes project on I-64 from US 150 to just north of Cherry Street with additional pavement rehabilitation extending to Main Street. Project also includes added lanes on I-265 from I-64 to north of State Street and improvements to the interchanges of I-64 at US 150 and I-265. | Floyd | 2028 | FALSE | To improve traffic congestion and accessibility. |  |  | 328553910 | 328553910 | CN | 2026 | 173466942 | 19274105 | 192741047 | NHPP | Active | TRUE
Indiana | 2899 | 1900162 | INDOT | I-64 Added Travel Lanes | Added travel lanes project on I-64 from US 150 to just north of Cherry Street with additional pavement rehabilitation extending to Main Street. Project also includes added lanes on I-265 from I-64 to north of State Street and improvements to the interchanges of I-64 at US 150 and I-265. | Floyd | 2028 | FALSE | To improve traffic congestion and accessibility. |  |  | 328553910 | 328553910 | ROW | 2026 | 18000 | 2000 | 20000 | NHPP | Active | TRUE
Indiana | 2899 | 1900162 | INDOT | I-64 Added Travel Lanes | Added travel lanes project on I-64 from US 150 to just north of Cherry Street with additional pavement rehabilitation extending to Main Street. Project also includes added lanes on I-265 from I-64 to north of State Street and improvements to the interchanges of I-64 at US 150 and I-265. | Floyd | 2028 | FALSE | To improve traffic congestion and accessibility. |  |  | 328553910 | 328553910 | U | 2026 | 99172 | 11019 | 110191 | NHPP | Active | TRUE
Indiana | 2899 | 1900162 | INDOT | I-64 Added Travel Lanes | Added travel lanes project on I-64 from US 150 to just north of Cherry Street with additional pavement rehabilitation extending to Main Street. Project also includes added lanes on I-265 from I-64 to north of State Street and improvements to the interchanges of I-64 at US 150 and I-265. | Floyd | 2028 | FALSE | To improve traffic congestion and accessibility. |  |  | 328553910 | 328553910 | PE | 2026 | 2096436 | 232937 | 2329373 | NHPP | Active | TRUE
Indiana | 2899 | 1900162 | INDOT | I-64 Added Travel Lanes | Added travel lanes project on I-64 from US 150 to just north of Cherry Street with additional pavement rehabilitation extending to Main Street. Project also includes added lanes on I-265 from I-64 to north of State Street and improvements to the interchanges of I-64 at US 150 and I-265. | Floyd | 2028 | FALSE | To improve traffic congestion and accessibility. |  |  | 328553910 | 328553910 | CE | 2026 | 10350000 | 1150000 | 11500000 | NHPP | Active | TRUE
Indiana | 2899 | 1900162 | INDOT | I-64 Added Travel Lanes | Added travel lanes project on I-64 from US 150 to just north of Cherry Street with additional pavement rehabilitation extending to Main Street. Project also includes added lanes on I-265 from I-64 to north of State Street and improvements to the interchanges of I-64 at US 150 and I-265. | Floyd | 2028 | FALSE | To improve traffic congestion and accessibility. |  |  | 328553910 | 328553910 | CN | 2027 | 28345655 | 3149517 | 31495172 | NHPP | Active | TRUE
Indiana | 2899 | 1900162 | INDOT | I-64 Added Travel Lanes | Added travel lanes project on I-64 from US 150 to just north of Cherry Street with additional pavement rehabilitation extending to Main Street. Project also includes added lanes on I-265 from I-64 to north of State Street and improvements to the interchanges of I-64 at US 150 and I-265. | Floyd | 2028 | FALSE | To improve traffic congestion and accessibility. |  |  | 328553910 | 328553910 | CE | 2027 | 12652343 | 1405816 | 14058159 | NHPP | Active | TRUE
Indiana | 2899 | 1900162 | INDOT | I-64 Added Travel Lanes | Added travel lanes project on I-64 from US 150 to just north of Cherry Street with additional pavement rehabilitation extending to Main Street. Project also includes added lanes on I-265 from I-64 to north of State Street and improvements to the interchanges of I-64 at US 150 and I-265. | Floyd | 2028 | FALSE | To improve traffic congestion and accessibility. |  |  | 328553910 | 328553910 | CN | 2028 | 31500000 | 3500000 | 35000000 | NHPP | Active | TRUE
Indiana | 2901 | 1800318 | INDOT | SR 64 | Intersection Improvement with added turn lanes on SR 64 at Copperfield Drive to reduce queueing and delay for motorists at this intersection. | Floyd | 2027 | FALSE | To help reduce congestion at SR 64 and Copperfield Drive due to traffic at large subdivision causing motorists to back up and cause long delays. Culvert beneath will be extended to allow for widening of road. |  |  | 2484664 | 2484664 | PE | 2025 | 320000 | 80000 | 400000 | STBG-ST | Active | TRUE
Indiana | 2901 | 1800318 | INDOT | SR 64 | Intersection Improvement with added turn lanes on SR 64 at Copperfield Drive to reduce queueing and delay for motorists at this intersection. | Floyd | 2027 | FALSE | To help reduce congestion at SR 64 and Copperfield Drive due to traffic at large subdivision causing motorists to back up and cause long delays. Culvert beneath will be extended to allow for widening of road. |  |  | 2484664 | 2484664 | ROW | 2025 | 12000 | 3000 | 15000 | STBG-ST | Active | TRUE
Indiana | 2901 | 1800318 | INDOT | SR 64 | Intersection Improvement with added turn lanes on SR 64 at Copperfield Drive to reduce queueing and delay for motorists at this intersection. | Floyd | 2027 | FALSE | To help reduce congestion at SR 64 and Copperfield Drive due to traffic at large subdivision causing motorists to back up and cause long delays. Culvert beneath will be extended to allow for widening of road. |  |  | 2484664 | 2484664 | CN | 2027 | 1485982 | 371495 | 1857477 | STBG-ST | Active | TRUE
Indiana | 2910 | 2002339 | INDOT | I-265 Over I-65 | Bridge painting rehabilitation at I-265 EB ramp over I-65 to I-65 NB, 02.50 miles east of SR 311. | Clark | 2027 | FALSE | The purpose of this rehabilitation is due to the decks transverse cracks and map cracking with one spall in span B in the deck underside. Three moderate size wet spots under the spalls in the wearing surface. Shrinkage cracks in copings and parapets. Cracking in the wearing surface. The concrete patches from previous repair still look good. |  | 2680 - Safety Improvements - Indiana | 587732 | 587732 | CN | 2025 | 420959 | 46773 | 467732 | NHPP | Active | TRUE
Indiana | 2911 | 2001805 | INDOT | SR 60 | Replace small structures and drainage in/around SR 60 at RP 58+32 which is 1.51 miles west of SR 311. | Clark | 2025 | FALSE | The purpose of this project is to correct the deficiencies in CLV 60-010-58.21 in order to extend or reset the service life of the asset. The project need is based on the current condition of the structure elements. The barrel invert is rusted, and the roadway is sinking and cracking above the pipe. The embankment on the inlet end is eroding, and there is debris in the flow line on the outlet end. This pipe is 24". |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 2326067 | 2268000 | C | 2025 | 1564200 | 173800 | 1738000 | NHPP | Active | TRUE
Indiana | 2911 | 2001805 | INDOT | SR 60 | Replace small structures and drainage in/around SR 60 at RP 58+32 which is 1.51 miles west of SR 311. | Clark | 2025 | FALSE | The purpose of this project is to correct the deficiencies in CLV 60-010-58.21 in order to extend or reset the service life of the asset. The project need is based on the current condition of the structure elements. The barrel invert is rusted, and the roadway is sinking and cracking above the pipe. The embankment on the inlet end is eroding, and there is debris in the flow line on the outlet end. This pipe is 24". |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 2326067 | 2268000 | U | 2025 | 27000 | 3000 | 30000 | NHPP | Active | TRUE
Indiana | 2912 | 2002049 | INDOT | SR 60 Bridge Replacement Over Packwood Branch | Bridge replacement on SR 60 over Packwood Branch, 02.47 miles east of SR 335. | Clark | 2025 | FALSE | The arch has cracking, delamination, efflorescence and two spalls with exposed rebar in the center of arch. Overall the bridge is in fair condition. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 2027108 | 1912508 | C | 2025 | 1373686 |  | 1717108 | NHPP | Active | TRUE
Indiana | 2912 | 2002049 | INDOT | SR 60 Bridge Replacement Over Packwood Branch | Bridge replacement on SR 60 over Packwood Branch, 02.47 miles east of SR 335. | Clark | 2025 | FALSE | The arch has cracking, delamination, efflorescence and two spalls with exposed rebar in the center of arch. Overall the bridge is in fair condition. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 2027108 | 1912508 | U | 2025 | 40000 | 10000 | 50000 | NHPP | Active | TRUE
Indiana | 2913 | 2000233 | INDOT | US 150 Intersection Improvement | Intersection improvement with new signals on US 150 at Everett Avenue, Steiller Road, and Buck Creek Road. | Floyd | 2030 | FALSE | Intent of the project to improve corridor progression on US 150 by implementing intersection upgrades. This report will focus on the segment of US 150 in Floyd County, between Edwardsville-Galena Road and Old Vincennes Road in and around the Galena and the Floyds Knobs area. The original study area extended west to Snyder Chapel Road, west of Greenville in Harrison County, for modeling purposes. All relevant background data is included. The report describes the project at a preliminary level and will guide the ongoing phases of project development. |  |  | 8590820 | 8590820 | PE | 2025 | 237890 | 59472 | 297362 | STBG-ST | Active | TRUE
Indiana | 2913 | 2000233 | INDOT | US 150 Intersection Improvement | Intersection improvement with new signals on US 150 at Everett Avenue, Steiller Road, and Buck Creek Road. | Floyd | 2030 | FALSE | Intent of the project to improve corridor progression on US 150 by implementing intersection upgrades. This report will focus on the segment of US 150 in Floyd County, between Edwardsville-Galena Road and Old Vincennes Road in and around the Galena and the Floyds Knobs area. The original study area extended west to Snyder Chapel Road, west of Greenville in Harrison County, for modeling purposes. All relevant background data is included. The report describes the project at a preliminary level and will guide the ongoing phases of project development. |  |  | 8590820 | 8590820 | ROW | 2028 | 16000 | 4000 | 20000 | STBG-ST | Active | TRUE
Indiana | 2914 | 2002073 | INDOT | US 150 - Little Indian Creek | Replace superstructure at WB over Little Indian Creek, 00.65 miles west of I-64. | Floyd | 2026 | FALSE | New latex modified overlay was installed under Contract B-37061, Des #1383546. The structure is in fair condition. Cracking and water staining with delamination and one spall with exposed rebar in girder #1 of span B at midspan at the drain pipe area. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 3473692 | 3473692 | CN | 2025 | 2574954 | 643738 | 3218692 | STBG-ST | Active | TRUE
Indiana | 2914 | 2002073 | INDOT | US 150 - Little Indian Creek | Replace superstructure at WB over Little Indian Creek, 00.65 miles west of I-64. | Floyd | 2026 | FALSE | New latex modified overlay was installed under Contract B-37061, Des #1383546. The structure is in fair condition. Cracking and water staining with delamination and one spall with exposed rebar in girder #1 of span B at midspan at the drain pipe area. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 3473692 | 3473692 | U | 2025 | 8000 | 2000 | 10000 | STBG-ST | Active | TRUE
Indiana | 2915 | 2002072 | INDOT | US 150 Replace Superstructure Over Little Indian Creek | Replace superstructure on US 150 EB over Little Indian Creek, 00.65 miles west of I-64. | Floyd | 2026 | FALSE | A new latex modified overlay was installed under Contract B-37061, Des #1383545. The structure is in fair condition. Girder #1 span B at mid span drain pipe area has cracking and delamination, also minor vertical cracking with efflorescence in several girders in spans A and span C. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 3367107 | 3221607 | CN | 2025 | 2669946 | 296661 | 2966607 | NHPP | Active | TRUE
Indiana | 2915 | 2002072 | INDOT | US 150 Replace Superstructure Over Little Indian Creek | Replace superstructure on US 150 EB over Little Indian Creek, 00.65 miles west of I-64. | Floyd | 2026 | FALSE | A new latex modified overlay was installed under Contract B-37061, Des #1383545. The structure is in fair condition. Girder #1 span B at mid span drain pipe area has cracking and delamination, also minor vertical cracking with efflorescence in several girders in spans A and span C. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 3367107 | 3221607 | U | 2025 | 8000 | 2000 | 10000 | STBG-ST | Active | TRUE
Indiana | 2951 | 2100081 | Floyd County Board of Commissioners | Countywide Bridge Inspection and Inventory Program for Cycle Years 2022-2025 | Inspect and rate all county bridges in Floyd County. | Floyd | 2025 | FALSE | Necessary/required inspection of bridges throughout Floyd County. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 261462 | 206830 | PE | 2025 | 7312 | 1828 | 9140 | Bridge | Active | TRUE
Indiana | 2964 | 2100048 | INDOT | SR 60 Intersection Improvement, Roundabout | Intersection improvement going to a roundabout at SR 60 and CR 311. | Clark | 2030 | FALSE | The purpose of this project is to reduce the number of traffic crashes being experienced at this location, in particular the rear end, left turn, and right-angle crashes. Using HAT 3 as the analysis tool the 129 crashes resulted in a 4.01 Icc crash severity value. The crash frequency value (Icf) is 6.68. The need for this project is to provide a geometric improvement to the intersection which will provide sufficient capacity and reduce these rear end, left turn and right angle crashes going forward to allow this intersection to operate at a more acceptable overall safety operating condition. |  |  | 6566843 | 6566843 | PE | 2025 | 85338 | 9482 | 94820 | NHPP | Active | TRUE
Indiana | 2965 | 2100047 | INDOT | US 150 Intersection Improvement of Old Vincennes Road/Lawrence Banet Road | Intersection improvement at the intersection of Old Vincennes Road/Lawrence Banet Road. | Floyd | 2033 | FALSE | An intersection improvement project is recommended for US 150 and Lawrence Banet Road in Floyds Knobs, Floyd County, IN. This location has experienced higher than anticipated crash frequency and cost. The recommended alternative would reconfigure US 150 and Lawrence Banet Road as a median U-turn intersection, eliminating left turns at the intersection and installing U-turn access points on US 150. |  |  | 4947600 | 4947600 | U | 2028 | 80000 | 20000 | 100000 | CMAQ-ST | Active | TRUE
Indiana | 2965 | 2100047 | INDOT | US 150 Intersection Improvement of Old Vincennes Road/Lawrence Banet Road | Intersection improvement at the intersection of Old Vincennes Road/Lawrence Banet Road. | Floyd | 2033 | FALSE | An intersection improvement project is recommended for US 150 and Lawrence Banet Road in Floyds Knobs, Floyd County, IN. This location has experienced higher than anticipated crash frequency and cost. The recommended alternative would reconfigure US 150 and Lawrence Banet Road as a median U-turn intersection, eliminating left turns at the intersection and installing U-turn access points on US 150. |  |  | 4947600 | 4947600 | ROW | 2028 | 400000 | 100000 | 500000 | CMAQ-ST | Active | TRUE
Indiana | 2967 | 2100036 | INDOT | SR 64 Added Travel Lane | Added travel lane on SR 64 from 2,150' west of the existing Oakes Road intersection to Edwardsville-Galena Road in Floyd County. | Floyd | 2033 | FALSE | The purpose of this project is to improve throughput on SR 64 by improving intersection operations. Adding these travel lanes will reduce driver delay for the side roads and mainline SR 64 in the design year. The added lanes to SR 64 will continue the multi-lane cross section further west towards Georgetown to benefit commuter trips to and from I-64. |  |  | 22689512 | 22689512 | PE | 2027 | 568312 | 142078 | 710390 | STBG-ST | Active | TRUE
Indiana | 2967 | 2100036 | INDOT | SR 64 Added Travel Lane | Added travel lane on SR 64 from 2,150' west of the existing Oakes Road intersection to Edwardsville-Galena Road in Floyd County. | Floyd | 2033 | FALSE | The purpose of this project is to improve throughput on SR 64 by improving intersection operations. Adding these travel lanes will reduce driver delay for the side roads and mainline SR 64 in the design year. The added lanes to SR 64 will continue the multi-lane cross section further west towards Georgetown to benefit commuter trips to and from I-64. |  |  | 22689512 | 22689512 | U | 2028 | 336000 | 84000 | 420000 | STBG-ST | Active | TRUE
Indiana | 2967 | 2100036 | INDOT | SR 64 Added Travel Lane | Added travel lane on SR 64 from 2,150' west of the existing Oakes Road intersection to Edwardsville-Galena Road in Floyd County. | Floyd | 2033 | FALSE | The purpose of this project is to improve throughput on SR 64 by improving intersection operations. Adding these travel lanes will reduce driver delay for the side roads and mainline SR 64 in the design year. The added lanes to SR 64 will continue the multi-lane cross section further west towards Georgetown to benefit commuter trips to and from I-64. |  |  | 22689512 | 22689512 | ROW | 2028 | 776000 | 194000 | 970000 | STBG-ST | Active | TRUE
Indiana | 2968 | 2100560 | INDOT | I-265 Bridge Deck Overlay on Klerner Lane Bridge, 0.40 Miles East of SR 111 | I-265 bridge deck overlay on Klerner Lane bridge over I-265 EB/WB, 0.40 miles east of SR 111. | Floyd | 2026 | FALSE | The purpose of this project is to correct the deficiencies in the wearing surface, deck, and superstructure to help further protect the structure and extend the service life of the bridge. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 3551833 | 3196500 | ROW | 2025 | 9000 | 1000 | 10000 | NHPP | Active | TRUE
Indiana | 2968 | 2100560 | INDOT | I-265 Bridge Deck Overlay on Klerner Lane Bridge, 0.40 Miles East of SR 111 | I-265 bridge deck overlay on Klerner Lane bridge over I-265 EB/WB, 0.40 miles east of SR 111. | Floyd | 2026 | FALSE | The purpose of this project is to correct the deficiencies in the wearing surface, deck, and superstructure to help further protect the structure and extend the service life of the bridge. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 3551833 | 3196500 | CN | 2026 | 2658330 | 295370 | 2953700 | NHPP | Active | TRUE
Indiana | 2968 | 2100560 | INDOT | I-265 Bridge Deck Overlay on Klerner Lane Bridge, 0.40 Miles East of SR 111 | I-265 bridge deck overlay on Klerner Lane bridge over I-265 EB/WB, 0.40 miles east of SR 111. | Floyd | 2026 | FALSE | The purpose of this project is to correct the deficiencies in the wearing surface, deck, and superstructure to help further protect the structure and extend the service life of the bridge. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 3551833 | 3196500 | U | 2026 | 99000 | 11000 | 110000 | NHPP | Active | TRUE
Indiana | 2969 | 2100817 | INDOT | I-64 Small Structure Pipe Lining, 0.40 Miles East of I-265 | Correct deficiencies in small structure pipe lining on I-64 over unnamed ditch, 0.40 miles east of I-265. | Floyd | 2028 | FALSE | The purpose of this project is to correct the deficiencies in the structure in order to extend or reset the service life of the asset. The project need is based on the current condition of the structure elements. There is a significant amount of sediment in the pipe and there is significant corrosion and deep pitting in the invert of the structure. The sediment in the pipe in the pipe accounts for ten to twenty-five percent of the cross section area of the pipe. There are also scattered perforations approximately 5' at the south outlet end. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 909899 | 890106 | U | 2026 | 9000 | 1000 | 10000 | NHPP | Active | TRUE
Indiana | 2969 | 2100817 | INDOT | I-64 Small Structure Pipe Lining, 0.40 Miles East of I-265 | Correct deficiencies in small structure pipe lining on I-64 over unnamed ditch, 0.40 miles east of I-265. | Floyd | 2028 | FALSE | The purpose of this project is to correct the deficiencies in the structure in order to extend or reset the service life of the asset. The project need is based on the current condition of the structure elements. There is a significant amount of sediment in the pipe and there is significant corrosion and deep pitting in the invert of the structure. The sediment in the pipe in the pipe accounts for ten to twenty-five percent of the cross section area of the pipe. There are also scattered perforations approximately 5' at the south outlet end. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 909899 | 890106 | CN | 2026 | 666095 | 74011 | 740106 | NHPP | Active | TRUE
Indiana | 2972 | 2100029 | INDOT | SR 60 New Signal Installation | New signal installation on SR 60 at the intersection of St. Joe Road East. | Clark | 2026 | FALSE | The need of this project is a crash rate higher than expected given the traffic volumes and substandard delays during peak hours. The purpose of the project is to implement improvements known to reduce crash rates at intersections and reduce the delay to acceptable levels. |  | 2680 - Safety Improvements - Indiana | 2140103 | 2140103 | ROW | 2025 | 3960 | 440 | 4400 | HSIP-ST | Active | TRUE
Indiana | 2972 | 2100029 | INDOT | SR 60 New Signal Installation | New signal installation on SR 60 at the intersection of St. Joe Road East. | Clark | 2026 | FALSE | The need of this project is a crash rate higher than expected given the traffic volumes and substandard delays during peak hours. The purpose of the project is to implement improvements known to reduce crash rates at intersections and reduce the delay to acceptable levels. |  | 2680 - Safety Improvements - Indiana | 2140103 | 2140103 | PE | 2026 | 62910 | 6990 | 69900 | HSIP-ST | Active | TRUE
Indiana | 2972 | 2100029 | INDOT | SR 60 New Signal Installation | New signal installation on SR 60 at the intersection of St. Joe Road East. | Clark | 2026 | FALSE | The need of this project is a crash rate higher than expected given the traffic volumes and substandard delays during peak hours. The purpose of the project is to implement improvements known to reduce crash rates at intersections and reduce the delay to acceptable levels. |  | 2680 - Safety Improvements - Indiana | 2140103 | 2140103 | CN | 2026 | 1577703 | 175300 | 1753003 | HSIP-ST | Active | TRUE
Indiana | 2973 | 2100800 | INDOT | SR 60 Small Structure Replacement, 1.58 Miles West of I-65 | Small structure replacement over unnamed ditch 1.58 miles west of I-65. | Clark | 2029 | FALSE | The purpose of this project is to correct the deficiencies in the structure in order to extend or reset the service life of the asset. The project need is based on the current condition of the structure elements. The pipe is either collapsed or full of sediment and cannot fail any further. The roadway is not affected, but the pipe is causing drainage issue for the nearby residents. This pipe was recently added into the inventory. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 635206 | 635206 | U | 2026 | 80000 | 20000 | 100000 | NHPP | Active | TRUE
Indiana | 2974 | 2100244 | INDOT | SR 111 Slide Correction | Slide correction on SR 111 0.7 miles south of the I-64 overpass. | Floyd | 2027 | FALSE | To stabilize the slide with solder piles, remove the barrier wall, replace the adjacent sidewalk and pavement that has been uplifted by the slide, and resurface the rest of the pavement in the project limits. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 3076842 | 3076842 | ROW | 2025 | 18000 | 2000 | 20000 | STBG-ST | Active | TRUE
Indiana | 2974 | 2100244 | INDOT | SR 111 Slide Correction | Slide correction on SR 111 0.7 miles south of the I-64 overpass. | Floyd | 2027 | FALSE | To stabilize the slide with solder piles, remove the barrier wall, replace the adjacent sidewalk and pavement that has been uplifted by the slide, and resurface the rest of the pavement in the project limits. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 3076842 | 3076842 | U | 2026 | 16000 | 4000 | 20000 | STBG-ST | Active | TRUE
Indiana | 2974 | 2100244 | INDOT | SR 111 Slide Correction | Slide correction on SR 111 0.7 miles south of the I-64 overpass. | Floyd | 2027 | FALSE | To stabilize the slide with solder piles, remove the barrier wall, replace the adjacent sidewalk and pavement that has been uplifted by the slide, and resurface the rest of the pavement in the project limits. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 3076842 | 3076842 | CN | 2027 | 1305322 | 145036 | 1450358 | STBG-ST | Active | TRUE
Indiana | 2976 | 2100683 | INDOT | SR 265 Utica-Sellersburg Road Bridge | Bridge thin deck overlay on SR 265 Utica-Sellersburg Road bridge over SR 265 EB/WB, 00.83 miles east of SR 62. | Clark | 2026 | FALSE | The purpose of this project is to protect the existing deck with a preventative maintenance wearing surface treatment to help extend the service life of the bridge deck. The project need is based on the current condition of the structure elements and notable deficiencies in the wearing surface. This bridge was built in 2015 and has never received a wearing surface treatment to date. There are minor cracks throughout the wearing surface that could benefit from additional protection through a preventative maintenance wearing surface treatment. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 333000 | 333000 | C | 2026 | 227700 | 25300 | 253000 | NHPP | Active | TRUE
Indiana | 2978 | 2100834 | INDOT | SR 60 Small Structure Pipe Lining Over East SR 335 | SR 60 small structure pipe lining 4.5 miles east of SR 335. | Clark | 2026 | FALSE | The purpose of this project is to correct the deficiencies in the structure inorder to extend or reset the service life of the asset. The project need is based on the current condition of the structure elements. Heavy corrosionand pitting is occurring in the flow line, and sediment has built up in the flowline. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 434788 | 434788 | CN | 2026 | 203173 | 22575 | 225748 | NHPP | Active | TRUE
Indiana | 2978 | 2100834 | INDOT | SR 60 Small Structure Pipe Lining Over East SR 335 | SR 60 small structure pipe lining 4.5 miles east of SR 335. | Clark | 2026 | FALSE | The purpose of this project is to correct the deficiencies in the structure inorder to extend or reset the service life of the asset. The project need is based on the current condition of the structure elements. Heavy corrosionand pitting is occurring in the flow line, and sediment has built up in the flowline. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 434788 | 434788 | U | 2026 | 9000 | 1000 | 10000 | NHPP | Active | TRUE
Indiana | 3018 | 2300582 | Clarksville | Progress Way Roadway Improvements | The project will install new curb and gutter, sidewalks, and drainage along Progress Way from I-65 to Broadway. The width of the lanes will not change, instead they will be shifted south slightly to allow for drainage improvements. | Clark | 2028 | FALSE | The Town is seeing significant growth along Progress Way. This includes the addition of Cunningham Campers and a large apartment complex, both near the Addmore Lane Intersection. The area is already well traveled as a bypass around Veteran's Parkway and the additional apartments will increase the traffic on the roadway. There is not a need for capacity, but instead a need to increase safety along the roadway. The road lacks drainage, curbs, gutters and a walking path. These are needed to increase safety along the entire corridor. The area west of Sam Gwin is highly traveled by individuals living in the Senior Housing along Greentree North. They often travel in and cross the roadway in their motorized scooters. This very unsafe and the proposed improvements will give them a place to safely cross and travel. |  |  | 5795000 | 5795000 | ROW | 2025 | 100000 | 25000 | 125000 | Group III | Active | TRUE
Indiana | 3018 | 2300582 | Clarksville | Progress Way Roadway Improvements | The project will install new curb and gutter, sidewalks, and drainage along Progress Way from I-65 to Broadway. The width of the lanes will not change, instead they will be shifted south slightly to allow for drainage improvements. | Clark | 2028 | FALSE | The Town is seeing significant growth along Progress Way. This includes the addition of Cunningham Campers and a large apartment complex, both near the Addmore Lane Intersection. The area is already well traveled as a bypass around Veteran's Parkway and the additional apartments will increase the traffic on the roadway. There is not a need for capacity, but instead a need to increase safety along the roadway. The road lacks drainage, curbs, gutters and a walking path. These are needed to increase safety along the entire corridor. The area west of Sam Gwin is highly traveled by individuals living in the Senior Housing along Greentree North. They often travel in and cross the roadway in their motorized scooters. This very unsafe and the proposed improvements will give them a place to safely cross and travel. |  |  | 5795000 | 5795000 | ROW | 2025 | 300000 | 75000 | 375000 | STBG-MPO | Active | TRUE
Indiana | 3018 | 2300582 | Clarksville | Progress Way Roadway Improvements | The project will install new curb and gutter, sidewalks, and drainage along Progress Way from I-65 to Broadway. The width of the lanes will not change, instead they will be shifted south slightly to allow for drainage improvements. | Clark | 2028 | FALSE | The Town is seeing significant growth along Progress Way. This includes the addition of Cunningham Campers and a large apartment complex, both near the Addmore Lane Intersection. The area is already well traveled as a bypass around Veteran's Parkway and the additional apartments will increase the traffic on the roadway. There is not a need for capacity, but instead a need to increase safety along the roadway. The road lacks drainage, curbs, gutters and a walking path. These are needed to increase safety along the entire corridor. The area west of Sam Gwin is highly traveled by individuals living in the Senior Housing along Greentree North. They often travel in and cross the roadway in their motorized scooters. This very unsafe and the proposed improvements will give them a place to safely cross and travel. |  |  | 5795000 | 5795000 | CE | 2027 | 336000 | 84000 | 420000 | STBG-MPO | Active | TRUE
Indiana | 3018 | 2300582 | Clarksville | Progress Way Roadway Improvements | The project will install new curb and gutter, sidewalks, and drainage along Progress Way from I-65 to Broadway. The width of the lanes will not change, instead they will be shifted south slightly to allow for drainage improvements. | Clark | 2028 | FALSE | The Town is seeing significant growth along Progress Way. This includes the addition of Cunningham Campers and a large apartment complex, both near the Addmore Lane Intersection. The area is already well traveled as a bypass around Veteran's Parkway and the additional apartments will increase the traffic on the roadway. There is not a need for capacity, but instead a need to increase safety along the roadway. The road lacks drainage, curbs, gutters and a walking path. These are needed to increase safety along the entire corridor. The area west of Sam Gwin is highly traveled by individuals living in the Senior Housing along Greentree North. They often travel in and cross the roadway in their motorized scooters. This very unsafe and the proposed improvements will give them a place to safely cross and travel. |  |  | 5795000 | 5795000 | CN | 2027 | 3200000 | 800000 | 4000000 | STBG-MPO | Active | TRUE
Indiana | 3018 | 2300582 | Clarksville | Progress Way Roadway Improvements | The project will install new curb and gutter, sidewalks, and drainage along Progress Way from I-65 to Broadway. The width of the lanes will not change, instead they will be shifted south slightly to allow for drainage improvements. | Clark | 2028 | FALSE | The Town is seeing significant growth along Progress Way. This includes the addition of Cunningham Campers and a large apartment complex, both near the Addmore Lane Intersection. The area is already well traveled as a bypass around Veteran's Parkway and the additional apartments will increase the traffic on the roadway. There is not a need for capacity, but instead a need to increase safety along the roadway. The road lacks drainage, curbs, gutters and a walking path. These are needed to increase safety along the entire corridor. The area west of Sam Gwin is highly traveled by individuals living in the Senior Housing along Greentree North. They often travel in and cross the roadway in their motorized scooters. This very unsafe and the proposed improvements will give them a place to safely cross and travel. |  |  | 5795000 | 5795000 | U | 2027 | 700000 | 175000 | 875000 | STBG-MPO | Active | TRUE
Indiana | 3019 | 2301311 | Clarksville | Stansifer Avenue Streetscape Improvements | The project is a complete overhaul of Stansifer Avenue from Akers Avenue to South Clark Boulevard. The roadway will have new landscaped medians, curb and gutter, the addition of on-street parking, narrowing of the lane widths and drainage improvements. The project will also include pedestrian sidewalk upgrades and widening to at least 5' and designated bike lanes. | Clark | 2030 | FALSE | Stansifer Avenue is directly off of I-65 and is a key exit for the Town’s South End Redevelopment, as well as Orgin Park. The Town recently built a new Fire Station on Stansifer Avenue and is working to redevelop the area. Stansifer Avenue is seen as one of the Gateway’s to the Town. It will provide main access to two large development ares in Town. However it is unsafe. The lanes are almost 20 feet wide in some areas, which leads drivers to think that there are two lanes, when there is only one. This causes confusion and can lead to unnecessary accidents. The roadway also lacks parking and drainage. It needs improvement across the board. |  |  | 5000000 | 5000000 | PE | 2025 | 323000 | 80750 | 403750 | STBG-MPO | Active | TRUE
Indiana | 3019 | 2301311 | Clarksville | Stansifer Avenue Streetscape Improvements | The project is a complete overhaul of Stansifer Avenue from Akers Avenue to South Clark Boulevard. The roadway will have new landscaped medians, curb and gutter, the addition of on-street parking, narrowing of the lane widths and drainage improvements. The project will also include pedestrian sidewalk upgrades and widening to at least 5' and designated bike lanes. | Clark | 2030 | FALSE | Stansifer Avenue is directly off of I-65 and is a key exit for the Town’s South End Redevelopment, as well as Orgin Park. The Town recently built a new Fire Station on Stansifer Avenue and is working to redevelop the area. Stansifer Avenue is seen as one of the Gateway’s to the Town. It will provide main access to two large development ares in Town. However it is unsafe. The lanes are almost 20 feet wide in some areas, which leads drivers to think that there are two lanes, when there is only one. This causes confusion and can lead to unnecessary accidents. The roadway also lacks parking and drainage. It needs improvement across the board. |  |  | 5000000 | 5000000 | ROW | 2027 | 80000 | 20000 | 100000 | STBG-MPO | Active | TRUE
Indiana | 3025 | 1902858, 2301561 | INDOT | Henryville Welcome Center Reconstruction | Rest area modernization project in Henryville on I-65 north bound at mile marker 22. | Clark | 2030 | FALSE | The Henryville Welcome Center will be reconstructed to help meet the needs of the traveling public. The welcome center building will be redesigned to accommodate a higher volume of travelers and the parking lot will be reconfigured to increase truck parking spaces by a minimum of 36 spaces. |  |  | 50599576 | 50599576 | PE | 2025 | 314000 | 0 | 314000 | NHPP | Active | TRUE
Indiana | 3025 | 1902858, 2301561 | INDOT | Henryville Welcome Center Reconstruction | Rest area modernization project in Henryville on I-65 north bound at mile marker 22. | Clark | 2030 | FALSE | The Henryville Welcome Center will be reconstructed to help meet the needs of the traveling public. The welcome center building will be redesigned to accommodate a higher volume of travelers and the parking lot will be reconfigured to increase truck parking spaces by a minimum of 36 spaces. |  |  | 50599576 | 50599576 | PE | 2025 | 419745 | 0 | 419745 | NHPP | Active | TRUE
Indiana | 3025 | 1902858, 2301561 | INDOT | Henryville Welcome Center Reconstruction | Rest area modernization project in Henryville on I-65 north bound at mile marker 22. | Clark | 2030 | FALSE | The Henryville Welcome Center will be reconstructed to help meet the needs of the traveling public. The welcome center building will be redesigned to accommodate a higher volume of travelers and the parking lot will be reconfigured to increase truck parking spaces by a minimum of 36 spaces. |  |  | 50599576 | 50599576 | ROW | 2026 | 80000 | 0 | 80000 | NHPP | Active | TRUE
Indiana | 3025 | 1902858, 2301561 | INDOT | Henryville Welcome Center Reconstruction | Rest area modernization project in Henryville on I-65 north bound at mile marker 22. | Clark | 2030 | FALSE | The Henryville Welcome Center will be reconstructed to help meet the needs of the traveling public. The welcome center building will be redesigned to accommodate a higher volume of travelers and the parking lot will be reconfigured to increase truck parking spaces by a minimum of 36 spaces. |  |  | 50599576 | 50599576 | PE | 2026 | 1297026 | 0 | 1297026 | NHPP | Active | TRUE
Indiana | 3025 | 1902858, 2301561 | INDOT | Henryville Welcome Center Reconstruction | Rest area modernization project in Henryville on I-65 north bound at mile marker 22. | Clark | 2030 | FALSE | The Henryville Welcome Center will be reconstructed to help meet the needs of the traveling public. The welcome center building will be redesigned to accommodate a higher volume of travelers and the parking lot will be reconfigured to increase truck parking spaces by a minimum of 36 spaces. |  |  | 50599576 | 50599576 | CN | 2028 | 45000000 | 0 | 45000000 | NHPP | Active | TRUE
Indiana | 3032 | 2001595 | INDOT | I-65 Small Structure Pipe Lining | Small structure pipe lining on I-65, 3.54 miles north of SR 160. | Clark | 2026 | FALSE | This project will improve the conditions of the small structure and extend its service life. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 615113 | 615113 | CN | 2025 | 553602 | 61511 | 615113 | NHPP | Active | TRUE
Indiana | 3033 | 2001597 | INDOT | I-65 Small Structure | Small structure paved invert on I-65, 3.42 mile north of SR 160. | Clark | 2026 | FALSE | This project will improve the conditions of the small structure and extend its service life. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 824380 | 824380 | CN | 2025 | 741942 | 82438 | 824380 | NHPP | Active | TRUE
Indiana | 3034 | 2001598 | INDOT | I-65 Small Structure | Small structure paved invert on I-65, 0.67 mile north of SR 160. | Clark | 2026 | FALSE | This project will improve the condition of the structure and extend its service life. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 658234 | 658234 | CN | 2025 | 592411 | 65823 | 658234 | NHPP | Active | TRUE
Indiana | 3049 | 2200718 | INDOT | I-64 Bridge Deck Overlay | Bridge deck overlay on I-64 over the I-64 Ramp 123D to I-64 westbound, 0.28 miles west of SR 111. | Floyd | 2028 | FALSE | This project will improve the condition of the bridge and extend its service life. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 700748 | 700748 | CN | 2026 | 473173 | 52575 | 525748 | NHS | Active | TRUE
Indiana | 3050 | 2200719 | INDOT | I-64 Bridge Deck Overlay | Bridge deck overlay on I-64 over SR 62X/Spring Street, 0.18 west of SR 111. | Floyd | 2028 | FALSE | This project will improve the conditions of the bridge and extend its service life. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 2372840 | 2372840 | PE | 2025 | 270000 | 30000 | 300000 | NHPP | Active | TRUE
Indiana | 3050 | 2200719 | INDOT | I-64 Bridge Deck Overlay | Bridge deck overlay on I-64 over SR 62X/Spring Street, 0.18 west of SR 111. | Floyd | 2028 | FALSE | This project will improve the conditions of the bridge and extend its service life. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 2372840 | 2372840 | CN | 2026 | 1847556 | 205284 | 2052840 | NHPP | Active | TRUE
Indiana | 3050 | 2200719 | INDOT | I-64 Bridge Deck Overlay | Bridge deck overlay on I-64 over SR 62X/Spring Street, 0.18 west of SR 111. | Floyd | 2028 | FALSE | This project will improve the conditions of the bridge and extend its service life. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 2372840 | 2372840 | U | 2026 | 18000 | 2000 | 20000 | NHPP | Active | TRUE
Indiana | 3051 | 2200873 | INDOT | I-265 Over Slate Run Creek Scour Protection | Scour and erosion protection on I-265 over Slate Run Creek, 0.2 mile south of I-265. | Floyd | 2027 | FALSE | The project will correct the deficiencies with erosion and scour at the outlet (east end) of the structure. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 632559 | 632559 | ROW | 2025 | 36000 | 4000 | 40000 | NHPP | Active | TRUE
Indiana | 3051 | 2200873 | INDOT | I-265 Over Slate Run Creek Scour Protection | Scour and erosion protection on I-265 over Slate Run Creek, 0.2 mile south of I-265. | Floyd | 2027 | FALSE | The project will correct the deficiencies with erosion and scour at the outlet (east end) of the structure. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 632559 | 632559 | ROW | 2026 | 11250 | 1250 | 12500 | NHPP | Active | TRUE
Indiana | 3051 | 2200873 | INDOT | I-265 Over Slate Run Creek Scour Protection | Scour and erosion protection on I-265 over Slate Run Creek, 0.2 mile south of I-265. | Floyd | 2027 | FALSE | The project will correct the deficiencies with erosion and scour at the outlet (east end) of the structure. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 632559 | 632559 | CN | 2027 | 343682 | 38187 | 381869 | NHPP | Active | TRUE
Indiana | 3054 | 2200052 | INDOT | SR 60 at St. Joe Road West Intersection Improvement | Intersection improvement with added turn lanes at SR 60 and St. Joe Road West. | Clark | 2028 | FALSE | This project will improve safety concerns at the intersection of SR 60 and St. Joe Road West. |  | 2680 - Safety Improvements - Indiana | 2421116 | 2421116 | ROW | 2025 | 48000 | 12000 | 60000 | NHPP | Active | TRUE
Indiana | 3054 | 2200052 | INDOT | SR 60 at St. Joe Road West Intersection Improvement | Intersection improvement with added turn lanes at SR 60 and St. Joe Road West. | Clark | 2028 | FALSE | This project will improve safety concerns at the intersection of SR 60 and St. Joe Road West. |  | 2680 - Safety Improvements - Indiana | 2421116 | 2421116 | U | 2027 | 40000 | 10000 | 50000 | NHPP | Active | TRUE
Indiana | 3054 | 2200052 | INDOT | SR 60 at St. Joe Road West Intersection Improvement | Intersection improvement with added turn lanes at SR 60 and St. Joe Road West. | Clark | 2028 | FALSE | This project will improve safety concerns at the intersection of SR 60 and St. Joe Road West. |  | 2680 - Safety Improvements - Indiana | 2421116 | 2421116 | CN | 2027 | 1072813 | 268203 | 1341016 | NHPP | Active | TRUE
Indiana | 3055 | 2100250 | INDOT | US 150 Hot-Mix Asphalt (HMA) Overlay, Minor Structural | Hot-mix asphalt (HMA) overlay, minor structural, on US 150 from SR 135 to SR 335. | Floyd | 2026 | FALSE | This project will improve the condition of the pavement. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 533160 | 533160 | ROW | 2025 | 28000 | 7000 | 35000 | NHPP | Active | TRUE
Indiana | 3056 | 2201148 | INDOT | US 150 Small Structures & Drains Construction (16 Locations) | Small structures and drains construction on US 150 at various locations between 3.32 miles west of I-64 (near Buck Creek Road) to I-64. | Floyd | 2028 | FALSE | This project will improve the conditions of various culverts on US 150. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 4111651 | 4111651 | CN | 2028 | 2489321 | 622330 | 3111651 | STBG-ST | Active | TRUE
Indiana | 3102 | 2301317 | New Albany | Graybrook Lane Extension | Extension of collector class roadway (Graybrook Lane) from the intersection with Bono Road/Pearl Street to the intersection of State Street. This roadway extension would further establish connections from economically depressed areas to the vital State Street corridor. | Floyd | 2031 | FALSE | Graybrook Lane currently deadends into Pearl Street/Bono Road intersection. By extending Graybrook Lane, the collector class roadway would be extended to an important arterial roadway of State Street which would allow citizens an easier route to connect to shopping, vital services, and transit. Furthermore, this project would allow better connections for the citizens adjacent to this project. |  |  | 3708432 | 1014745 | PE | 2025 | 357109 | 108636 | 465745 | STBG-MPO | Active | TRUE
Indiana | 3136 | 2301550 | New Albany | Intersection of East Spring Street and Beharrell Avenue | Improvement of the intersection of East Spring Street (a major arterial and gateway into the community with Beharrell Avenue (a collector class roadway). The concept is to utilize a roundabout, a proven safety counter measure, in order to improve the safety of this intersection, slow traffic entering the City of New Albany, and to enhance the livability and walkability of the surrounding areas of the community. This would also allow for a connection to the Ohio River Greenway, and provide a road diet on Spring Street that will accommodate bicycle facilities, parking, and other amenities for the community which will make this corridor more functional for all citizens and not solely drivers. The cost estimate for these intersection improvements is $3,230,000. | Floyd | 2029 | FALSE | The City of New Albany is always looking to improve the safety of our roadways and intersections. The current configuration of East Spring Street effectively bisects the neighborhood along Beharrell Avenue. This project will reunite the community, improve safety, improve walkability, improve quality of place and life, all while utilizing a proven safety counter measure that is championed by the FHWA. Furthermore, this project will connect neighborhoods to the north of East Spring Street with the vital community asset that is the Ohio River Greenway. |  |  | 2871112 | 2871112 | PE | 2026 | 252000 | 28000 | 280000 | HSIP-MPO | Active | TRUE
Indiana | 3136 | 2301550 | New Albany | Intersection of East Spring Street and Beharrell Avenue | Improvement of the intersection of East Spring Street (a major arterial and gateway into the community with Beharrell Avenue (a collector class roadway). The concept is to utilize a roundabout, a proven safety counter measure, in order to improve the safety of this intersection, slow traffic entering the City of New Albany, and to enhance the livability and walkability of the surrounding areas of the community. This would also allow for a connection to the Ohio River Greenway, and provide a road diet on Spring Street that will accommodate bicycle facilities, parking, and other amenities for the community which will make this corridor more functional for all citizens and not solely drivers. The cost estimate for these intersection improvements is $3,230,000. | Floyd | 2029 | FALSE | The City of New Albany is always looking to improve the safety of our roadways and intersections. The current configuration of East Spring Street effectively bisects the neighborhood along Beharrell Avenue. This project will reunite the community, improve safety, improve walkability, improve quality of place and life, all while utilizing a proven safety counter measure that is championed by the FHWA. Furthermore, this project will connect neighborhoods to the north of East Spring Street with the vital community asset that is the Ohio River Greenway. |  |  | 2871112 | 2871112 | ROW | 2027 | 400000 | 44445 | 444445 | HSIP-MPO | Active | TRUE
Indiana | 3142 | 2001599 | INDOT | I-65 Small Structure Pipe Lining | Small structure pipe lining on I-65, 9.21 miles north of SR 311. | Clark | 2026 | FALSE | This project will improve the current condition of the structure and extend its service life. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 454927 | 454927 | CN | 2025 | 409434 | 45493 | 454927 | NHPP | Active | TRUE
Indiana | 3143 | 2001600 | INDOT | I-65 Bridge Widening at Brownstown Road | Bridge widening on the southbound I-65 at Brownstown Road, 2.03 miles north of SR 160. | Clark | 2026 | FALSE | This is a bridge widening project on I-65 to accommodate the new added travel lane. |  |  | 852848 | 852848 | CN | 2025 | 767563 | 85285 | 852848 | NHPP | Active | TRUE
Indiana | 3144 | 2001601 | INDOT | I-65 Bridge Widening at Brownstown Road | Bridge widening on northbound I-65 at Brownstown Road, 2.03 mile north of SR 160. | Clark | 2026 | FALSE | This project will widen the bridge to accommodate the added travel lanes project on I-65. |  |  | 852848 | 852848 | CN | 2025 | 767563 | 85285 | 852848 | NHPP | Active | TRUE
Indiana | 3145 | 2001181 | INDOT | SR 62 Intersection Improvement | Intersection improvement on SR 62 at SR 3 and Charlestown Landing Road. | Clark | 2025 | FALSE | This project will add left turn lanes on SR 62 which will increase capacity and improve safety at this intersection. |  | 2678 - Roadway Operational Improvements - Indiana | 263000 | 262600 | CN | 2025 | 210000 | 52600 | 262600 | STBG-ST | Active | TRUE
Indiana | 3147 | 1800706 | INDOT | US 150 Bridge Painting | Bridge painting on US 150, 8.81 miles east of SR 335 over I-64 eastbound/westbound. | Floyd | 2027 | FALSE | This project will paint the bridge on US 150 over I-64 Eastbound/Westbound to extend the service life of the bridge. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 183892 | 183892 | CN | 2026 | 147114 | 36778 | 183892 | STBG-ST | Active | TRUE
Indiana | 3148 | 2100019 | INDOT | I-64 Lighting | Lighting improvements from the I-64/I-265 interchange to US 150. | Floyd | 2028 | FALSE | This project will improve visibility and safety conditions along I-64 from the I-64/I-265 interchange to US 150. |  |  | 11542765 | 11542765 | CN | 2026 | 5642429 | 626937 | 6269366 | NHPP | Active | TRUE
Indiana | 3148 | 2100019 | INDOT | I-64 Lighting | Lighting improvements from the I-64/I-265 interchange to US 150. | Floyd | 2028 | FALSE | This project will improve visibility and safety conditions along I-64 from the I-64/I-265 interchange to US 150. |  |  | 11542765 | 11542765 | CN | 2026 | 5273400 | 0 | 5273400 | HSIP-ST | Active | TRUE
Indiana | 3149 | 2200015 | INDOT | I-64 Westbound Lane Over Quarry Road Bridge Replacement | Bridge replacement of the I-64 westbound lane bridge over Quarry Road. | Floyd | 2028 | FALSE | This is a bridge replacement project to accommodate the added travel lanes contract on I-64. |  |  | 3767102 | 3767102 | CN | 2026 | 3390392 | 376710 | 3767102 | NHPP | Active | TRUE
Indiana | 3150 | 2200016 | INDOT | I-64 New Bridge Over I-64 EB to I-265 EB Ramp | New bridge construction on I-64 over the I-64 eastbound to the I-265 eastbound ramp. | Floyd | 2028 | FALSE | This project will provide a new eastbound alignment over I-64 eastbound to the I-265 eastbound ramp. |  |  | 8954952 | 8954952 | CN | 2026 | 8059457 | 895495 | 8954952 | NHPP | Active | TRUE
Indiana | 3151 | 2200017 | INDOT | I-64 Eastbound Bridge Replacement Over Captain Frank Road | I-64 bridge replacement on I-64 eastbound over Captain Frank Road. | Floyd | 2028 | FALSE | This is a bridge replacement on I-64 eastbound over Captain Frank Road to accommodate the I-64 added travel lanes project. |  |  | 3583038 | 3583038 | CN | 2026 | 3224734 | 358304 | 3583038 | NHPP | Active | TRUE
Indiana | 3152 | 2200018 | INDOT | I-64 Westbound Bridge Replacement Over Captain Frank Road | Bridge replacement on I-64 westbound over Captain Frank Road. | Floyd | 2028 | FALSE | This is a bridge replacement project to accommodate the I-64 added travel lanes project. |  |  | 5784170 | 5784170 | CN | 2026 | 5205753 | 578417 | 5784170 | NHPP | Active | TRUE
Indiana | 3153 | 2200019 | INDOT | I-265 Bridge Replacement | Bridge replacement on I-265 from the westbound I-265 ramp to EB I-64 over eastbound I-64 to eastbound I-265 ramp. | Floyd | 2030 | FALSE | This project will replace the I-265 bridge to accommodate the I-64 added travel lanes project. |  |  | 6481377 | 12962754 | CN | 2026 | 5833239 | 648138 | 6481377 | NHPP | Active | TRUE
Indiana | 3153 | 2200019 | INDOT | I-265 Bridge Replacement | Bridge replacement on I-265 from the westbound I-265 ramp to EB I-64 over eastbound I-64 to eastbound I-265 ramp. | Floyd | 2030 | FALSE | This project will replace the I-265 bridge to accommodate the I-64 added travel lanes project. |  |  | 6481377 | 12962754 | CN | 2026 | 5833239 | 648138 | 6481377 | NHPP | Active | TRUE
Indiana | 3154 | 2200994 | INDOT | US 150 Bridge Rehab Pipe Lining | Bridge rehab pipe lining on US 150 over unknown tributary Little Indian Creek, 0.14 mile west of I-64. | Floyd | 2027 | FALSE | This is a bridge rehab pipe lining on US 150 to improve the condition of the structure and extend its service life. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 93200 | 93200 | CN | 2026 | 74560 | 18640 | 93200 | STBG-ST | Active | TRUE
Indiana | 3155 | 1900373 | INDOT | SR 60 Intersection Improvement | Intersection improvement with added turn lanes at the intersection of SR 60 and Twinbrook Drive/Old SR 60 in Sellersburg. | Clark | 2029 | FALSE | This project will improve the safety of the intersection by adding eastbound and westbound left turn lanes on SR 60. |  |  | 1498808 | 1498808 | PE | 2025 | 278960 | 69740 | 348700 | NHPP | Active | TRUE
Indiana | 3155 | 1900373 | INDOT | SR 60 Intersection Improvement | Intersection improvement with added turn lanes at the intersection of SR 60 and Twinbrook Drive/Old SR 60 in Sellersburg. | Clark | 2029 | FALSE | This project will improve the safety of the intersection by adding eastbound and westbound left turn lanes on SR 60. |  |  | 1498808 | 1498808 | ROW | 2027 | 6000 | 1500 | 7500 | NHPP | Active | TRUE
Indiana | 3156 | 2200698 | INDOT | SR 160 Bridge Deck Overlay | Bridge deck overlay on SR 160 over I-65, 0.54 mile west of US 31. | Clark | 2029 | FALSE | This project will improve the condition of the bridge and extend its service life. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 2435491 | 2435491 | U | 2027 | 8000 | 2000 | 10000 | STBG-ST | Active | TRUE
Indiana | 3157 | 2200837 | INDOT | US 150 Hot-Mix Asphalt (HMA) Overlay | Hot-mix asphalt (HMA) overlay, preventive maintenance, on US 150 from 3.32 miles west of I-64 (near Buck Creek) to I-64. | Floyd | 2027 | FALSE | This project will improve the conditions of the pavement and extend its service life. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 3862000 | 3862000 | ROW | 2025 | 40000 | 10000 | 50000 | STBG-ST | Active | TRUE
Indiana | 3157 | 2200837 | INDOT | US 150 Hot-Mix Asphalt (HMA) Overlay | Hot-mix asphalt (HMA) overlay, preventive maintenance, on US 150 from 3.32 miles west of I-64 (near Buck Creek) to I-64. | Floyd | 2027 | FALSE | This project will improve the conditions of the pavement and extend its service life. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 3862000 | 3862000 | CN | 2028 | 3049600 | 762400 | 3812000 | STBG-ST | Active | TRUE
Indiana | 3158 | 2200963 | INDOT | US 31 Concrete Pavement Restoration | Concrete pavement restoration on US 31 from 0.99 miles north of I-65 to 3.41 miles south of SR 60. | Clark | 2030 | FALSE | This project will improve the conditions of the pavement and extend its service life. |  |  | 4853634 | 4853634 | PE | 2025 | 418303 | 104576 | 522879 | STBG-ST | Active | TRUE
Indiana | 3158 | 2200963 | INDOT | US 31 Concrete Pavement Restoration | Concrete pavement restoration on US 31 from 0.99 miles north of I-65 to 3.41 miles south of SR 60. | Clark | 2030 | FALSE | This project will improve the conditions of the pavement and extend its service life. |  |  | 4853634 | 4853634 | RR | 2027 | 8000 | 2000 | 10000 | STBG-ST | Active | TRUE
Indiana | 3158 | 2200963 | INDOT | US 31 Concrete Pavement Restoration | Concrete pavement restoration on US 31 from 0.99 miles north of I-65 to 3.41 miles south of SR 60. | Clark | 2030 | FALSE | This project will improve the conditions of the pavement and extend its service life. |  |  | 4853634 | 4853634 | U | 2027 | 8000 | 2000 | 10000 | STBG-ST | Active | TRUE
Indiana | 3161 | 2400027 | INDOT | Statewide Wrong Way Ramp Entry Project | Install wrong way signs with lights on a detector, powered by either solar installation or grid hookup. I-65 southbound at Broadway Street ramp from collector-distributor (MP 4). The exit ramp from the collector-distributer road from I-65 SB to Broadway Street will have new signs and detection. | Clark | 2025 | FALSE | The effort is aimed at targeting ramps that are near locations of wrong way crashes on the Interstate and the likely entry location as well as ramps that have similar attributes. The plan is to install a mid-level treatment with detection and pole assembly holding an off the shelf available system, using a sign with flashing LED along the border on a pole at the primary locations. The secondary locations will then receive an entry-level treatment consisting of a solar powered flashing beacon. |  | 2678 - Roadway Operational Improvements - Indiana | 178076 | 178076 | CN | 2025 | 139945 | 15550 | 155495 | NHPP | Active | TRUE
Indiana | 3162 | 2101785 | INDOT | Repair or Replace Lighting at Various Locations in Seymour District | Replace or repair lighting with LED at various locations within the Seymour District. | Clark, Floyd | 2025 | FALSE | This project will provide maintenance and upgrades to the lighting within Seymour District which will improve safety and visibility. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 2600000 | 2600000 | CN | 2025 | 2080000 | 520000 | 2600000 | STBG-ST | Active | TRUE
Indiana | 3177 | 2301301 | Clark County | Jeffersonville-Charlestown Pike Improvements | The Jeffersonville-Charlestown Pike project begins at the intersection of Jeffersonville-Charlestown Pike and Salem Noble Road and extend 0.8 miles to the intersection with Highway 62. The project will extend the Jeffersonville Project that begins at Utica-Sellersburg Road and extends to Salem-Noble Road. The improvements planned include an increased shoulder for bike traffic and an area for sidewalks to be added by developers or property owners fronting the project. Improved traffic flow and alternative means of travel will be offered and will help improve emissions. The multiuse path is being added to protect and help provide alternatives for local residents. | Clark | 2028 | FALSE | The project is an extension of the Jeffersonville project to improve Jeffersonville-Charlestown Pike from Utica-Sellersburg Road ultimately to Highway 62. This improved road will provide an alternative to Highway 62 for local residents. The multi-use path will provide safe alternatives for residents in the area. |  |  | 5081250 | 5081250 | ROW | 2027 | 765000 | 191250 | 956250 | TA-MPO | Active | TRUE
Indiana | 3177 | 2301301 | Clark County | Jeffersonville-Charlestown Pike Improvements | The Jeffersonville-Charlestown Pike project begins at the intersection of Jeffersonville-Charlestown Pike and Salem Noble Road and extend 0.8 miles to the intersection with Highway 62. The project will extend the Jeffersonville Project that begins at Utica-Sellersburg Road and extends to Salem-Noble Road. The improvements planned include an increased shoulder for bike traffic and an area for sidewalks to be added by developers or property owners fronting the project. Improved traffic flow and alternative means of travel will be offered and will help improve emissions. The multiuse path is being added to protect and help provide alternatives for local residents. | Clark | 2028 | FALSE | The project is an extension of the Jeffersonville project to improve Jeffersonville-Charlestown Pike from Utica-Sellersburg Road ultimately to Highway 62. This improved road will provide an alternative to Highway 62 for local residents. The multi-use path will provide safe alternatives for residents in the area. |  |  | 5081250 | 5081250 | C | 2028 | 3300000 | 825000 | 4125000 | CRP-MPO | Active | TRUE
Indiana | 3180 | 2301302 | Clark County | Henryville Sidewalks | The existing sidewalks in the Henryville area are crumbling and do not currently meet ADA requirements. Ramps will be added at intersections and slopes will be adjusted to help meet current ADA requirements. Extending sidewalks from the Henryville High School to the local library should also help the community. | Clark | 2029 | FALSE | Sidewalks in the Henryville area do not currently meet ADA requirements. Improvements to the sidewalks including but not limited to curb ramps, sidewalk ramps and other improvements as well as extending the sidewalks to the Henryville School are planned for this project. |  |  | 2242683 | 2242683 | PE | 2025 | 144000 | 36000 | 180000 | TA-MPO | Active | TRUE
Indiana | 3180 | 2301302 | Clark County | Henryville Sidewalks | The existing sidewalks in the Henryville area are crumbling and do not currently meet ADA requirements. Ramps will be added at intersections and slopes will be adjusted to help meet current ADA requirements. Extending sidewalks from the Henryville High School to the local library should also help the community. | Clark | 2029 | FALSE | Sidewalks in the Henryville area do not currently meet ADA requirements. Improvements to the sidewalks including but not limited to curb ramps, sidewalk ramps and other improvements as well as extending the sidewalks to the Henryville School are planned for this project. |  |  | 2242683 | 2242683 | PE | 2025 | 19445 | 4861 | 24306 | Group III | Active | TRUE
Indiana | 3180 | 2301302 | Clark County | Henryville Sidewalks | The existing sidewalks in the Henryville area are crumbling and do not currently meet ADA requirements. Ramps will be added at intersections and slopes will be adjusted to help meet current ADA requirements. Extending sidewalks from the Henryville High School to the local library should also help the community. | Clark | 2029 | FALSE | Sidewalks in the Henryville area do not currently meet ADA requirements. Improvements to the sidewalks including but not limited to curb ramps, sidewalk ramps and other improvements as well as extending the sidewalks to the Henryville School are planned for this project. |  |  | 2242683 | 2242683 | PE | 2026 | 49872 | 12468 | 62340 | Group III | Active | TRUE
Indiana | 3180 | 2301302 | Clark County | Henryville Sidewalks | The existing sidewalks in the Henryville area are crumbling and do not currently meet ADA requirements. Ramps will be added at intersections and slopes will be adjusted to help meet current ADA requirements. Extending sidewalks from the Henryville High School to the local library should also help the community. | Clark | 2029 | FALSE | Sidewalks in the Henryville area do not currently meet ADA requirements. Improvements to the sidewalks including but not limited to curb ramps, sidewalk ramps and other improvements as well as extending the sidewalks to the Henryville School are planned for this project. |  |  | 2242683 | 2242683 | ROW | 2027 | 520661 | 57851 | 578512 | LSP | Active | TRUE
Indiana | 3180 | 2301302 | Clark County | Henryville Sidewalks | The existing sidewalks in the Henryville area are crumbling and do not currently meet ADA requirements. Ramps will be added at intersections and slopes will be adjusted to help meet current ADA requirements. Extending sidewalks from the Henryville High School to the local library should also help the community. | Clark | 2029 | FALSE | Sidewalks in the Henryville area do not currently meet ADA requirements. Improvements to the sidewalks including but not limited to curb ramps, sidewalk ramps and other improvements as well as extending the sidewalks to the Henryville School are planned for this project. |  |  | 2242683 | 2242683 | U | 2028 | 45000 | 5000 | 50000 | LSP | Active | TRUE
Indiana | 3182 | 2400021 | KIPDA | KIPDA Regional Rideshare Program - Indiana FY 2026 | The KIPDA Regional Rideshare Program provides ride-matching services, employer-based and regional ridesharing, vanpool subscription services, promotional activities to support ride-sharing, which includes carpooling, vanpooling, taking transit, walking, telecommuting, and bikepooling. This also includes program evaluation and administration. | Clark, Floyd | 2026 | FALSE | To reduce congestion, improve air quality, and promote sustainability. | 56 |  | 158750 | 158750 | Operations | 2026 | 127000 | 31750 | 158750 | STBG-MPO | Active | TRUE
Indiana | 3183 |  | KIPDA | KIPDA Regional Rideshare Program - Indiana FY 2027 | The KIPDA Regional Rideshare Program provides ride-matching services, employer-based and regional ridesharing, vanpool subscription services, promotional activities to support ride-sharing, which includes carpooling, vanpooling, taking transit, walking, telecommuting, and bikepooling. This also includes program evaluation and administration. | Clark, Floyd | 2027 | FALSE | To reduce congestion, improve air quality, and promote sustainability. | 56 |  | 158750 | 158750 | Operations | 2027 | 127000 | 31750 | 158750 | STBG-MPO | Active | TRUE
Indiana | 3184 |  | KIPDA | KIPDA Regional Rideshare Program - Indiana FY 2028 | The KIPDA Regional Rideshare Program provides ride-matching services, employer-based and regional ridesharing, vanpool subscription services, promotional activities to support ride-sharing, which includes carpooling, vanpooling, taking transit, walking, telecommuting, and bikepooling. This also includes program evaluation and administration. | Clark, Floyd | 2028 | FALSE | To reduce congestion, improve air quality, and promote sustainability. | 56 |  | 158750 | 158750 | Operations | 2028 | 127000 | 31750 | 158750 | STBG-MPO | Active | TRUE
Indiana | 3186 | 2500030 | APCD | Kentuckiana Air Education 2026 | Kentuckiana Air Education (KAIRE) is an air pollution prevention and awareness program that will increase public awareness of the impacts individual choices can have on local air quality. | Clark, Floyd | 2026 | FALSE | KAIRE works to encourage voluntary air quality changes through community involvement, increasing public awareness of the impacts individual choices can have on local air quality. | 370 |  | 250000 | 250000 | Operations | 2026 | 200000 | 50000 | 250000 | CMAQ-MPO | Active | TRUE
Indiana | 3187 |  | APCD | Kentuckiana Air Education 2027 | Kentuckiana Air Education (KAIRE) is an air pollution prevention and awareness program that will increase public awareness of the impacts individual choices can have on local air quality. | Clark, Floyd | 2027 | FALSE | KAIRE works to encourage voluntary air quality changes through community involvement, increasing public awareness of the impacts individual choices can have on local air quality. | 370 |  | 250000 | 250000 | Operations | 2027 | 200000 | 50000 | 250000 | CMAQ-MPO | Active | TRUE
Indiana | 3188 |  | APCD | Kentuckiana Air Education 2028 | Kentuckiana Air Education (KAIRE) is an air pollution prevention and awareness program that will increase public awareness of the impacts individual choices can have on local air quality. | Clark, Floyd | 2028 | FALSE | KAIRE works to encourage voluntary air quality changes through community involvement, increasing public awareness of the impacts individual choices can have on local air quality. | 370 |  | 250000 | 250000 | Operations | 2028 | 200000 | 50000 | 250000 | CMAQ-MPO | Active | TRUE
Indiana | 3192 | 2200833 | INDOT | I-64 Hot-Mix Asphalt (HMA) Overlay | Hot-mix asphalt (HMA) overlay minor structural on I-64 from 0.50 miles west of SR 135 to 1.01 miles west of SR 64. | Floyd | 2030 | FALSE | This project will improve the conditions of the pavement and extend its service life. |  |  | 45192754 | 45192754 | ROW | 2025 | 9000 | 1000 | 10000 | NHPP | Active | TRUE
Indiana | 3193 | 2101799 | INDOT | I-65 & Veterans Parkway | Modify I-65 and Veterans Parkway interchange by providing additional left turn capacity and adding pedestrian signal indications and push buttons at the signalized ramp terminal intersections. | Clark | 2035 | FALSE | The interchange is currently experiencing poor peak hour operating conditions that are expected to worsen. It is recommended that the interchange be modified to improve traffic operations, especially by providing additional left turn capacity. |  |  | 25580478 | 25580478 | ROW | 2025 | 180000 | 20000 | 200000 | NHPP | Active | TRUE
Indiana | 3193 | 2101799 | INDOT | I-65 & Veterans Parkway | Modify I-65 and Veterans Parkway interchange by providing additional left turn capacity and adding pedestrian signal indications and push buttons at the signalized ramp terminal intersections. | Clark | 2035 | FALSE | The interchange is currently experiencing poor peak hour operating conditions that are expected to worsen. It is recommended that the interchange be modified to improve traffic operations, especially by providing additional left turn capacity. |  |  | 25580478 | 25580478 | PE | 2026 | 2122211 | 235801 | 2358012 | NHPP | Active | TRUE
Indiana | 3193 | 2101799 | INDOT | I-65 & Veterans Parkway | Modify I-65 and Veterans Parkway interchange by providing additional left turn capacity and adding pedestrian signal indications and push buttons at the signalized ramp terminal intersections. | Clark | 2035 | FALSE | The interchange is currently experiencing poor peak hour operating conditions that are expected to worsen. It is recommended that the interchange be modified to improve traffic operations, especially by providing additional left turn capacity. |  |  | 25580478 | 25580478 | ROW | 2026 | 180000 | 20000 | 200000 | NHPP | Active | TRUE
Indiana | 3193 | 2101799 | INDOT | I-65 & Veterans Parkway | Modify I-65 and Veterans Parkway interchange by providing additional left turn capacity and adding pedestrian signal indications and push buttons at the signalized ramp terminal intersections. | Clark | 2035 | FALSE | The interchange is currently experiencing poor peak hour operating conditions that are expected to worsen. It is recommended that the interchange be modified to improve traffic operations, especially by providing additional left turn capacity. |  |  | 25580478 | 25580478 | U | 2027 | 900000 | 100000 | 1000000 | NHPP | Active | TRUE
Indiana | 3194 | 2200050 | INDOT | SR 60 & Perry Crossing Road Intersection Improvement | Intersection improvement at SR 60 and Perry Crossing Road. | Clark | 2032 | FALSE | This project will address safety concerns at the intersection of SR 60 and Perry Crossing Road. |  |  | 5646720 | 5646720 | PE | 2026 | 635945 | 0 | 635945 | HSIP-ST | Active | TRUE
Indiana | 3194 | 2200050 | INDOT | SR 60 & Perry Crossing Road Intersection Improvement | Intersection improvement at SR 60 and Perry Crossing Road. | Clark | 2032 | FALSE | This project will address safety concerns at the intersection of SR 60 and Perry Crossing Road. |  |  | 5646720 | 5646720 | PE | 2027 | 397400 | 0 | 397400 | HSIP-ST | Active | TRUE
Indiana | 3194 | 2200050 | INDOT | SR 60 & Perry Crossing Road Intersection Improvement | Intersection improvement at SR 60 and Perry Crossing Road. | Clark | 2032 | FALSE | This project will address safety concerns at the intersection of SR 60 and Perry Crossing Road. |  |  | 5646720 | 5646720 | ROW | 2028 | 100000 | 0 | 100000 | HSIP-ST | Active | TRUE
Indiana | 3215 | 2300274, 2400612 | INDOT | National Electric Vehicle Infrastructure (NEVI) | Electric vehicle charging infrastructure at various locations along Indiana interstates. Round 1 electric vehicle charging infrostructure at 4222 Charlestown Road, New Albany, IN 47150, and 1540 Veterans Parkway, Jeffersonville, IN 47130. DES #2400612. Round 2 and 3 locations TBD. | Clark, Floyd | 2029 | FALSE | The National Electric Vehicle Infrastructure Formula Program strategically deploys electric vehicle charging infrastructure and supports an interconnected network to facilitate data collection, access, and reliability. Eligible funding uses include acquisition and installation of electric vehicle charging infrastructure to serve as a catalyst for the deployment of such infrastructure and to connect it to a network to facilitate data collection, access, and reliability; proper operation and maintenance of electric vehicle charging infrastructure; data sharing about electric vehicle charging infrastructure to ensure the long-term success of investments. |  |  | 99650738 | 76576845 | PE | 2025 | 6669120 | 1667280 | 8336400 | NEVI | Active | TRUE
Indiana | 3215 | 2300274, 2400612 | INDOT | National Electric Vehicle Infrastructure (NEVI) | Electric vehicle charging infrastructure at various locations along Indiana interstates. Round 1 electric vehicle charging infrostructure at 4222 Charlestown Road, New Albany, IN 47150, and 1540 Veterans Parkway, Jeffersonville, IN 47130. DES #2400612. Round 2 and 3 locations TBD. | Clark, Floyd | 2029 | FALSE | The National Electric Vehicle Infrastructure Formula Program strategically deploys electric vehicle charging infrastructure and supports an interconnected network to facilitate data collection, access, and reliability. Eligible funding uses include acquisition and installation of electric vehicle charging infrastructure to serve as a catalyst for the deployment of such infrastructure and to connect it to a network to facilitate data collection, access, and reliability; proper operation and maintenance of electric vehicle charging infrastructure; data sharing about electric vehicle charging infrastructure to ensure the long-term success of investments. |  |  | 99650738 | 76576845 | CN | 2025 | 424590 | 106147 | 530737 | NEVI | Active | TRUE
Indiana | 3215 | 2300274, 2400612 | INDOT | National Electric Vehicle Infrastructure (NEVI) | Electric vehicle charging infrastructure at various locations along Indiana interstates. Round 1 electric vehicle charging infrostructure at 4222 Charlestown Road, New Albany, IN 47150, and 1540 Veterans Parkway, Jeffersonville, IN 47130. DES #2400612. Round 2 and 3 locations TBD. | Clark, Floyd | 2029 | FALSE | The National Electric Vehicle Infrastructure Formula Program strategically deploys electric vehicle charging infrastructure and supports an interconnected network to facilitate data collection, access, and reliability. Eligible funding uses include acquisition and installation of electric vehicle charging infrastructure to serve as a catalyst for the deployment of such infrastructure and to connect it to a network to facilitate data collection, access, and reliability; proper operation and maintenance of electric vehicle charging infrastructure; data sharing about electric vehicle charging infrastructure to ensure the long-term success of investments. |  |  | 99650738 | 76576845 | CN | 2026 | 15958569 | 3989642 | 19948211 | NEVI | Active | TRUE
Indiana | 3215 | 2300274, 2400612 | INDOT | National Electric Vehicle Infrastructure (NEVI) | Electric vehicle charging infrastructure at various locations along Indiana interstates. Round 1 electric vehicle charging infrostructure at 4222 Charlestown Road, New Albany, IN 47150, and 1540 Veterans Parkway, Jeffersonville, IN 47130. DES #2400612. Round 2 and 3 locations TBD. | Clark, Floyd | 2029 | FALSE | The National Electric Vehicle Infrastructure Formula Program strategically deploys electric vehicle charging infrastructure and supports an interconnected network to facilitate data collection, access, and reliability. Eligible funding uses include acquisition and installation of electric vehicle charging infrastructure to serve as a catalyst for the deployment of such infrastructure and to connect it to a network to facilitate data collection, access, and reliability; proper operation and maintenance of electric vehicle charging infrastructure; data sharing about electric vehicle charging infrastructure to ensure the long-term success of investments. |  |  | 99650738 | 76576845 | CN | 2027 | 21794319 | 5448580 | 27242899 | NEVI | Active | TRUE
Indiana | 3215 | 2300274, 2400612 | INDOT | National Electric Vehicle Infrastructure (NEVI) | Electric vehicle charging infrastructure at various locations along Indiana interstates. Round 1 electric vehicle charging infrostructure at 4222 Charlestown Road, New Albany, IN 47150, and 1540 Veterans Parkway, Jeffersonville, IN 47130. DES #2400612. Round 2 and 3 locations TBD. | Clark, Floyd | 2029 | FALSE | The National Electric Vehicle Infrastructure Formula Program strategically deploys electric vehicle charging infrastructure and supports an interconnected network to facilitate data collection, access, and reliability. Eligible funding uses include acquisition and installation of electric vehicle charging infrastructure to serve as a catalyst for the deployment of such infrastructure and to connect it to a network to facilitate data collection, access, and reliability; proper operation and maintenance of electric vehicle charging infrastructure; data sharing about electric vehicle charging infrastructure to ensure the long-term success of investments. |  |  | 99650738 | 76576845 | CN | 2028 | 15190289 | 3797572 | 18987861 | NEVI | Active | TRUE
Indiana | 3219 | 2201285 | Clark County | Clark County Bridge Inspection 2024-2027 | Clark County is required to have all bridges inspected every 24 months unless otherwise noted. Inspections are scheduled to be completed in March. | Clark | 2028 | FALSE | The FHWA requires all Indiana Counties to inspect bridges and prepare sufficiency ratings for all bridges. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 156504 | 146303 | PE | 2025 | 6986 | 1746 | 8732 | Bridge | Active | TRUE
Indiana | 3219 | 2201285 | Clark County | Clark County Bridge Inspection 2024-2027 | Clark County is required to have all bridges inspected every 24 months unless otherwise noted. Inspections are scheduled to be completed in March. | Clark | 2028 | FALSE | The FHWA requires all Indiana Counties to inspect bridges and prepare sufficiency ratings for all bridges. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 156504 | 146303 | PE | 2026 | 110430 | 27608 | 138038 | Bridge | Active | TRUE
Indiana | 3219 | 2201285 | Clark County | Clark County Bridge Inspection 2024-2027 | Clark County is required to have all bridges inspected every 24 months unless otherwise noted. Inspections are scheduled to be completed in March. | Clark | 2028 | FALSE | The FHWA requires all Indiana Counties to inspect bridges and prepare sufficiency ratings for all bridges. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 156504 | 146303 | PE | 2027 | 7626 | 1907 | 9533 | Bridge | Active | TRUE
Indiana | 3243 | 2101113 | INDOT | Camera/Communications/Detection/DMS Replacements in Southern Indiana ATMS Area - FY 25 | This is a non-let procurement of as-needed replacements or repairs to INDOT CCTV cameras, communications devices, or dynamic message signs in the Southern Indiana advanced traffic management system (ATMS) area for FY 25. These ITS/traffic management devices are located on or adjacent to the interstate/freeway system in Clark and Floyd counties. | Clark, Floyd | 2026 | FALSE | INDOT ITS/traffic management devices need repairs or replacements from time to time and this provides the funding for these as-needed actions. |  | 2678 - Roadway Operational Improvements - Indiana | 100000 | 100000 | CN | 2025 | 90000 | 10000 | 100000 | IM | Active | TRUE
Indiana | 3244 | 2201178 | INDOT | Camera/Communications/Detection/DMS Replacements in Southern Indiana ATMS Area - FY 26 | This is a non-let procurement of as-needed replacements or repairs to INDOT CCTV cameras, communications devices, or dynamic message signs in the Southern Indiana advanced traffic management system (ATMS) area for FY 26. These ITS/traffic management devices are located on or adjacent to the interstate/freeway system in Clark and Floyd counties. | Clark, Floyd | 2027 | FALSE | INDOT ITS/traffic management devices need repairs or replacements from time to time and this provides the funding for these as-needed actions. |  | 2678 - Roadway Operational Improvements - Indiana | 100000 | 100000 | CN | 2026 | 90000 | 10000 | 100000 | IM | Active | TRUE
Indiana | 3245 | 2201701 | INDOT | Seymour District CCTV Camera Lowering Arms & Pole Wiring Replacement - FY 26 | This is project adds or replaces INDOT CCTV camera lowering arms and replaces wiring in the poles for FY 26. These ITS/traffic management devices are located on or adjacent to the interstate/freeway system in Clark and Floyd counties. | Clark, Floyd | 2027 | FALSE | INDOT ITS/traffic management devices need repairs or replacements from time to time and this provides the funding for these as-needed actions. |  | 2678 - Roadway Operational Improvements - Indiana | 870000 | 870000 | PE | 2025 | 63000 | 7000 | 70000 | IM | Active | TRUE
Indiana | 3245 | 2201701 | INDOT | Seymour District CCTV Camera Lowering Arms & Pole Wiring Replacement - FY 26 | This is project adds or replaces INDOT CCTV camera lowering arms and replaces wiring in the poles for FY 26. These ITS/traffic management devices are located on or adjacent to the interstate/freeway system in Clark and Floyd counties. | Clark, Floyd | 2027 | FALSE | INDOT ITS/traffic management devices need repairs or replacements from time to time and this provides the funding for these as-needed actions. |  | 2678 - Roadway Operational Improvements - Indiana | 870000 | 870000 | CN | 2026 | 720000 | 80000 | 800000 | IM | Active | TRUE
Indiana | 3246 | 2300810 | INDOT | SR 62 Bridge Deck Overlay Over Fourteen Mile Creek | Bridge deck overlay on SR 62 bridge over Fourteen Mile Creek, 2.86 miles east of SR 3. | Clark | 2028 | FALSE | Repair a post missing from the north guardrail at the east joint and correct the deficiencies in the wearing surface, deck, and superstructure to help further protect the structure and extend the service life of the bridge. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 3149904 | 3149904 | ROW | 2027 | 8000 | 2000 | 10000 | NHPP | Active | TRUE
Indiana | 3246 | 2300810 | INDOT | SR 62 Bridge Deck Overlay Over Fourteen Mile Creek | Bridge deck overlay on SR 62 bridge over Fourteen Mile Creek, 2.86 miles east of SR 3. | Clark | 2028 | FALSE | Repair a post missing from the north guardrail at the east joint and correct the deficiencies in the wearing surface, deck, and superstructure to help further protect the structure and extend the service life of the bridge. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 3149904 | 3149904 | U | 2027 | 64000 | 16000 | 80000 | NHPP | Active | TRUE
Indiana | 3246 | 2300810 | INDOT | SR 62 Bridge Deck Overlay Over Fourteen Mile Creek | Bridge deck overlay on SR 62 bridge over Fourteen Mile Creek, 2.86 miles east of SR 3. | Clark | 2028 | FALSE | Repair a post missing from the north guardrail at the east joint and correct the deficiencies in the wearing surface, deck, and superstructure to help further protect the structure and extend the service life of the bridge. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 3149904 | 3149904 | CN | 2028 | 2176848 | 544212 | 2721060 | NHPP | Active | TRUE
Indiana | 3247 | 2300823 | INDOT | SR 160 Bridge Over Pigeon Roost Creek | Scour protection on SR 160 bridge over Pigeon Roost Creek, 03.44 miles west of I-65. | Clark | 2029 | FALSE | The project will correct the deficiencies with erosion and scour at the outlet (east end) of the structure. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 539275 | 539275 | PE | 2025 | 243074 | 60769 | 303843 | NHPP | Active | TRUE
Indiana | 3247 | 2300823 | INDOT | SR 160 Bridge Over Pigeon Roost Creek | Scour protection on SR 160 bridge over Pigeon Roost Creek, 03.44 miles west of I-65. | Clark | 2029 | FALSE | The project will correct the deficiencies with erosion and scour at the outlet (east end) of the structure. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 539275 | 539275 | ROW | 2026 | 9000 | 1000 | 10000 | NHPP | Active | TRUE
Indiana | 3247 | 2300823 | INDOT | SR 160 Bridge Over Pigeon Roost Creek | Scour protection on SR 160 bridge over Pigeon Roost Creek, 03.44 miles west of I-65. | Clark | 2029 | FALSE | The project will correct the deficiencies with erosion and scour at the outlet (east end) of the structure. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 539275 | 539275 | PE | 2026 | 33785 | 8446 | 42231 | NHPP | Active | TRUE
Indiana | 3247 | 2300823 | INDOT | SR 160 Bridge Over Pigeon Roost Creek | Scour protection on SR 160 bridge over Pigeon Roost Creek, 03.44 miles west of I-65. | Clark | 2029 | FALSE | The project will correct the deficiencies with erosion and scour at the outlet (east end) of the structure. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 539275 | 539275 | U | 2027 | 9000 | 1000 | 10000 | NHPP | Active | TRUE
Indiana | 3248 | 2300056 | INDOT | I-64 Small Structure Replacement - Valley View Creek | I-64 small structure replacement - Valley View Creek - 122.14 WB. | Floyd | 2025 | FALSE | Small structure replacement on I-64 in Floyd County. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 628161 | 628161 | CN | 2025 | 565344 | 62817 | 628161 | NHPP | Active | TRUE
Indiana | 3249 | 2300057 | INDOT | I-64 Small Structure Pipe Lining - Valley View Creek | I-64 small structure pipe lining - Valley View Creek, I-64-022-122.60. | Floyd | 2026 | FALSE | The purpose of this project is to correct the deficiencies in the structure in order to extend or reset the service life of the asset. The project need is based on the current condition of the structure elements. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 629964 | 629964 | CN | 2026 | 566968 | 62996 | 629964 | NHPP | Active | TRUE
Indiana | 3250 | 2300058 | INDOT | I-64 Small Structures & Drains Construction - Valley View Creek EB | I-64 small structure - Valley View Creek - I-64-022-121.71 EB. | Floyd | 2028 | FALSE | This project will improve the conditions of various culverts on I-64. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 62816 | 62816 | CN | 2026 | 56534 | 6282 | 62816 | NHPP | Active | TRUE
Indiana | 3251 | 2300059 | INDOT | I-64 Small Structure Pipe Lining EB | Small structure pipe lining on I-64, Valley View Creek - 121.95 EB. | Floyd | 2026 | FALSE | This project will improve the current condition of the structure and extend its service life. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 472473 | 472473 | CN | 2026 | 425226 | 47247 | 472473 | NHPP | Active | TRUE
Indiana | 3252 | 2300060 | INDOT | I-64 Small Structure Pipe Lining - Little Indian Creek | Small structure pipe lining on I-64, UNT to Little Indian Creek - 119.83. | Floyd | 2028 | FALSE | This project will improve the current condition of the structure and extend its service life. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 1364922 | 1364922 | CN | 2026 | 1228430 | 136492 | 1364922 | NHPP | Active | TRUE
Indiana | 3253 | 2301566 | INDOT | I-64 Small Structure Replacement | Small structure replacement on I-64, 1.96 miles east of US 150. | Floyd | 2028 | FALSE | Small structure replacement on I-64. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 2100000 | 2100000 | CN | 2026 | 1890000 | 210000 | 2100000 | NHPP | Active | TRUE
Indiana | 3255 | 2201590 | INDOT | SR 60 Small Structures and Drains Construction | Small structures and drains constructions on US 60 1.50 mile north of SR 311 for 4.52 miles. | Clark | 2026 | FALSE | This project will improve the conditions of the culvert on SR 60 from RF 55+88 - 60+35. |  | 2678 - Roadway Operational Improvements - Indiana | 759169 | 759169 | CN | 2025 | 585735 | 146434 | 732169 | STBG-ST | Active | TRUE
Indiana | 3256 | 2400032 | INDOT | Scenic Byway Corridor Along the Ohio River | This is a scenic byway project replacing old signs with new ones. This is in 13 counties along the Ohio River. This will be a total of $800,000 in CN dollars. | Clark, Floyd | 2025 | FALSE | This project is needed to replace old or damaged signs along the Ohio River. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 800000 | 800000 | CN | 2025 | 720000 | 80000 | 800000 | NHPP | Active | TRUE
Indiana | 3257 | 2300848 | INDOT | I-65 SB Bridge Over Brownstown Road | Bridge thin deck overlay on I-65 SB bridge over Brownstown Road, 02.03 miles north of SR 160. | Clark | 2028 | FALSE | The project need is based on the current condition of the structure elements and notable deficiencies in the wearing surface. This bridge was built in 2016 and has not received a wearing surface treatment to date. There are minor hairline cracks in the wearing surface that could benefit from additional protection through a preventive maintenance wearing surface treatment. This structure will be widened with upcoming ATL project and the new portion will need to have a polymeric overlay installed as well. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 375813 | 375813 | PE | 2025 | 140000 | 35000 | 175000 | STBG-ST | Active | TRUE
Indiana | 3257 | 2300848 | INDOT | I-65 SB Bridge Over Brownstown Road | Bridge thin deck overlay on I-65 SB bridge over Brownstown Road, 02.03 miles north of SR 160. | Clark | 2028 | FALSE | The project need is based on the current condition of the structure elements and notable deficiencies in the wearing surface. This bridge was built in 2016 and has not received a wearing surface treatment to date. There are minor hairline cracks in the wearing surface that could benefit from additional protection through a preventive maintenance wearing surface treatment. This structure will be widened with upcoming ATL project and the new portion will need to have a polymeric overlay installed as well. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 375813 | 375813 | CN | 2028 | 160650 | 40163 | 200813 | STBG-ST | Active | TRUE
Indiana | 3258 | 2300847 | INDOT | I-65 NB Over Brownstown Road | Bridge thin deck overlay on I-65 NB bridge over Brownstown Road, 02.03 miles north of SR 160. | Clark | 2028 | FALSE | "The project need is based on the current condition of the structure elements and notable deficiencies in the wearing surface. This bridge was built in 2016 and has not received a wearing surface treatment to date. There are minor hairline cracks in the wearing surface that could benefit from additional protection through a preventive maintenance wearing surface treatment. This structure will be widened with upcoming ATL project and the new portion will need to have a polymeric overlay installed as well. " |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 375813 | 375813 | PE | 2025 | 140000 | 35000 | 175000 | STBG-ST | Active | TRUE
Indiana | 3258 | 2300847 | INDOT | I-65 NB Over Brownstown Road | Bridge thin deck overlay on I-65 NB bridge over Brownstown Road, 02.03 miles north of SR 160. | Clark | 2028 | FALSE | "The project need is based on the current condition of the structure elements and notable deficiencies in the wearing surface. This bridge was built in 2016 and has not received a wearing surface treatment to date. There are minor hairline cracks in the wearing surface that could benefit from additional protection through a preventive maintenance wearing surface treatment. This structure will be widened with upcoming ATL project and the new portion will need to have a polymeric overlay installed as well. " |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 375813 | 375813 | CN | 2028 | 160650 | 40163 | 200813 | STBG-ST | Active | TRUE
Indiana | 3259 | 2300846 | INDOT | I-65 Hebron Church Road | Bridge thin deck overlay on I-65 Hebron Church Road bridge over I-65 NB/SB, 01.27 miles north of SR 160. | Clark | 2028 | FALSE | The project need is based on the current condition of the structure elements and notable deficiencies in the wearing surface. This bridge received a superstructure replacement in 2015 and has not received a wearing surface treatment to date. There are minor hairline cracks in the wearing surface that could benefit from additional protection through a preventive maintenance wearing surface treatment. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 189657 | 189657 | CN | 2028 | 170691 | 18966 | 189657 | STBG-ST | Active | TRUE
Indiana | 3260 | 2300845 | INDOT | I-65 Biggs Road | Bridge thin deck overlay on I-65 Biggs Road bridge over I-65, 02.51 miles south of SR 160. | Clark | 2028 | FALSE | The project need is based on the current condition of the structure elements and notable deficiencies in the wearing surface. This bridge received a superstructure replacement in 2015 and has not received a wearing surface treatment to date. There are minor hairline cracks in the wearing surface that could benefit from additional protection through a preventive maintenance wearing surface treatment. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 200813 | 200813 | CN | 2028 | 180732 | 20081 | 200813 | NHPP | Active | TRUE
Indiana | 3261 | 2300844 | INDOT | I-65 Ebenezer Church Road | Bridge thin deck overlay on I-65 Ebenezer Church Road bridge over I-65 NB/SB, 04.46 miles south of SR 160. | Clark | 2028 | FALSE | The project need is based on the current condition of the structure elements and notable deficiencies in the wearing surface. This bridge received a superstructure replacement in 2015 and has not received a wearing surface treatment to date. There are minor transverse and a few longitudinal cracks in the wearing surface that could benefit from additional protection through a preventive maintenance wearing surface treatment. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 200813 | 200813 | CN | 2028 | 180732 | 20081 | 200813 | NHPP | Active | TRUE
Indiana | 3262 | 2300988 | INDOT | I-65 Small Structure | Small structure paved invert on I-65 0.06 miles north of SR 311 at the intersection with the I-65 NB ramp. | Clark | 2028 | FALSE | "The purpose of this project is to correct the deficiencies in the structure to extend the service life of the small structure. The project need is based on the current condition of the structure elements. The culvert has several locations of complete section loss in flowline. There is also debris at the outlet end of pipe and is causing water to be held in pipe along with sediment. " |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 723944 | 723944 | PE | 2025 | 202500 | 22500 | 225000 | NHPP | Active | TRUE
Indiana | 3262 | 2300988 | INDOT | I-65 Small Structure | Small structure paved invert on I-65 0.06 miles north of SR 311 at the intersection with the I-65 NB ramp. | Clark | 2028 | FALSE | "The purpose of this project is to correct the deficiencies in the structure to extend the service life of the small structure. The project need is based on the current condition of the structure elements. The culvert has several locations of complete section loss in flowline. There is also debris at the outlet end of pipe and is causing water to be held in pipe along with sediment. " |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 723944 | 723944 | ROW | 2026 | 9000 | 1000 | 10000 | NHPP | Active | TRUE
Indiana | 3262 | 2300988 | INDOT | I-65 Small Structure | Small structure paved invert on I-65 0.06 miles north of SR 311 at the intersection with the I-65 NB ramp. | Clark | 2028 | FALSE | "The purpose of this project is to correct the deficiencies in the structure to extend the service life of the small structure. The project need is based on the current condition of the structure elements. The culvert has several locations of complete section loss in flowline. There is also debris at the outlet end of pipe and is causing water to be held in pipe along with sediment. " |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 723944 | 723944 | U | 2027 | 27000 | 3000 | 30000 | NHPP | Active | TRUE
Indiana | 3262 | 2300988 | INDOT | I-65 Small Structure | Small structure paved invert on I-65 0.06 miles north of SR 311 at the intersection with the I-65 NB ramp. | Clark | 2028 | FALSE | "The purpose of this project is to correct the deficiencies in the structure to extend the service life of the small structure. The project need is based on the current condition of the structure elements. The culvert has several locations of complete section loss in flowline. There is also debris at the outlet end of pipe and is causing water to be held in pipe along with sediment. " |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 723944 | 723944 | CN | 2028 | 413050 | 45894 | 458944 | NHPP | Active | TRUE
Indiana | 3263 | 2300986 | INDOT | I-65 Small Structure | Small structure pipe lining 5.66 miles north of SR 311 on I-65. | Clark | 2028 | FALSE | The purpose of this project is to correct the deficiencies in the structure to extend the service life of the small structure. The project need is based on the current condition of the structure elements. There is significant section loss, corrosion, and pitting throughout the invert of the structure. These perforations and section loss in the flow line could eventually lead to material being pulled from above and impact the roadway above through the presence of voids under or adjacent to the pavement. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 1827739 | 1827739 | PE | 2025 | 274723 | 30525 | 305248 | NHPP | Active | TRUE
Indiana | 3263 | 2300986 | INDOT | I-65 Small Structure | Small structure pipe lining 5.66 miles north of SR 311 on I-65. | Clark | 2028 | FALSE | The purpose of this project is to correct the deficiencies in the structure to extend the service life of the small structure. The project need is based on the current condition of the structure elements. There is significant section loss, corrosion, and pitting throughout the invert of the structure. These perforations and section loss in the flow line could eventually lead to material being pulled from above and impact the roadway above through the presence of voids under or adjacent to the pavement. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 1827739 | 1827739 | ROW | 2026 | 18000 | 2000 | 20000 | NHPP | Active | TRUE
Indiana | 3263 | 2300986 | INDOT | I-65 Small Structure | Small structure pipe lining 5.66 miles north of SR 311 on I-65. | Clark | 2028 | FALSE | The purpose of this project is to correct the deficiencies in the structure to extend the service life of the small structure. The project need is based on the current condition of the structure elements. There is significant section loss, corrosion, and pitting throughout the invert of the structure. These perforations and section loss in the flow line could eventually lead to material being pulled from above and impact the roadway above through the presence of voids under or adjacent to the pavement. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 1827739 | 1827739 | PE | 2026 | 95372 | 10597 | 105969 | NHPP | Active | TRUE
Indiana | 3263 | 2300986 | INDOT | I-65 Small Structure | Small structure pipe lining 5.66 miles north of SR 311 on I-65. | Clark | 2028 | FALSE | The purpose of this project is to correct the deficiencies in the structure to extend the service life of the small structure. The project need is based on the current condition of the structure elements. There is significant section loss, corrosion, and pitting throughout the invert of the structure. These perforations and section loss in the flow line could eventually lead to material being pulled from above and impact the roadway above through the presence of voids under or adjacent to the pavement. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 1827739 | 1827739 | U | 2027 | 9000 | 1000 | 10000 | NHPP | Active | TRUE
Indiana | 3263 | 2300986 | INDOT | I-65 Small Structure | Small structure pipe lining 5.66 miles north of SR 311 on I-65. | Clark | 2028 | FALSE | The purpose of this project is to correct the deficiencies in the structure to extend the service life of the small structure. The project need is based on the current condition of the structure elements. There is significant section loss, corrosion, and pitting throughout the invert of the structure. These perforations and section loss in the flow line could eventually lead to material being pulled from above and impact the roadway above through the presence of voids under or adjacent to the pavement. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 1827739 | 1827739 | CN | 2028 | 1247869 | 138653 | 1386522 | NHPP | Active | TRUE
Indiana | 3264 | 2301121 | INDOT | SR 111 HMA Overlay | HMA overlay, preventive maintenance on SR 111 from 0.92 miles south of I-64 (Corydon Pike) to 0.19 miles north of I-64 (State Street). | Floyd | 2030 | FALSE | The purpose of this project is to extend the life of the pavement by addressing functional and structural deficiencies. This investment must last until the next predicted project in the 20 year plan, which is estimated to be in 2042. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 3522400 | 3522400 | PE | 2025 | 400000 | 100000 | 500000 | STBG-ST | Active | TRUE
Indiana | 3264 | 2301121 | INDOT | SR 111 HMA Overlay | HMA overlay, preventive maintenance on SR 111 from 0.92 miles south of I-64 (Corydon Pike) to 0.19 miles north of I-64 (State Street). | Floyd | 2030 | FALSE | The purpose of this project is to extend the life of the pavement by addressing functional and structural deficiencies. This investment must last until the next predicted project in the 20 year plan, which is estimated to be in 2042. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 3522400 | 3522400 | ROW | 2027 | 32000 | 8000 | 40000 | STBG-ST | Active | TRUE
Indiana | 3264 | 2301121 | INDOT | SR 111 HMA Overlay | HMA overlay, preventive maintenance on SR 111 from 0.92 miles south of I-64 (Corydon Pike) to 0.19 miles north of I-64 (State Street). | Floyd | 2030 | FALSE | The purpose of this project is to extend the life of the pavement by addressing functional and structural deficiencies. This investment must last until the next predicted project in the 20 year plan, which is estimated to be in 2042. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 3522400 | 3522400 | U | 2028 | 40000 | 10000 | 50000 | STBG-ST | Active | TRUE
Indiana | 3264 | 2301121 | INDOT | SR 111 HMA Overlay | HMA overlay, preventive maintenance on SR 111 from 0.92 miles south of I-64 (Corydon Pike) to 0.19 miles north of I-64 (State Street). | Floyd | 2030 | FALSE | The purpose of this project is to extend the life of the pavement by addressing functional and structural deficiencies. This investment must last until the next predicted project in the 20 year plan, which is estimated to be in 2042. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 3522400 | 3522400 | RR | 2028 | 40000 | 10000 | 50000 | STBG-ST | Active | TRUE
Indiana | 3265 | 2400038 | INDOT | Various Locations of Pavement Patching (IDIQ) | Pavement patching in various locations throughout the Seymour District. | Clark, Floyd | 2025 | FALSE | An INDOT contract for projects that need patching work done but is not a part of INDOT's call log. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 1000000 | 1000000 | CN | 2025 | 900000 | 100000 | 1000000 | NHS | Active | TRUE
Indiana | 3266 | 2301127 | INDOT | I-265 Pavement Replacement | Pavement replacement on I-265 from 0.36 miles west of I-65 to I-65. This project will be constructed in FY 2028. | Clark | 2028 | FALSE | This section of I 265 is an urban interstate with 4 lanes approximately 12 ’ wide, inside shoulders approximately 4’ wide, and outside shoulders approximately 10' wide on average. This road section had a concrete pavement restoration project completed in 2019. The concrete slabs on the adjacent section to the East (PK 50103) are faulting and rocking in multiple locations, which is causing the pavement to rapidly deteriorate. Some patching has already been necessary on the Eastbound ramp to I65, and an emergency patching contract is scheduled for FY 2023 to help reduce the chances of this pavement failing before the pavement replacement project is completed. The purpose of this project is to reset the life of the failing pavement through replacement. The new pavement should be designed to last at least 12 years before a preventative maintenance treatment is needed. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 5078972 | 5078972 | ROW | 2026 | 18000 | 2000 | 20000 | NHS | Active | TRUE
Indiana | 3266 | 2301127 | INDOT | I-265 Pavement Replacement | Pavement replacement on I-265 from 0.36 miles west of I-65 to I-65. This project will be constructed in FY 2028. | Clark | 2028 | FALSE | This section of I 265 is an urban interstate with 4 lanes approximately 12 ’ wide, inside shoulders approximately 4’ wide, and outside shoulders approximately 10' wide on average. This road section had a concrete pavement restoration project completed in 2019. The concrete slabs on the adjacent section to the East (PK 50103) are faulting and rocking in multiple locations, which is causing the pavement to rapidly deteriorate. Some patching has already been necessary on the Eastbound ramp to I65, and an emergency patching contract is scheduled for FY 2023 to help reduce the chances of this pavement failing before the pavement replacement project is completed. The purpose of this project is to reset the life of the failing pavement through replacement. The new pavement should be designed to last at least 12 years before a preventative maintenance treatment is needed. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 5078972 | 5078972 | U | 2027 | 9000 | 1000 | 10000 | NHS | Active | TRUE
Indiana | 3266 | 2301127 | INDOT | I-265 Pavement Replacement | Pavement replacement on I-265 from 0.36 miles west of I-65 to I-65. This project will be constructed in FY 2028. | Clark | 2028 | FALSE | This section of I 265 is an urban interstate with 4 lanes approximately 12 ’ wide, inside shoulders approximately 4’ wide, and outside shoulders approximately 10' wide on average. This road section had a concrete pavement restoration project completed in 2019. The concrete slabs on the adjacent section to the East (PK 50103) are faulting and rocking in multiple locations, which is causing the pavement to rapidly deteriorate. Some patching has already been necessary on the Eastbound ramp to I65, and an emergency patching contract is scheduled for FY 2023 to help reduce the chances of this pavement failing before the pavement replacement project is completed. The purpose of this project is to reset the life of the failing pavement through replacement. The new pavement should be designed to last at least 12 years before a preventative maintenance treatment is needed. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 5078972 | 5078972 | CN | 2028 | 4544075 | 504897 | 5048972 | NHS | Active | TRUE
Indiana | 3267 | 2300912 | INDOT | I-265 WB Hamburg Pike | Bridge deck overlay on I-265 WB bridge over Hamburg Pike, 0.09 miles east of US 31. This project will be constructed in FY 2028. | Clark | 2028 | FALSE | The purpose of this project is to correct the deficiencies in the wearing surface and deck to help further protect the structure and extend the service life of the bridge. The project need is based on the current condition of the structure elements and notable deficiencies in the wearing surface, deck, joints, beam ends, and approach slabs. In Span A at Abutment 1: Beam #1 has a spall on the north side of the web at beam end. Beam #2 has cracking and delamination on the north side at bearing area and north side of web, along with a small spall. There are minor diagonal hairline cracks in a few of the beam ends at both abutments. There is minor cracking in curtain walls, and vertical cracks with efflorescence in both abutment backwalls. The west slope wall has a transverse crack across the top of wall and has settled approximately 2'' at the north end. There is minor cracking in interior crash walls. The bridge seat at Abutment #1 under Beam #3 and Beam #4 has cracking. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 1263356 | 1263356 | PE | 2025 | 247500 | 27500 | 275000 | NHPP | Active | TRUE
Indiana | 3267 | 2300912 | INDOT | I-265 WB Hamburg Pike | Bridge deck overlay on I-265 WB bridge over Hamburg Pike, 0.09 miles east of US 31. This project will be constructed in FY 2028. | Clark | 2028 | FALSE | The purpose of this project is to correct the deficiencies in the wearing surface and deck to help further protect the structure and extend the service life of the bridge. The project need is based on the current condition of the structure elements and notable deficiencies in the wearing surface, deck, joints, beam ends, and approach slabs. In Span A at Abutment 1: Beam #1 has a spall on the north side of the web at beam end. Beam #2 has cracking and delamination on the north side at bearing area and north side of web, along with a small spall. There are minor diagonal hairline cracks in a few of the beam ends at both abutments. There is minor cracking in curtain walls, and vertical cracks with efflorescence in both abutment backwalls. The west slope wall has a transverse crack across the top of wall and has settled approximately 2'' at the north end. There is minor cracking in interior crash walls. The bridge seat at Abutment #1 under Beam #3 and Beam #4 has cracking. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 1263356 | 1263356 | U | 2027 | 9000 | 1000 | 10000 | NHPP | Active | TRUE
Indiana | 3267 | 2300912 | INDOT | I-265 WB Hamburg Pike | Bridge deck overlay on I-265 WB bridge over Hamburg Pike, 0.09 miles east of US 31. This project will be constructed in FY 2028. | Clark | 2028 | FALSE | The purpose of this project is to correct the deficiencies in the wearing surface and deck to help further protect the structure and extend the service life of the bridge. The project need is based on the current condition of the structure elements and notable deficiencies in the wearing surface, deck, joints, beam ends, and approach slabs. In Span A at Abutment 1: Beam #1 has a spall on the north side of the web at beam end. Beam #2 has cracking and delamination on the north side at bearing area and north side of web, along with a small spall. There are minor diagonal hairline cracks in a few of the beam ends at both abutments. There is minor cracking in curtain walls, and vertical cracks with efflorescence in both abutment backwalls. The west slope wall has a transverse crack across the top of wall and has settled approximately 2'' at the north end. There is minor cracking in interior crash walls. The bridge seat at Abutment #1 under Beam #3 and Beam #4 has cracking. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 1263356 | 1263356 | CN | 2028 | 880520 | 97836 | 978356 | NHPP | Active | TRUE
Indiana | 3268 | 2300911 | INDOT | I-265 EB Hamburg Pike | Bridge deck overlay on I-265 EB bridge over Hamburg, 0.09 miles east of US 31. This project will be constructed in FY 2028. | Clark | 2028 | FALSE | The purpose of this project is to correct the deficiencies in the wearing surface and deck to help further protect the structure and extend the service life of the bridge. The project need is based on the current condition of the structure elements and notable deficiencies in the wearing surface, deck, joints, and approach slabs. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 1452356 | 1452356 | PE | 2025 | 247500 | 27500 | 275000 | NHPP | Active | TRUE
Indiana | 3268 | 2300911 | INDOT | I-265 EB Hamburg Pike | Bridge deck overlay on I-265 EB bridge over Hamburg, 0.09 miles east of US 31. This project will be constructed in FY 2028. | Clark | 2028 | FALSE | The purpose of this project is to correct the deficiencies in the wearing surface and deck to help further protect the structure and extend the service life of the bridge. The project need is based on the current condition of the structure elements and notable deficiencies in the wearing surface, deck, joints, and approach slabs. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 1452356 | 1452356 | U | 2027 | 9000 | 1000 | 10000 | NHPP | Active | TRUE
Indiana | 3268 | 2300911 | INDOT | I-265 EB Hamburg Pike | Bridge deck overlay on I-265 EB bridge over Hamburg, 0.09 miles east of US 31. This project will be constructed in FY 2028. | Clark | 2028 | FALSE | The purpose of this project is to correct the deficiencies in the wearing surface and deck to help further protect the structure and extend the service life of the bridge. The project need is based on the current condition of the structure elements and notable deficiencies in the wearing surface, deck, joints, and approach slabs. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 1452356 | 1452356 | CN | 2028 | 1050620 | 116736 | 1167356 | NHPP | Active | TRUE
Indiana | 3269 | 2300914 | INDOT | I-265 WB Lick Run | Bridge deck overlay on I-265 WB bridge over Lick Run, 0.23 miles east of US 31. This will be constructed in FY 2028. | Clark | 2029 | FALSE | The purpose of this project is to correct the deficiencies in the wearing surface and deck to help further protect the structure and extend the service life of the bridge. The project need is based on the current condition of the structure elements and notable deficiencies in the bearing surface, deck, joints, beam ends, and approach slabs. Beam #7 in Span A has one small spall at the south west end of beam. There are spalls in Beam 7 in Span A. The beam ends at Abutment 1 have delamination and minor cracking. There are small spalls on Beam 2, 4, and 5 at Abutment 1. There are spread footings, NO piles, set in rock, riprap. Minor cracking with efflorescence in both backwalls. Minor cracks, delamination, and staining are present in the abutments and bridge seats. This bridge has been determined to be scour critical due to the footings being constructed on erodible shale. This bridge is part of the SR-265 Corridor for FY2028. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 1519062 | 1519062 | PE | 2025 | 220000 | 55000 | 275000 | STBG-ST | Active | TRUE
Indiana | 3269 | 2300914 | INDOT | I-265 WB Lick Run | Bridge deck overlay on I-265 WB bridge over Lick Run, 0.23 miles east of US 31. This will be constructed in FY 2028. | Clark | 2029 | FALSE | The purpose of this project is to correct the deficiencies in the wearing surface and deck to help further protect the structure and extend the service life of the bridge. The project need is based on the current condition of the structure elements and notable deficiencies in the bearing surface, deck, joints, beam ends, and approach slabs. Beam #7 in Span A has one small spall at the south west end of beam. There are spalls in Beam 7 in Span A. The beam ends at Abutment 1 have delamination and minor cracking. There are small spalls on Beam 2, 4, and 5 at Abutment 1. There are spread footings, NO piles, set in rock, riprap. Minor cracking with efflorescence in both backwalls. Minor cracks, delamination, and staining are present in the abutments and bridge seats. This bridge has been determined to be scour critical due to the footings being constructed on erodible shale. This bridge is part of the SR-265 Corridor for FY2028. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 1519062 | 1519062 | U | 2027 | 9000 | 1000 | 10000 | NHPP | Active | TRUE
Indiana | 3269 | 2300914 | INDOT | I-265 WB Lick Run | Bridge deck overlay on I-265 WB bridge over Lick Run, 0.23 miles east of US 31. This will be constructed in FY 2028. | Clark | 2029 | FALSE | The purpose of this project is to correct the deficiencies in the wearing surface and deck to help further protect the structure and extend the service life of the bridge. The project need is based on the current condition of the structure elements and notable deficiencies in the bearing surface, deck, joints, beam ends, and approach slabs. Beam #7 in Span A has one small spall at the south west end of beam. There are spalls in Beam 7 in Span A. The beam ends at Abutment 1 have delamination and minor cracking. There are small spalls on Beam 2, 4, and 5 at Abutment 1. There are spread footings, NO piles, set in rock, riprap. Minor cracking with efflorescence in both backwalls. Minor cracks, delamination, and staining are present in the abutments and bridge seats. This bridge has been determined to be scour critical due to the footings being constructed on erodible shale. This bridge is part of the SR-265 Corridor for FY2028. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 1519062 | 1519062 | CN | 2028 | 1110656 | 123406 | 1234062 | NHPP | Active | TRUE
Indiana | 3270 | 2300913 | INDOT | I-265 EB Lick Run | Bridge deck overlay on I-265 EB bridge over Lick Run, 0.23 miles east of US 31. This project will be constructed in FY 2028. | Clark | 2028 | FALSE | The purpose of this project is to correct the deficiencies in the wearing surface and deck to help further protect the structure and extend the service life of the bridge. The project need is based on the current condition of the structure elements and notable deficiencies in the wearing surface, deck, joints, beam ends, and approach slabs. There is one small spall in Beam #7 span C at the south east end. It appears to have happened during placement of beam during construction. There are minor cracks in a few curtain walls, and minor diagonal hairline cracks in a few of the beam ends at both abutments. Beam end 1 has a diagonal crack and a small spall at Abutment 1. This bridge has spread footings, NO piles. The footings are set in rock with riprap. There are minor cracks with efflorescence in the back wall. This bridge has been determined to be Scour Critical due to the footings being constructed in erodible shale. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 1519062 | 1519062 | U | 2025 | 9000 | 1000 | 10000 | NHPP | Active | TRUE
Indiana | 3270 | 2300913 | INDOT | I-265 EB Lick Run | Bridge deck overlay on I-265 EB bridge over Lick Run, 0.23 miles east of US 31. This project will be constructed in FY 2028. | Clark | 2028 | FALSE | The purpose of this project is to correct the deficiencies in the wearing surface and deck to help further protect the structure and extend the service life of the bridge. The project need is based on the current condition of the structure elements and notable deficiencies in the wearing surface, deck, joints, beam ends, and approach slabs. There is one small spall in Beam #7 span C at the south east end. It appears to have happened during placement of beam during construction. There are minor cracks in a few curtain walls, and minor diagonal hairline cracks in a few of the beam ends at both abutments. Beam end 1 has a diagonal crack and a small spall at Abutment 1. This bridge has spread footings, NO piles. The footings are set in rock with riprap. There are minor cracks with efflorescence in the back wall. This bridge has been determined to be Scour Critical due to the footings being constructed in erodible shale. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 1519062 | 1519062 | PE | 2025 | 247500 | 27500 | 275000 | NHPP | Active | TRUE
Indiana | 3270 | 2300913 | INDOT | I-265 EB Lick Run | Bridge deck overlay on I-265 EB bridge over Lick Run, 0.23 miles east of US 31. This project will be constructed in FY 2028. | Clark | 2028 | FALSE | The purpose of this project is to correct the deficiencies in the wearing surface and deck to help further protect the structure and extend the service life of the bridge. The project need is based on the current condition of the structure elements and notable deficiencies in the wearing surface, deck, joints, beam ends, and approach slabs. There is one small spall in Beam #7 span C at the south east end. It appears to have happened during placement of beam during construction. There are minor cracks in a few curtain walls, and minor diagonal hairline cracks in a few of the beam ends at both abutments. Beam end 1 has a diagonal crack and a small spall at Abutment 1. This bridge has spread footings, NO piles. The footings are set in rock with riprap. There are minor cracks with efflorescence in the back wall. This bridge has been determined to be Scour Critical due to the footings being constructed in erodible shale. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 1519062 | 1519062 | CN | 2028 | 1110656 | 123406 | 1234062 | NHPP | Active | TRUE
Indiana | 3271 | 2300910 | INDOT | I-265 WB Conrail RR | Bridge deck overlay on I-265 WB bridge over US 31, Conrail RR, 0.39 miles east of I-65. This will be constructed in FY 2028. | Clark | 2028 | FALSE | The purpose of this project is to correct the deficiencies in the wearing surface and deck to help further protect the structure and extend the service life of the bridge. The project need is based on the current condition of the structure elements and notable deficiencies in the wearing surface, deck, joints, and approach slabs. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 1773063 | 1773063 | PE | 2025 | 270000 | 30000 | 300000 | NHPP | Active | TRUE
Indiana | 3271 | 2300910 | INDOT | I-265 WB Conrail RR | Bridge deck overlay on I-265 WB bridge over US 31, Conrail RR, 0.39 miles east of I-65. This will be constructed in FY 2028. | Clark | 2028 | FALSE | The purpose of this project is to correct the deficiencies in the wearing surface and deck to help further protect the structure and extend the service life of the bridge. The project need is based on the current condition of the structure elements and notable deficiencies in the wearing surface, deck, joints, and approach slabs. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 1773063 | 1773063 | U | 2027 | 27000 | 3000 | 30000 | NHPP | Active | TRUE
Indiana | 3271 | 2300910 | INDOT | I-265 WB Conrail RR | Bridge deck overlay on I-265 WB bridge over US 31, Conrail RR, 0.39 miles east of I-65. This will be constructed in FY 2028. | Clark | 2028 | FALSE | The purpose of this project is to correct the deficiencies in the wearing surface and deck to help further protect the structure and extend the service life of the bridge. The project need is based on the current condition of the structure elements and notable deficiencies in the wearing surface, deck, joints, and approach slabs. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 1773063 | 1773063 | RR | 2027 | 18000 | 2000 | 20000 | NHPP | Active | TRUE
Indiana | 3271 | 2300910 | INDOT | I-265 WB Conrail RR | Bridge deck overlay on I-265 WB bridge over US 31, Conrail RR, 0.39 miles east of I-65. This will be constructed in FY 2028. | Clark | 2028 | FALSE | The purpose of this project is to correct the deficiencies in the wearing surface and deck to help further protect the structure and extend the service life of the bridge. The project need is based on the current condition of the structure elements and notable deficiencies in the wearing surface, deck, joints, and approach slabs. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 1773063 | 1773063 | CN | 2028 | 1280757 | 142306 | 1423063 | NHPP | Active | TRUE
Indiana | 3272 | 2300909 | INDOT | I-265 EB Conrail RR | Bridge deck overlay on I-265 EB bridge over US 31, Conrail RR, 0.39 miles east of I-65. This will be constructed in FY 2028. | Clark | 2028 | FALSE | The purpose of this project is to correct the deficiencies in the wearing surface and deck to help further protect the structure and extend the service life of the bridge. The project need is based on the current condition of the structure elements and notable deficiencies in the wearing surface, deck, joints, and approach slabs. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 1773063 | 1773063 | PE | 2025 | 270000 | 30000 | 300000 | NHPP | Active | TRUE
Indiana | 3272 | 2300909 | INDOT | I-265 EB Conrail RR | Bridge deck overlay on I-265 EB bridge over US 31, Conrail RR, 0.39 miles east of I-65. This will be constructed in FY 2028. | Clark | 2028 | FALSE | The purpose of this project is to correct the deficiencies in the wearing surface and deck to help further protect the structure and extend the service life of the bridge. The project need is based on the current condition of the structure elements and notable deficiencies in the wearing surface, deck, joints, and approach slabs. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 1773063 | 1773063 | U | 2027 | 27000 | 3000 | 30000 | NHPP | Active | TRUE
Indiana | 3272 | 2300909 | INDOT | I-265 EB Conrail RR | Bridge deck overlay on I-265 EB bridge over US 31, Conrail RR, 0.39 miles east of I-65. This will be constructed in FY 2028. | Clark | 2028 | FALSE | The purpose of this project is to correct the deficiencies in the wearing surface and deck to help further protect the structure and extend the service life of the bridge. The project need is based on the current condition of the structure elements and notable deficiencies in the wearing surface, deck, joints, and approach slabs. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 1773063 | 1773063 | RR | 2027 | 18000 | 2000 | 20000 | NHPP | Active | TRUE
Indiana | 3272 | 2300909 | INDOT | I-265 EB Conrail RR | Bridge deck overlay on I-265 EB bridge over US 31, Conrail RR, 0.39 miles east of I-65. This will be constructed in FY 2028. | Clark | 2028 | FALSE | The purpose of this project is to correct the deficiencies in the wearing surface and deck to help further protect the structure and extend the service life of the bridge. The project need is based on the current condition of the structure elements and notable deficiencies in the wearing surface, deck, joints, and approach slabs. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 1773063 | 1773063 | CN | 2028 | 1280757 | 142306 | 1423063 | NHPP | Active | TRUE
Indiana | 3273 | 2300906 | INDOT | I-265 WB Charlestown Pike | Bridge deck overlay on I-265 WB bridge over Conrail RR, Charlestown Pike, 1.51 miles east of US 31. | Clark | 2028 | FALSE | The purpose of this project is to correct the deficiencies in the wearing surface and deck to help further protect the structure and extend the service life of the bridge and to improve the steel beam paint coatings to extend the service life of the steel beams. The project need is based on the current condition of the structure elements and notable deficiencies in the wearing surface, deck, joints, beams, and approach slabs. Transverse cracks are in the east approach slab, also two shallow pop outs are present in the slow lane west slab. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 2323888 | 2313888 | PE | 2025 | 337500 | 37500 | 375000 | NHPP | Active | TRUE
Indiana | 3273 | 2300906 | INDOT | I-265 WB Charlestown Pike | Bridge deck overlay on I-265 WB bridge over Conrail RR, Charlestown Pike, 1.51 miles east of US 31. | Clark | 2028 | FALSE | The purpose of this project is to correct the deficiencies in the wearing surface and deck to help further protect the structure and extend the service life of the bridge and to improve the steel beam paint coatings to extend the service life of the steel beams. The project need is based on the current condition of the structure elements and notable deficiencies in the wearing surface, deck, joints, beams, and approach slabs. Transverse cracks are in the east approach slab, also two shallow pop outs are present in the slow lane west slab. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 2323888 | 2313888 | U | 2027 | 45000 | 5000 | 50000 | NHPP | Active | TRUE
Indiana | 3273 | 2300906 | INDOT | I-265 WB Charlestown Pike | Bridge deck overlay on I-265 WB bridge over Conrail RR, Charlestown Pike, 1.51 miles east of US 31. | Clark | 2028 | FALSE | The purpose of this project is to correct the deficiencies in the wearing surface and deck to help further protect the structure and extend the service life of the bridge and to improve the steel beam paint coatings to extend the service life of the steel beams. The project need is based on the current condition of the structure elements and notable deficiencies in the wearing surface, deck, joints, beams, and approach slabs. Transverse cracks are in the east approach slab, also two shallow pop outs are present in the slow lane west slab. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 2323888 | 2313888 | RR | 2027 | 9000 | 1000 | 10000 | NHPP | Active | TRUE
Indiana | 3273 | 2300906 | INDOT | I-265 WB Charlestown Pike | Bridge deck overlay on I-265 WB bridge over Conrail RR, Charlestown Pike, 1.51 miles east of US 31. | Clark | 2028 | FALSE | The purpose of this project is to correct the deficiencies in the wearing surface and deck to help further protect the structure and extend the service life of the bridge and to improve the steel beam paint coatings to extend the service life of the steel beams. The project need is based on the current condition of the structure elements and notable deficiencies in the wearing surface, deck, joints, beams, and approach slabs. Transverse cracks are in the east approach slab, also two shallow pop outs are present in the slow lane west slab. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 2323888 | 2313888 | CN | 2028 | 1690999 | 187889 | 1878888 | NHPP | Active | TRUE
Indiana | 3274 | 2300905 | INDOT | I-265 EB Charlestown Pike | Bridge deck overlay on I-265 EB bridge over Conrail Railroad, Charlestown Pike, 1.51 miles east of US 31. This will be constructed in FY 2028. | Clark | 2028 | FALSE | The purpose of this project is to correct the deficiencies in the wearing surface and deck to help further protect the structure and extend the service life of the bridge and to improve the steel beam paint coatings to extend the service life of the steel beams. The project need is based on the current condition of the structure elements and notable deficiencies in the wearing surface, deck, joints, beams, and approach slabs. The west approach slab center lane has been paved over. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 2724124 | 2729124 | PE | 2025 | 337500 | 37500 | 375000 | NHPP | Active | TRUE
Indiana | 3274 | 2300905 | INDOT | I-265 EB Charlestown Pike | Bridge deck overlay on I-265 EB bridge over Conrail Railroad, Charlestown Pike, 1.51 miles east of US 31. This will be constructed in FY 2028. | Clark | 2028 | FALSE | The purpose of this project is to correct the deficiencies in the wearing surface and deck to help further protect the structure and extend the service life of the bridge and to improve the steel beam paint coatings to extend the service life of the steel beams. The project need is based on the current condition of the structure elements and notable deficiencies in the wearing surface, deck, joints, beams, and approach slabs. The west approach slab center lane has been paved over. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 2724124 | 2729124 | RR | 2027 | 45000 | 5000 | 50000 | NHPP | Active | TRUE
Indiana | 3274 | 2300905 | INDOT | I-265 EB Charlestown Pike | Bridge deck overlay on I-265 EB bridge over Conrail Railroad, Charlestown Pike, 1.51 miles east of US 31. This will be constructed in FY 2028. | Clark | 2028 | FALSE | The purpose of this project is to correct the deficiencies in the wearing surface and deck to help further protect the structure and extend the service life of the bridge and to improve the steel beam paint coatings to extend the service life of the steel beams. The project need is based on the current condition of the structure elements and notable deficiencies in the wearing surface, deck, joints, beams, and approach slabs. The west approach slab center lane has been paved over. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 2724124 | 2729124 | U | 2027 | 18000 | 7000 | 25000 | NHPP | Active | TRUE
Indiana | 3274 | 2300905 | INDOT | I-265 EB Charlestown Pike | Bridge deck overlay on I-265 EB bridge over Conrail Railroad, Charlestown Pike, 1.51 miles east of US 31. This will be constructed in FY 2028. | Clark | 2028 | FALSE | The purpose of this project is to correct the deficiencies in the wearing surface and deck to help further protect the structure and extend the service life of the bridge and to improve the steel beam paint coatings to extend the service life of the steel beams. The project need is based on the current condition of the structure elements and notable deficiencies in the wearing surface, deck, joints, beams, and approach slabs. The west approach slab center lane has been paved over. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 2724124 | 2729124 | CN | 2028 | 2051212 | 227912 | 2279124 | NHPP | Active | TRUE
Indiana | 3275 | 2300904 | INDOT | I-265 WB Coopers Lane | Bridge deck overlay on I-265 WB bridge over Coopers Lane, 0.28 miles east of I-65. This project will be constructed in FY 2028. | Clark | 2028 | FALSE | The purpose of this project is to correct the deficiencies in the wearing surface and deck to help further protect the structure and extend the service life of the bridge and to improve the steel beam paint coatings to extend the service life of the steel beams. The project need is based on the current condition of the structure elements and notable deficiencies in the wearing surface, deck, joints, beams, and approach slabs. There are longitudinal and transverse cracks in both approach slabs, and there is map cracking at the north side of the east joint. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 2202770 | 2202770 | PE | 2025 | 292500 | 32500 | 325000 | NHPP | Active | TRUE
Indiana | 3275 | 2300904 | INDOT | I-265 WB Coopers Lane | Bridge deck overlay on I-265 WB bridge over Coopers Lane, 0.28 miles east of I-65. This project will be constructed in FY 2028. | Clark | 2028 | FALSE | The purpose of this project is to correct the deficiencies in the wearing surface and deck to help further protect the structure and extend the service life of the bridge and to improve the steel beam paint coatings to extend the service life of the steel beams. The project need is based on the current condition of the structure elements and notable deficiencies in the wearing surface, deck, joints, beams, and approach slabs. There are longitudinal and transverse cracks in both approach slabs, and there is map cracking at the north side of the east joint. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 2202770 | 2202770 | U | 2027 | 9000 | 1000 | 10000 | NHPP | Active | TRUE
Indiana | 3275 | 2300904 | INDOT | I-265 WB Coopers Lane | Bridge deck overlay on I-265 WB bridge over Coopers Lane, 0.28 miles east of I-65. This project will be constructed in FY 2028. | Clark | 2028 | FALSE | The purpose of this project is to correct the deficiencies in the wearing surface and deck to help further protect the structure and extend the service life of the bridge and to improve the steel beam paint coatings to extend the service life of the steel beams. The project need is based on the current condition of the structure elements and notable deficiencies in the wearing surface, deck, joints, beams, and approach slabs. There are longitudinal and transverse cracks in both approach slabs, and there is map cracking at the north side of the east joint. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 2202770 | 2202770 | CN | 2028 | 1680993 | 186777 | 1867770 | NHPP | Active | TRUE
Indiana | 3276 | 2300903 | INDOT | I-265 EB Coopers Lane | Bridge deck overlay on I-265 EB bridge over Coopers Lane, 0.28 miles east of I-65. This will be constructed in FY 2028. | Clark | 2028 | FALSE | The purpose of this project is to correct the deficiencies in the wearing surface and deck to help further protect the structure and extend the service life of the bridge and to improve the steel beam paint coatings to extend the service life of the steel beams. The project need is based on the current condition of the structure elements and notable deficiencies in the wearing surface, deck, joints, beams, and approach slabs. Transverse cracks are present in both approach slabs. The west approach slab has two patches, the east approach has one patch. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 2202770 | 2202770 | PE | 2025 | 292500 | 32500 | 325000 | NHPP | Active | TRUE
Indiana | 3276 | 2300903 | INDOT | I-265 EB Coopers Lane | Bridge deck overlay on I-265 EB bridge over Coopers Lane, 0.28 miles east of I-65. This will be constructed in FY 2028. | Clark | 2028 | FALSE | The purpose of this project is to correct the deficiencies in the wearing surface and deck to help further protect the structure and extend the service life of the bridge and to improve the steel beam paint coatings to extend the service life of the steel beams. The project need is based on the current condition of the structure elements and notable deficiencies in the wearing surface, deck, joints, beams, and approach slabs. Transverse cracks are present in both approach slabs. The west approach slab has two patches, the east approach has one patch. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 2202770 | 2202770 | U | 2027 | 9000 | 1000 | 10000 | NHPP | Active | TRUE
Indiana | 3276 | 2300903 | INDOT | I-265 EB Coopers Lane | Bridge deck overlay on I-265 EB bridge over Coopers Lane, 0.28 miles east of I-65. This will be constructed in FY 2028. | Clark | 2028 | FALSE | The purpose of this project is to correct the deficiencies in the wearing surface and deck to help further protect the structure and extend the service life of the bridge and to improve the steel beam paint coatings to extend the service life of the steel beams. The project need is based on the current condition of the structure elements and notable deficiencies in the wearing surface, deck, joints, beams, and approach slabs. Transverse cracks are present in both approach slabs. The west approach slab has two patches, the east approach has one patch. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 2202770 | 2202770 | CN | 2028 | 1680993 | 186777 | 1867770 | NHPP | Active | TRUE
Indiana | 3277 | 2300902 | INDOT | I-265 | Bridge deck overlay on I-265 WB bridge over I-265 ramp SW-D to I-65, 0.13 miles east of I-65. This will be constructed in FY 2028. | Clark | 2028 | FALSE | The purpose of this project is to correct the deficiencies in the wearing surface and deck to help further protect the structure and extend the service life of the bridge. The project need is based on the current condition of the structure elements and notable deficiencies in the wearing surface, deck, joints, beam ends, and approach slabs. There is diagonal cracking in the ends of the beams at the abutments. These cracks are typical for precast concrete I-beams from the time the bridge was built. There are minor cracks and spalls in the abutments. Overall the bridge is in good to satisfactory condition. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 1174314 | 1174314 | PE | 2025 | 247500 | 27500 | 275000 | NHPP | Active | TRUE
Indiana | 3277 | 2300902 | INDOT | I-265 | Bridge deck overlay on I-265 WB bridge over I-265 ramp SW-D to I-65, 0.13 miles east of I-65. This will be constructed in FY 2028. | Clark | 2028 | FALSE | The purpose of this project is to correct the deficiencies in the wearing surface and deck to help further protect the structure and extend the service life of the bridge. The project need is based on the current condition of the structure elements and notable deficiencies in the wearing surface, deck, joints, beam ends, and approach slabs. There is diagonal cracking in the ends of the beams at the abutments. These cracks are typical for precast concrete I-beams from the time the bridge was built. There are minor cracks and spalls in the abutments. Overall the bridge is in good to satisfactory condition. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 1174314 | 1174314 | U | 2027 | 9000 | 1000 | 10000 | NHPP | Active | TRUE
Indiana | 3277 | 2300902 | INDOT | I-265 | Bridge deck overlay on I-265 WB bridge over I-265 ramp SW-D to I-65, 0.13 miles east of I-65. This will be constructed in FY 2028. | Clark | 2028 | FALSE | The purpose of this project is to correct the deficiencies in the wearing surface and deck to help further protect the structure and extend the service life of the bridge. The project need is based on the current condition of the structure elements and notable deficiencies in the wearing surface, deck, joints, beam ends, and approach slabs. There is diagonal cracking in the ends of the beams at the abutments. These cracks are typical for precast concrete I-beams from the time the bridge was built. There are minor cracks and spalls in the abutments. Overall the bridge is in good to satisfactory condition. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 1174314 | 1174314 | CN | 2028 | 800473 | 88841 | 889314 | NHPP | Active | TRUE
Indiana | 3278 | 2300901 | INDOT | I-265 | Bridge deck overlay on I-265 EB bridge over I-265 ramp SW-D TO I-65, 0.13 miles east of I-65. This will be constructed in FY 2028. | Clark | 2028 | FALSE | The purpose of this project is to correct the deficiencies in the wearing surface and deck to help further protect the structure and extend the service life of the bridge. The project need is based on the current condition of the structure elements and notable deficiencies in the wearing surface, deck, joints, beam ends, and approach slabs. There is a longitudinal cracking and one pop-out in the west approach slab. The east approach has had a new approach slab poured for the lanes carrying traffic. There are minor diagonal cracks in the beams at the abutments. These cracks are typical of precast I-beams of the time that the bridge was built. Overall the bridge is in good to satisfactory condition. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 1374533 | 1374533 | PE | 2025 | 247500 | 27500 | 275000 | NHPP | Active | TRUE
Indiana | 3278 | 2300901 | INDOT | I-265 | Bridge deck overlay on I-265 EB bridge over I-265 ramp SW-D TO I-65, 0.13 miles east of I-65. This will be constructed in FY 2028. | Clark | 2028 | FALSE | The purpose of this project is to correct the deficiencies in the wearing surface and deck to help further protect the structure and extend the service life of the bridge. The project need is based on the current condition of the structure elements and notable deficiencies in the wearing surface, deck, joints, beam ends, and approach slabs. There is a longitudinal cracking and one pop-out in the west approach slab. The east approach has had a new approach slab poured for the lanes carrying traffic. There are minor diagonal cracks in the beams at the abutments. These cracks are typical of precast I-beams of the time that the bridge was built. Overall the bridge is in good to satisfactory condition. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 1374533 | 1374533 | U | 2027 | 9000 | 1000 | 10000 | NHPP | Active | TRUE
Indiana | 3278 | 2300901 | INDOT | I-265 | Bridge deck overlay on I-265 EB bridge over I-265 ramp SW-D TO I-65, 0.13 miles east of I-65. This will be constructed in FY 2028. | Clark | 2028 | FALSE | The purpose of this project is to correct the deficiencies in the wearing surface and deck to help further protect the structure and extend the service life of the bridge. The project need is based on the current condition of the structure elements and notable deficiencies in the wearing surface, deck, joints, beam ends, and approach slabs. There is a longitudinal cracking and one pop-out in the west approach slab. The east approach has had a new approach slab poured for the lanes carrying traffic. There are minor diagonal cracks in the beams at the abutments. These cracks are typical of precast I-beams of the time that the bridge was built. Overall the bridge is in good to satisfactory condition. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 1374533 | 1374533 | CN | 2028 | 980580 | 108953 | 1089533 | NHPP | Active | TRUE
Indiana | 3279 | 2300900 | INDOT | I-265 WB Bridge Over I-65 | Bridge deck overlay on I-265 WB bridge over I-65 NB/SB, 2.50 miles east of SR 311. This will be constructed in FY 2028. | Clark | 2028 | FALSE | The purpose of this project is to correct the deficiencies in the wearing surface and deck to help further protect the structure and extend the service life of the bridge. The project need is based on the current condition of the structure elements and notable deficiencies in the wearing surface, deck, joints, beam ends, and approach slabs. There are vertical and horizontal cracks on both abutments with several delaminated areas. Moderate cracking with efflorescence is in the west backwall. Minor scaling in column #1 at pier #2. Bent #3 seat has some minor cracking and delamination. Minor cracking in both bent caps. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 1619121 | 1619121 | PE | 2025 | 247500 | 27500 | 275000 | NHPP | Active | TRUE
Indiana | 3279 | 2300900 | INDOT | I-265 WB Bridge Over I-65 | Bridge deck overlay on I-265 WB bridge over I-65 NB/SB, 2.50 miles east of SR 311. This will be constructed in FY 2028. | Clark | 2028 | FALSE | The purpose of this project is to correct the deficiencies in the wearing surface and deck to help further protect the structure and extend the service life of the bridge. The project need is based on the current condition of the structure elements and notable deficiencies in the wearing surface, deck, joints, beam ends, and approach slabs. There are vertical and horizontal cracks on both abutments with several delaminated areas. Moderate cracking with efflorescence is in the west backwall. Minor scaling in column #1 at pier #2. Bent #3 seat has some minor cracking and delamination. Minor cracking in both bent caps. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 1619121 | 1619121 | U | 2027 | 9000 | 1000 | 10000 | NHPP | Active | TRUE
Indiana | 3279 | 2300900 | INDOT | I-265 WB Bridge Over I-65 | Bridge deck overlay on I-265 WB bridge over I-65 NB/SB, 2.50 miles east of SR 311. This will be constructed in FY 2028. | Clark | 2028 | FALSE | The purpose of this project is to correct the deficiencies in the wearing surface and deck to help further protect the structure and extend the service life of the bridge. The project need is based on the current condition of the structure elements and notable deficiencies in the wearing surface, deck, joints, beam ends, and approach slabs. There are vertical and horizontal cracks on both abutments with several delaminated areas. Moderate cracking with efflorescence is in the west backwall. Minor scaling in column #1 at pier #2. Bent #3 seat has some minor cracking and delamination. Minor cracking in both bent caps. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 1619121 | 1619121 | CN | 2028 | 1200709 | 133412 | 1334121 | NHPP | Active | TRUE
Indiana | 3280 | 2300899 | INDOT | I-265 EB Bridge Over I-65 | Bridge deck overlay on I-265 EB bridge over I-65 NB/SB, 2.50 miles east of SR 311. This will be constructed in FY 2028. | Clark | 2028 | FALSE | The purpose of this project is to correct the deficiencies in the wearing surface and deck to help further protect the structure and extend the service life of the bridge. The project need is based on the current condition of the structure elements and notable deficiencies in the wearing surface, deck, joints, beam ends, and approach slabs. Vertical and horizontal cracking in both abutment bent caps. Pier 2 column 1 has exposed rebar that appears to be set too close to surface. Minor cracks with efflorescence in both backwalls. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 1608004 | 1608004 | PE | 2025 | 247500 | 27500 | 275000 | NHPP | Active | TRUE
Indiana | 3280 | 2300899 | INDOT | I-265 EB Bridge Over I-65 | Bridge deck overlay on I-265 EB bridge over I-65 NB/SB, 2.50 miles east of SR 311. This will be constructed in FY 2028. | Clark | 2028 | FALSE | The purpose of this project is to correct the deficiencies in the wearing surface and deck to help further protect the structure and extend the service life of the bridge. The project need is based on the current condition of the structure elements and notable deficiencies in the wearing surface, deck, joints, beam ends, and approach slabs. Vertical and horizontal cracking in both abutment bent caps. Pier 2 column 1 has exposed rebar that appears to be set too close to surface. Minor cracks with efflorescence in both backwalls. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 1608004 | 1608004 | U | 2027 | 9000 | 1000 | 10000 | NHPP | Active | TRUE
Indiana | 3280 | 2300899 | INDOT | I-265 EB Bridge Over I-65 | Bridge deck overlay on I-265 EB bridge over I-65 NB/SB, 2.50 miles east of SR 311. This will be constructed in FY 2028. | Clark | 2028 | FALSE | The purpose of this project is to correct the deficiencies in the wearing surface and deck to help further protect the structure and extend the service life of the bridge. The project need is based on the current condition of the structure elements and notable deficiencies in the wearing surface, deck, joints, beam ends, and approach slabs. Vertical and horizontal cracking in both abutment bent caps. Pier 2 column 1 has exposed rebar that appears to be set too close to surface. Minor cracks with efflorescence in both backwalls. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 1608004 | 1608004 | CN | 2028 | 1190704 | 132300 | 1323004 | NHPP | Active | TRUE
Indiana | 3281 | 2301023 | INDOT | SR 160 | Small structure replacement on SR 160 bridge over Guernsey Creek, east of SR 60. | Clark | 2029 | FALSE | The purpose of this project is to correct the deficiencies in the structure in order to extend or reset the service life of the asset. The project need is based on the current condition of the structure elements. The bottoms of the channel beams have horizontal cracking with efflorescence. Beams #2 and #3 are cracked with heavy efflorescence and Beam #1 is spalling at the downspouts. There are spalls and staining throughout the beams and there is evident leaking and efflorescence between each channel beam. The abutments have vertical cracks above the weep holes and the west abutment below Beam #8 has a 2' x 3' spall. In addition, there are spalls and staining on the south wingwalls. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 1393741 | 1393741 | PE | 2025 | 384120 | 42680 | 426800 | NHPP | Active | TRUE
Indiana | 3281 | 2301023 | INDOT | SR 160 | Small structure replacement on SR 160 bridge over Guernsey Creek, east of SR 60. | Clark | 2029 | FALSE | The purpose of this project is to correct the deficiencies in the structure in order to extend or reset the service life of the asset. The project need is based on the current condition of the structure elements. The bottoms of the channel beams have horizontal cracking with efflorescence. Beams #2 and #3 are cracked with heavy efflorescence and Beam #1 is spalling at the downspouts. There are spalls and staining throughout the beams and there is evident leaking and efflorescence between each channel beam. The abutments have vertical cracks above the weep holes and the west abutment below Beam #8 has a 2' x 3' spall. In addition, there are spalls and staining on the south wingwalls. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 1393741 | 1393741 | ROW | 2026 | 13500 | 1500 | 15000 | NHPP | Active | TRUE
Indiana | 3281 | 2301023 | INDOT | SR 160 | Small structure replacement on SR 160 bridge over Guernsey Creek, east of SR 60. | Clark | 2029 | FALSE | The purpose of this project is to correct the deficiencies in the structure in order to extend or reset the service life of the asset. The project need is based on the current condition of the structure elements. The bottoms of the channel beams have horizontal cracking with efflorescence. Beams #2 and #3 are cracked with heavy efflorescence and Beam #1 is spalling at the downspouts. There are spalls and staining throughout the beams and there is evident leaking and efflorescence between each channel beam. The abutments have vertical cracks above the weep holes and the west abutment below Beam #8 has a 2' x 3' spall. In addition, there are spalls and staining on the south wingwalls. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 1393741 | 1393741 | U | 2027 | 90000 | 10000 | 100000 | NHPP | Active | TRUE
Indiana | 3283 | 1802047 | INDOT | I-64 CCTV/DMS From 3 Miles West of SR 69 to 1 Mile West of SR 62/64, Excluding Vanderburgh & Warrick Counties | Deployment of 14 CCTV cameras and six dynamic message signs on I-64 from 3 miles west of SR 69 near the Illinois state line to 1 mile west of SR 62/64, excluding Vanderburgh and Warrick Counties. The easternmost four CCTV cameras and one DMS are located in Floyd County. | Floyd | 2030 | FALSE | The deployment of CCTV cameras and dynamic message signs on I-64 across southern and southwestern Indiana will improve traffic monitoring and incident response capabilities by INDOT Traffic Management Center personnel and greatly improve pre-trip and en-route traveler information. |  |  | 6400000 | 6400000 | CN | 2028 | 5310000 | 590000 | 5900000 | IM | Active | TRUE
Indiana | 3284 | 2301706 | INDOT | US 31 | Sidewalk improvements on US 31, 1.53 miles north of IN 60 (Foothill Road) to 3.28 miles north of IN 60. This project is going to be bundled with DES 1700111/KIPDA ID 2487. | Clark | 2025 | FALSE | Reconstruction of the existing roadway, improving the safety of pedestrian and bicycle facilities. |  |  | 1100000 | 1100000 | CN | 2025 | 880000 | 220000 | 1100000 | TA-ST | Active | TRUE
Indiana | 3285 | 2200937 | INDOT | Traffic Signals Modernization in Clark County | Updating traffic signal heads through Clark County on US 31 at Lewis and Clark, US 31 and Eastern, and US 31 Stansifer. | Clark | 2027 | FALSE | This project will improve various intersections in Clark County. |  |  | 1977800 | 1977800 | CN | 2027 | 1249240 | 312310 | 1561550 | HSIP-ST | Active | TRUE
Indiana | 3304 | 2201216 | INDOT | Various Locations of Raised Pavement Markings in Seymour District | Raised pavement markings in various locations throughout Seymour District. | Clark, Floyd | 2026 | FALSE | Raised pavement markings in various locations throughout Seymour District. This is in FY 25 for a total of $878,243. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 878243 | 878243 | CN | 2025 | 790419 | 87824 | 878243 | HSIP-ST | Active | TRUE
Indiana | 3306 | 2301123 | INDOT | I-265 | Pavement patching on I-265 from I-65 to 0.69 miles west of SR 62 (ORB O&M Limit). This will be constructed in FY 2028. | Clark | 2028 | FALSE | This section of SR 265 is an urban interstate with 4 lanes approximately 12 ’ wide, inside shoulders approximately 4’ wide, and outside shoulders approximately 10' wide on average. This road section had a concrete pavement restoration project completed in 2019. The concrete slabs are faulting and rocking in multiple locations, which is causing the pavement to rapidly deteriorate. An emergency patching contract is scheduled for FY 2023 to help reduce the chances of this pavement failing before the pavement replacement project is completed. The purpose of this project is to reset the life of the failing pavement through replacement. The new pavement should be designed to last at least 12 years before a preventative maintenance treatment is needed. |  |  | 41024376 | 41024376 | PE | 2025 | 8130690 | 903410 | 9034100 | NHS | Active | TRUE
Indiana | 3306 | 2301123 | INDOT | I-265 | Pavement patching on I-265 from I-65 to 0.69 miles west of SR 62 (ORB O&M Limit). This will be constructed in FY 2028. | Clark | 2028 | FALSE | This section of SR 265 is an urban interstate with 4 lanes approximately 12 ’ wide, inside shoulders approximately 4’ wide, and outside shoulders approximately 10' wide on average. This road section had a concrete pavement restoration project completed in 2019. The concrete slabs are faulting and rocking in multiple locations, which is causing the pavement to rapidly deteriorate. An emergency patching contract is scheduled for FY 2023 to help reduce the chances of this pavement failing before the pavement replacement project is completed. The purpose of this project is to reset the life of the failing pavement through replacement. The new pavement should be designed to last at least 12 years before a preventative maintenance treatment is needed. |  |  | 41024376 | 41024376 | ROW | 2026 | 90000 | 10000 | 100000 | NHS | Active | TRUE
Indiana | 3306 | 2301123 | INDOT | I-265 | Pavement patching on I-265 from I-65 to 0.69 miles west of SR 62 (ORB O&M Limit). This will be constructed in FY 2028. | Clark | 2028 | FALSE | This section of SR 265 is an urban interstate with 4 lanes approximately 12 ’ wide, inside shoulders approximately 4’ wide, and outside shoulders approximately 10' wide on average. This road section had a concrete pavement restoration project completed in 2019. The concrete slabs are faulting and rocking in multiple locations, which is causing the pavement to rapidly deteriorate. An emergency patching contract is scheduled for FY 2023 to help reduce the chances of this pavement failing before the pavement replacement project is completed. The purpose of this project is to reset the life of the failing pavement through replacement. The new pavement should be designed to last at least 12 years before a preventative maintenance treatment is needed. |  |  | 41024376 | 41024376 | U | 2027 | 18000 | 2000 | 20000 | NHS | Active | TRUE
Indiana | 3306 | 2301123 | INDOT | I-265 | Pavement patching on I-265 from I-65 to 0.69 miles west of SR 62 (ORB O&M Limit). This will be constructed in FY 2028. | Clark | 2028 | FALSE | This section of SR 265 is an urban interstate with 4 lanes approximately 12 ’ wide, inside shoulders approximately 4’ wide, and outside shoulders approximately 10' wide on average. This road section had a concrete pavement restoration project completed in 2019. The concrete slabs are faulting and rocking in multiple locations, which is causing the pavement to rapidly deteriorate. An emergency patching contract is scheduled for FY 2023 to help reduce the chances of this pavement failing before the pavement replacement project is completed. The purpose of this project is to reset the life of the failing pavement through replacement. The new pavement should be designed to last at least 12 years before a preventative maintenance treatment is needed. |  |  | 41024376 | 41024376 | CN | 2028 | 28683248 | 3187028 | 31870276 | NHS | Active | TRUE
Indiana | 3313 | 2100157 | INDOT | Traffic Signals Modernization in Seymour District | Traffic signals modernization in various locations throughout Seymour district. | Clark, Floyd | 2026 | FALSE | To replace traffic signals throughout the Seymour district in fiscal year 2026. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 1380000 | 13800000 | CN | 2026 | 1242000 | 138000 | 1380000 | NHPP | Active | TRUE
Indiana | 3314 | 2100195 | INDOT | Install New Cable Barriers Throughout Seymour District | Install new cable barriers throughout Seymour sistrict in various locations. | Clark, Floyd | 2026 | FALSE | Repair cable barriers throughout Seymour district. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 2000000 | 2000000 | CN | 2026 | 1800000 | 200000 | 2000000 | NHPP | Active | TRUE
Indiana | 3315 | 2100189 | INDOT | Raised Pavement Markings in Various Locations in Seymour District | Raised pavement markings in various locations in Seymour district. | Clark, Floyd | 2026 | FALSE | Replace raised pavement markings throughout the Seymour district in various locations. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 750000 | 750000 | CN | 2026 | 675000 | 75000 | 750000 | NHPP | Active | TRUE
Indiana | 3316 | 2400584 | INDOT | Indiana EV Reliability Project | Electric vehicle charging infrastructure in various locations in Indiana. This will be adding PE funds and CN funds in FY 2025. | Clark, Floyd | 2026 | FALSE | Electric vehicle charging infrastructure in various locations in Indiana. |  | 2672 - Air Quality Improvements - Indiana | 983250 | 174991 | PE | 2025 | 122250 | 30563 | 152813 | EVC-RAA | Active | TRUE
Indiana | 3316 | 2400584 | INDOT | Indiana EV Reliability Project | Electric vehicle charging infrastructure in various locations in Indiana. This will be adding PE funds and CN funds in FY 2025. | Clark, Floyd | 2026 | FALSE | Electric vehicle charging infrastructure in various locations in Indiana. |  | 2672 - Air Quality Improvements - Indiana | 983250 | 174991 | CN | 2025 | 17739 | 4439 | 22178 | EVC-RAA | Active | TRUE
Indiana | 3317 | 2400755 | INDOT | I-64 Pavement Patching | Pavement patching on I-64 from 1.01 miles west of SR 64 to 0.19 miles east of SR 111. | Floyd | 2027 | FALSE | Pavement patching along I-64 to repair holes on the interstate. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 3000000 | 3000000 | CN | 2026 | 0 | 3000000 | 3000000 | NHPP | Active | TRUE
Indiana | 3318 | 2301236 | INDOT | Traffic Signal Modernizations in Seymour District FY 2028 | Various locations in Seymour District for traffic signal modernizations to repair. | Clark, Floyd | 2029 | FALSE | To replace traffic signals throughout the Seymour district in discal year 2028. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 3506550 | 3506550 | CN | 2028 | 3155895 | 350655 | 3506550 | HSIP-ST | Active | TRUE
Indiana | 3319 | 2301237 | INDOT | Raised Pavement Markings in Various Locations in Seymour District FY 2028 | Raised pavement markings in various locations in the Seymour District. | Clark, Floyd | 2029 | FALSE | Replace any missed or damage raised pavement markings in the Seymour District. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 750000 | 750000 | CN | 2028 | 675000 | 75000 | 750000 | HSIP-ST | Active | TRUE
Indiana | 3321 | 2300292 | INDOT | SR 60 Over Tributary to Sugar Creek | The purpose of this project is to maintain or improve the current condition ratings of this large culvert to extend the life of the structure. | Clark | 2029 | FALSE | This project will extend the life of the large culvert/structure. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 642733 | 642733 | PE | 2025 | 280000 | 70000 | 350000 | NHPP | Active | TRUE
Indiana | 3322 | 2301127 | INDOT | I-265 Pavement Replacement | Pavement restoration on I-265 from 0.36 miles west of I-65 to I-65. | Clark | 2028 | FALSE | The purpose of this project is to extend the functional life of the pavement by addressing structural and functional deficiencies. This is a standalone project. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 5819396 | 5819396 | PE | 2025 | 450000 | 50000 | 500000 | NHPP | Active | TRUE
Indiana | 3322 | 2301127 | INDOT | I-265 Pavement Replacement | Pavement restoration on I-265 from 0.36 miles west of I-65 to I-65. | Clark | 2028 | FALSE | The purpose of this project is to extend the functional life of the pavement by addressing structural and functional deficiencies. This is a standalone project. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 5819396 | 5819396 | ROW | 2026 | 18000 | 2000 | 20000 | NHPP | Active | TRUE
Indiana | 3322 | 2301127 | INDOT | I-265 Pavement Replacement | Pavement restoration on I-265 from 0.36 miles west of I-65 to I-65. | Clark | 2028 | FALSE | The purpose of this project is to extend the functional life of the pavement by addressing structural and functional deficiencies. This is a standalone project. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 5819396 | 5819396 | U | 2027 | 9000 | 1000 | 10000 | NHPP | Active | TRUE
Indiana | 3322 | 2301127 | INDOT | I-265 Pavement Replacement | Pavement restoration on I-265 from 0.36 miles west of I-65 to I-65. | Clark | 2028 | FALSE | The purpose of this project is to extend the functional life of the pavement by addressing structural and functional deficiencies. This is a standalone project. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 5819396 | 5819396 | CN | 2028 | 4760456 | 528940 | 5289396 | NHPP | Active | TRUE
Indiana | 3323 | 2300707 | INDOT | SR 62 Intersection Improvement at Charlestown Pike and Logistics Avenue | Proposed intersection improvement project on SR 62 at the Charlestown Pike and Logistics Avenue intersection. | Clark | 2031 | FALSE | The need for the project is to improve access, safety, and traffic operations due to increasing growth and congestion along SR 62. Existing developments built along the corridor in combination with growing traffic in the area are beginning to negatively impact operations. Anticipated future development, including developments at River Ridge will further affect safety and operation at intersections in the design year. Fifteen intersections along the corridor were evaluated for existing and future operations, safety, and access. |  | 2678 - Roadway Operational Improvements - Indiana | 1177471 | 1177471 | PE | 2025 | 270000 | 30000 | 300000 | HSIP-ST | Active | TRUE
Indiana | 3323 | 2300707 | INDOT | SR 62 Intersection Improvement at Charlestown Pike and Logistics Avenue | Proposed intersection improvement project on SR 62 at the Charlestown Pike and Logistics Avenue intersection. | Clark | 2031 | FALSE | The need for the project is to improve access, safety, and traffic operations due to increasing growth and congestion along SR 62. Existing developments built along the corridor in combination with growing traffic in the area are beginning to negatively impact operations. Anticipated future development, including developments at River Ridge will further affect safety and operation at intersections in the design year. Fifteen intersections along the corridor were evaluated for existing and future operations, safety, and access. |  | 2678 - Roadway Operational Improvements - Indiana | 1177471 | 1177471 | Planning | 2027 | 270000 | 30000 | 300000 | HSIP-ST | Active | TRUE
Indiana | 3323 | 2300707 | INDOT | SR 62 Intersection Improvement at Charlestown Pike and Logistics Avenue | Proposed intersection improvement project on SR 62 at the Charlestown Pike and Logistics Avenue intersection. | Clark | 2031 | FALSE | The need for the project is to improve access, safety, and traffic operations due to increasing growth and congestion along SR 62. Existing developments built along the corridor in combination with growing traffic in the area are beginning to negatively impact operations. Anticipated future development, including developments at River Ridge will further affect safety and operation at intersections in the design year. Fifteen intersections along the corridor were evaluated for existing and future operations, safety, and access. |  | 2678 - Roadway Operational Improvements - Indiana | 1177471 | 1177471 | ROW | 2027 | 9000 | 1000 | 10000 | HSIP-ST | Active | TRUE
Indiana | 3323 | 2300707 | INDOT | SR 62 Intersection Improvement at Charlestown Pike and Logistics Avenue | Proposed intersection improvement project on SR 62 at the Charlestown Pike and Logistics Avenue intersection. | Clark | 2031 | FALSE | The need for the project is to improve access, safety, and traffic operations due to increasing growth and congestion along SR 62. Existing developments built along the corridor in combination with growing traffic in the area are beginning to negatively impact operations. Anticipated future development, including developments at River Ridge will further affect safety and operation at intersections in the design year. Fifteen intersections along the corridor were evaluated for existing and future operations, safety, and access. |  | 2678 - Roadway Operational Improvements - Indiana | 1177471 | 1177471 | U | 2027 | 22500 | 2500 | 25000 | HSIP-ST | Active | TRUE
Indiana | 3324 | 2401157 | INDOT | SR 3 Bridge Deck Overlay | Bridge deck overlay on SR 3 Bridge over Pleasant Run, 1.01 Miles north of SR 62. | Floyd | 2029 | FALSE | The purpose of the project is to protect the existing deck with a preventive maintenance wearing surface treatment to help extend the service life of the bridge deck The wearing surface is monolithic with the deck. There are sealed cracks on the north and south side of the west sidewalk. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 360000 | 360000 | PE | 2026 | 80000 | 20000 | 100000 | Bridge | Active | TRUE
Indiana | 3330 |  | Clark County | Clark County Small Structure Inventory | Clark County would like to complete a Small Structure Inventory of all drainage structures larger than 3-foot diameter up to the 20-foot span for bridges. Clark County last completed a small structure inventory in 1996. IDEM has asked the County to prepare an inventory of all drainage structures. | Clark | 2026 | FALSE | IDEM has asked the County to prepare an inventory of all drainage structures throughout the County. presently we are digitizing drainage structures an all new subdivisions but we will need to update our current small structure inventory last completed in 1996. |  | 2682 - Transit Improvements - Indiana | 250000 | 250000 | Planning | 2025 | 200000 | 50000 | 250000 | Group III | Active | TRUE
Indiana | 3331 | 2401684 | Sellersburg | Allentown Road Safety Curb | Installation of safety curb on both sides of roadway. Starting point on Allentown Road approximately 830' south of Perry Crossing Road. End point on Allentown Road approximately 1520' south of Perry Crossing Road. Includes 4 driveway culvert replacements. | Clark | 2025 | FALSE | Due to age of road and buildup of asphalt, this area of Allentown Road has 8-12 inches of drop-off at edge of pavement. Safety curb will provide a transition at edge of road to prevent accidents and property damage. |  | 2680 - Safety Improvements - Indiana | 45265 | 45265 | C | 2025 | 40738 | 4527 | 45265 | HSIP-ST | Active | TRUE
Indiana | 3332 | 2401687 | Sellersburg | Penn Avenue Safety Curb | Installation of safety curb on South Penn Avenue, 230' north of US 31. Project continues for 405' north along the east side of Penn Avenue and ends 635' north of US 31. | Clark | 2025 | FALSE | Due to age of road and repaving over the years, Penn Avenue has 8-12 inches of drop-off at edge of pavement then into a ditch along railroad. Project will improve safety along roadway as drivers exit US 31 on to Penn Avenue. |  | 2680 - Safety Improvements - Indiana | 40150 | 150000 | C | 2025 | 135000 | 15000 | 150000 | HSIP-ST | Active | TRUE
Indiana | 3333 | 2401688 | Sellersburg | Camp Run/American Way Lighting Installation | Installation of lighting along Camp Run Parkway and American Way. | Clark | 2027 | FALSE | Camp Run Parkway and American Way are new roadways within the Town of Sellersburg. They are currently unlit and receive extensive use by vehicle traffic as well as walkers. Lighting will improve overall safety of the area. |  | 2680 - Safety Improvements - Indiana | 150000 | 150000 | CN | 2027 | 135000 | 15000 | 150000 | HSIP-ST | Active | TRUE
Indiana | 3334 | 2401659 | Jeffersonville | Jeffersonville High School HAWK Beacon | The City intends to install a high-intensity activated crosswalk on Allison Lane at Wooded Way, in front of the Jeffersonville High School. | Clark | 2026 | FALSE | The purpose of this project is to install a High-intensity Activated Crosswalk (HAWK) signal at the crosswalk in front of Jeffersonville High School on Allison Lane at Wooded Way. The need for this project is very high, due to this being a very busy crosswalk for pedestrians including student pedestrians, especially before and after school. |  | 2674 - Bicycle & Pedestrian Improvements - Indiana | 327500 | 327500 | C | 2025 | 294750 | 32750 | 327500 | HSIP-ST | Active | TRUE
Indiana | 3335 | 2401673 | Jeffersonville | Jeffersonville Raised Pavement Markings | Install raised pavement markings (RPMs) in the centerline stripes, broken white lane stripes, and turn lane stripes on various city streets. | Clark | 2026 | FALSE | The intent of this project is to improve the visibility at night and during poor visibility weather conditions. |  | 2680 - Safety Improvements - Indiana | 270362 | 270362 | C | 2025 | 243326 | 27036 | 270362 | HSIP-ST | Active | TRUE
Indiana | 3336 | 2401683 | Jeffersonville | Utica Pike Rumble Strips | Install centerline rumble strips along Utica Pike from Main Street to Loop Road. | Clark | 2026 | FALSE | Utica Pike is a long stretch of roadway with heavy two-way traffic. There are very few controlled intersections and a very high risk of head-on collisions due to the length, speed, and heavy two-way, two-lane traffic flow on this roadway. With the installation of rumble strips along the centerline of the roadway, this will be an early indication for drivers potentially crossing over the centerline to correct and avoid serious head-on collisions with other motorists. |  | 2680 - Safety Improvements - Indiana | 55600 | 55600 | CN | 2025 | 50040 | 5560 | 55600 | HSIP-ST | Active | TRUE
Indiana | 3338 |  | Blue River Services | Operating Expenses (Section 5310-24 OTHER Project) | Operating Assistance for Blue River Services Fleet Expansion for Floyd County Project to provide on-demand transportation service for seniors in assisted living residences in Floyd County and for individuals with disabilities. | Floyd | 2025 | FALSE | The purpose of this Section 5310 project is to provide transportation for seniors and individuals with disabilities when public transportation is insufficient, inappropriate, or unavailable. | 2291 |  | 30368 | 30368 | Transit Capital | 2025 | 15184 | 15184 | 30368 | Section 5310 | Active | TRUE
Indiana | 3342 |  | Blue River Services | Purchase Transit Vehicles (Section 5310-24 TRADITIONAL Project) | Blue River Services Fleet Expansion for Floyd County Project to purchase two (2) ADA-accessible full-size vans. The project will provide on-demand transportation service for seniors in assisted living residences in Floyd County and for individuals with disabilities. | Floyd | 2025 | FALSE | The purpose of this Section 5310 project is to provide transportation for seniors and individuals with disabilities when public transportation is insufficient, inappropriate, or unavailable. | 2291 |  | 193600 | 193600 | Transit Capital | 2025 | 154880 | 38720 | 193600 | Section 5310 | Active | TRUE
Indiana | 3346 |  | LifeSpan | Purchase Transit Vehicles (Section 5310-24 TRADITIONAL Project) | Lifespan Resources Transportation Project to purchase two (2) ADA-accessible full-size vans with enhanced HVAC, all-wheel-drive, fog lights, and automatic sliding door. The project will provide transportation for individuals with disabilities to and from day services and work programs. The vehicles will also provide on-demand transportation for seniors and individuals with disabilities for medical trips, including critical care trips such as dialysis, and chemotherapy, as well as trips to the grocery, senior center, library, and post office, with an emphasis on serving low-income residents. | Clark, Floyd | 2025 | FALSE | The purpose of this Section 5310 project is to provide transportation for seniors and individuals with disabilities when public transportation is insufficient, inappropriate, or unavailable. | 2291 |  | 214400 | 214400 | Transit Capital | 2025 | 171520 | 42880 | 214400 | Section 5310 | Active | TRUE
Indiana | 3348 |  | Volunteers of America | Purchase Transit Vehicles (Section 5310-24 TRADITIONAL Project) | Volunteers of America for the VOA Community IN 2024 Project to purchase one (1) ADA-wheelchair-accessible minivan. The project will transport seniors and individuals with developmental and physical disabilities in Floyd and Clark Counties in Indiana to medical care appointments, recreation, and participation in the community, including enrichment activities. | Clark, Floyd | 2025 | FALSE | The purpose of this Section 5310 project is to provide transportation for seniors and individuals with disabilities when public transportation is insufficient, inappropriate, or unavailable. | 2291 |  | 87000 | 87000 | Transit Capital | 2025 | 69600 | 17400 | 87000 | Section 5310 | Active | TRUE
Indiana | 3362 | 2401391 | INDOT | Intersection Improvement at US 31 and Eastern Boulevard | US 31 and Eastern Boulevard intersection improvement. | Clark | 2029 | FALSE | The project will improve pedestrian mobility with the roundabouts by providing shorter crossings across Eastern Boulevard and refuge with raised curb medians. |  |  | 8847958 | 8847958 | PE | 2026 | 1697126 | 188570 | 1885696 | NHPP | Active | TRUE
Indiana | 3362 | 2401391 | INDOT | Intersection Improvement at US 31 and Eastern Boulevard | US 31 and Eastern Boulevard intersection improvement. | Clark | 2029 | FALSE | The project will improve pedestrian mobility with the roundabouts by providing shorter crossings across Eastern Boulevard and refuge with raised curb medians. |  |  | 8847958 | 8847958 | U | 2027 | 182700 | 20300 | 203000 | NHPP | Active | TRUE
Indiana | 3363 | 2201202 | INDOT | Merry Way Near Georgetown Elementary | The purpose of this project is to remove physical barriers that inhibit access to and away from schools and public parking in Georgetown. Upon completion of the project, all pedestrian facilities at the SR 64 intersection of Merry Way and at SR 64 should meet the minimum requirements for ADA compliance. INDOT is required to address substandard curb ramps and pedestrian facilities to remain in keeping with FHWA requirements and the law, therefore the no-build alternative is dismissed. | Floyd | 2027 | FALSE | INDOT is required to address substandard curb ramps and pedestrian facilities to remain in keeping wi FHWA requirements and the law, therefore the no-build alternative is dismissed. |  |  | 1078250 | 1078250 | ROW | 2026 | 45000 | 5000 | 50000 | HSIP-ST | Active | TRUE
Indiana | 3363 | 2201202 | INDOT | Merry Way Near Georgetown Elementary | The purpose of this project is to remove physical barriers that inhibit access to and away from schools and public parking in Georgetown. Upon completion of the project, all pedestrian facilities at the SR 64 intersection of Merry Way and at SR 64 should meet the minimum requirements for ADA compliance. INDOT is required to address substandard curb ramps and pedestrian facilities to remain in keeping with FHWA requirements and the law, therefore the no-build alternative is dismissed. | Floyd | 2027 | FALSE | INDOT is required to address substandard curb ramps and pedestrian facilities to remain in keeping wi FHWA requirements and the law, therefore the no-build alternative is dismissed. |  |  | 1078250 | 1078250 | CN | 2027 | 749700 | 83300 | 833000 | HSIP-ST | Active | TRUE
Indiana | 3364 | 2401840 | Clark County | CR 311 and Sellersburg Improvements | Corridor improvements will extend along CR 311 from SR 60 to US 31 in Sellersburg. Project will add sidewalks, a bike path and a center turn lane to provide safe traffic/transportation alternatives and improve overall safety in the area. | Clark | 2030 | FALSE | KIPDA funded corridor study recommended a center left turn lane for the CR 311. Sellersburg has asked for sidewalks and bike path to provide safe alternative options for residents. Sellersburg is moving most of their town center options to this part of Sellersburg and are requesting the county to help improve the area for their residents. |  |  | 14628416 | 2791342 | PE | 2026 | 600000 | 150000 | 750000 | Group III | Active | TRUE
Indiana | 3364 | 2401840 | Clark County | CR 311 and Sellersburg Improvements | Corridor improvements will extend along CR 311 from SR 60 to US 31 in Sellersburg. Project will add sidewalks, a bike path and a center turn lane to provide safe traffic/transportation alternatives and improve overall safety in the area. | Clark | 2030 | FALSE | KIPDA funded corridor study recommended a center left turn lane for the CR 311. Sellersburg has asked for sidewalks and bike path to provide safe alternative options for residents. Sellersburg is moving most of their town center options to this part of Sellersburg and are requesting the county to help improve the area for their residents. |  |  | 14628416 | 2791342 | PE | 2026 | 142733 | 35683 | 178416 | CMAQ-MPO | Active | TRUE
Indiana | 3364 | 2401840 | Clark County | CR 311 and Sellersburg Improvements | Corridor improvements will extend along CR 311 from SR 60 to US 31 in Sellersburg. Project will add sidewalks, a bike path and a center turn lane to provide safe traffic/transportation alternatives and improve overall safety in the area. | Clark | 2030 | FALSE | KIPDA funded corridor study recommended a center left turn lane for the CR 311. Sellersburg has asked for sidewalks and bike path to provide safe alternative options for residents. Sellersburg is moving most of their town center options to this part of Sellersburg and are requesting the county to help improve the area for their residents. |  |  | 14628416 | 2791342 | PE | 2027 | 50341 | 12585 | 62926 | CMAQ-MPO | Active | TRUE
Indiana | 3364 | 2401840 | Clark County | CR 311 and Sellersburg Improvements | Corridor improvements will extend along CR 311 from SR 60 to US 31 in Sellersburg. Project will add sidewalks, a bike path and a center turn lane to provide safe traffic/transportation alternatives and improve overall safety in the area. | Clark | 2030 | FALSE | KIPDA funded corridor study recommended a center left turn lane for the CR 311. Sellersburg has asked for sidewalks and bike path to provide safe alternative options for residents. Sellersburg is moving most of their town center options to this part of Sellersburg and are requesting the county to help improve the area for their residents. |  |  | 14628416 | 2791342 | ROW | 2028 | 500000 | 100000 | 600000 | CMAQ-MPO | Active | TRUE
Indiana | 3365 | 2401839 | Clark County | Memphis Blue Lick Roadway Improvements | This project will enhance the overall capacity of the Memphis Blue Lick Road and the surrounding area, from Crone Road near the I-65 Interchange to the existing Champions Point S/D, 2+ miles to the west. There are potentially four intersections that must be enhanced (one is an INDOT interchange at I-65); potentially two bridge improvement structures and several small structure crossings that will need to be improved along with the roadway widening for the area. The roadway widening shall include pavement drive lane expansion and improved paved shoulders. Bike paths will also be considered for this project. | Clark | 2031 | FALSE | This area is experiencing significant growth. To date there are 6 residential developments that have been platted with over 2500 new residential lots already approved and significantly more potential for the area. Vehicle counts in the area were completed in 2013 and ranged from 800-2000 AVD. new vehicle counts were completed in 2023, and the numbers have increased to 8000-9000 AVD at locations along the Memphis Blue Lick corridor. Residents in the area are concerned with the growth occurring and the potential for new growth in the currently undeveloped areas. |  |  | 9700000 | 100000 | Planning | 2026 | 80000 | 20000 | 100000 | Group III | Active | TRUE
Indiana | 3366 | 2401835 | Floyd County Board of Commissioners | Bridge 38 (Baylor Wissman Replacement) | Project will replace existing bridge due to poor geometry and the superstructure and substructure deterioration. It will expand bridge from one to two travel lanes with 2 foot shoulders. Approach will be re-aligned to improve site distance. | Floyd | 2031 | FALSE | Existing bridge was constructed in 1950 as one lane crossing and is deteriorating. Bridge provides access to road connecting major subdivisions and provides cross I-64 access to County. Approach has horizontal curve decreasing sight distance and making more unsafe. |  |  | 3151000 | 3151000 | PE | 2026 | 360000 | 90000 | 450000 | Group III | Active | TRUE
Indiana | 3366 | 2401835 | Floyd County Board of Commissioners | Bridge 38 (Baylor Wissman Replacement) | Project will replace existing bridge due to poor geometry and the superstructure and substructure deterioration. It will expand bridge from one to two travel lanes with 2 foot shoulders. Approach will be re-aligned to improve site distance. | Floyd | 2031 | FALSE | Existing bridge was constructed in 1950 as one lane crossing and is deteriorating. Bridge provides access to road connecting major subdivisions and provides cross I-64 access to County. Approach has horizontal curve decreasing sight distance and making more unsafe. |  |  | 3151000 | 3151000 | ROW | 2027 | 32000 | 8000 | 40000 | STBG-MPO | Active | TRUE
Indiana | 3367 | 2401834 | Floyd County Board of Commissioners | Baylor Wissman Hilltop | Project will replace existing roadway on Baylor Wissman Road from Brookstone Court to Bridge 38 to widen lanes to 11 feet in each direction, add 2-foot shoulders with 1-foot aggregate. Additional safety measures including edge striping and curve notices will be included among other potential improvements. | Floyd | 2031 | FALSE | Crash data and a recent Thoroughfare Study indicated run off road crashes on this roadway. The development of a large subdivision in the Town of Georgetown that will utilize this roadway will increase traffic volume and likelihood of additional incidents. |  |  | 3336344 | 867486 | PE | 2026 | 161481 | 40371 | 201852 | Group III | Active | TRUE
Indiana | 3368 | 2401836 | Floyd County Board of Commissioners | Highway 150 Break Highlander Point | Establishment of lighted intersection between Old Vincennes Road and West Luther Road on Highway 150 providing additional access to Highlander Point Gateway district. | Floyd | 2030 | FALSE | Additional access needed from Highway 150 to alleviate congestion and reduce accidents at Old Vincennes Road intersection. Additionally, will provide access to developing areas on either side of Highway. |  |  | 4246525 | 4246525 | PE | 2026 | 315000 | 78750 | 393750 | Group III | Active | TRUE
Indiana | 3368 | 2401836 | Floyd County Board of Commissioners | Highway 150 Break Highlander Point | Establishment of lighted intersection between Old Vincennes Road and West Luther Road on Highway 150 providing additional access to Highlander Point Gateway district. | Floyd | 2030 | FALSE | Additional access needed from Highway 150 to alleviate congestion and reduce accidents at Old Vincennes Road intersection. Additionally, will provide access to developing areas on either side of Highway. |  |  | 4246525 | 4246525 | CE | 2028 | 402029 | 100507 | 502536 | STBG-MPO | Active | TRUE
Indiana | 3368 | 2401836 | Floyd County Board of Commissioners | Highway 150 Break Highlander Point | Establishment of lighted intersection between Old Vincennes Road and West Luther Road on Highway 150 providing additional access to Highlander Point Gateway district. | Floyd | 2030 | FALSE | Additional access needed from Highway 150 to alleviate congestion and reduce accidents at Old Vincennes Road intersection. Additionally, will provide access to developing areas on either side of Highway. |  |  | 4246525 | 4246525 | CN | 2028 | 2680191 | 670048 | 3350239 | STBG-MPO | Active | TRUE
Indiana | 3369 | 2401854 | New Albany | Slate Run Road Improvements Phase 2 | The project consists of the widening of Slate Run Road from Lockwood Drive to Ekin Avenue in New Albany, Indiana. The road is being widened to create new separate bicycle lanes. Curb and gutter will be added to both sides of the roadway, and new sidewalks will be constructed outside of the curb lines. | Floyd | 2031 | FALSE | This is Phase 2 of an overall project for which Phase 1 construction was completed in 2021. Slate Run Road has been a safety issue for the City of New Albany due to speeding motorists and the lack of bicycle and pedestrian facilities. The roadway is highly trafficked by bicycles and pedestrians due to the existence of the Slate Run Elementary School. This project is needed to assist in traffic calming to reduce speeding motorists, as well as provide safe bicycle paths and pedestrian walkways separate and outside of the roadway to reduce the risk of fatalities and injuries along this corridor. |  |  | 7645000 | 7645000 | PE | 2026 | 200000 | 50000 | 250000 | Group III | Active | TRUE
Indiana | 3369 | 2401854 | New Albany | Slate Run Road Improvements Phase 2 | The project consists of the widening of Slate Run Road from Lockwood Drive to Ekin Avenue in New Albany, Indiana. The road is being widened to create new separate bicycle lanes. Curb and gutter will be added to both sides of the roadway, and new sidewalks will be constructed outside of the curb lines. | Floyd | 2031 | FALSE | This is Phase 2 of an overall project for which Phase 1 construction was completed in 2021. Slate Run Road has been a safety issue for the City of New Albany due to speeding motorists and the lack of bicycle and pedestrian facilities. The roadway is highly trafficked by bicycles and pedestrians due to the existence of the Slate Run Elementary School. This project is needed to assist in traffic calming to reduce speeding motorists, as well as provide safe bicycle paths and pedestrian walkways separate and outside of the roadway to reduce the risk of fatalities and injuries along this corridor. |  |  | 7645000 | 7645000 | ROW | 2027 | 402940 | 100735 | 503675 | TA-MPO | Active | TRUE
Indiana | 3369 | 2401854 | New Albany | Slate Run Road Improvements Phase 2 | The project consists of the widening of Slate Run Road from Lockwood Drive to Ekin Avenue in New Albany, Indiana. The road is being widened to create new separate bicycle lanes. Curb and gutter will be added to both sides of the roadway, and new sidewalks will be constructed outside of the curb lines. | Floyd | 2031 | FALSE | This is Phase 2 of an overall project for which Phase 1 construction was completed in 2021. Slate Run Road has been a safety issue for the City of New Albany due to speeding motorists and the lack of bicycle and pedestrian facilities. The roadway is highly trafficked by bicycles and pedestrians due to the existence of the Slate Run Elementary School. This project is needed to assist in traffic calming to reduce speeding motorists, as well as provide safe bicycle paths and pedestrian walkways separate and outside of the roadway to reduce the risk of fatalities and injuries along this corridor. |  |  | 7645000 | 7645000 | ROW | 2028 | 1033060 | 258265 | 1291325 | TA-MPO | Active | TRUE
Indiana | 3395 | 2400591 | INDOT | Soil Nail Repair on Mechanically Stabilized Earth Failures | IDIQ contract, specific locations not yet determined, soil nail repair on MSE failures - INDOT South Districts Vincennes and Seymour. | Clark, Floyd | 2027 | FALSE | Repair failed/failing MSE walls, asset preservation. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 2000000 | 2000000 | CN | 2026 | 1600000 | 400000 | 2000000 | STBG-ST | Active | TRUE
Indiana | 3396 | 2401479 | INDOT | Small Structure and Drain Construction on SR 3, 4.85 Miles North of SR 62 | Small structure and drain repair/replacement on SR 3, 4.85 miles north of SR 62. | Clark | 2029 | FALSE | This project will improve the condition of the culvert, prevent damage to roadway, and assist with drainage. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 536000 | 536000 | PE | 2026 | 160000 | 40000 | 200000 | STBG-ST | Active | TRUE
Indiana | 3396 | 2401479 | INDOT | Small Structure and Drain Construction on SR 3, 4.85 Miles North of SR 62 | Small structure and drain repair/replacement on SR 3, 4.85 miles north of SR 62. | Clark | 2029 | FALSE | This project will improve the condition of the culvert, prevent damage to roadway, and assist with drainage. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 536000 | 536000 | U | 2027 | 40000 | 10000 | 50000 | STBG-ST | Active | TRUE
Indiana | 3396 | 2401479 | INDOT | Small Structure and Drain Construction on SR 3, 4.85 Miles North of SR 62 | Small structure and drain repair/replacement on SR 3, 4.85 miles north of SR 62. | Clark | 2029 | FALSE | This project will improve the condition of the culvert, prevent damage to roadway, and assist with drainage. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 536000 | 536000 | ROW | 2027 | 16000 | 4000 | 20000 | STBG-ST | Active | TRUE
Indiana | 3396 | 2401479 | INDOT | Small Structure and Drain Construction on SR 3, 4.85 Miles North of SR 62 | Small structure and drain repair/replacement on SR 3, 4.85 miles north of SR 62. | Clark | 2029 | FALSE | This project will improve the condition of the culvert, prevent damage to roadway, and assist with drainage. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 536000 | 536000 | CN | 2028 | 212800 | 53200 | 266000 | STBG-ST | Active | TRUE
Indiana | 3397 | 2401349 | INDOT | Small Structure Repair/Replacement on SR 60, 5.38 Miles East of SR 335 | Repair/replacement of culvert on SR 60, 5.38 miles east of SR 335. | Clark | 2029 | FALSE | This project will improve the condition of the existing culvert and prevent damage to the roadway and improve drainage. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 2590000 | 2590000 | PE | 2026 | 240000 | 60000 | 300000 | STBG-ST | Active | TRUE
Indiana | 3397 | 2401349 | INDOT | Small Structure Repair/Replacement on SR 60, 5.38 Miles East of SR 335 | Repair/replacement of culvert on SR 60, 5.38 miles east of SR 335. | Clark | 2029 | FALSE | This project will improve the condition of the existing culvert and prevent damage to the roadway and improve drainage. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 2590000 | 2590000 | ROW | 2027 | 32000 | 8000 | 40000 | STBG-ST | Active | TRUE
Indiana | 3397 | 2401349 | INDOT | Small Structure Repair/Replacement on SR 60, 5.38 Miles East of SR 335 | Repair/replacement of culvert on SR 60, 5.38 miles east of SR 335. | Clark | 2029 | FALSE | This project will improve the condition of the existing culvert and prevent damage to the roadway and improve drainage. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 2590000 | 2590000 | U | 2028 | 200000 | 50000 | 250000 | STBG-ST | Active | TRUE
Indiana | 3404 | 2500081 | INDOT | Pavement Patching on I-265 from I-65 to 0.69 Miles West of SR 62 | The small culvert replacement portion of project with original DES # 2301123. Funding was decreased from DES #2301123 and separated to DES # 2500081. | Clark | 2028 | FALSE | To improve the pavement conditions of I-265. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 3373475 | 3373475 | CN | 2028 | 3036128 | 337347 | 3373475 | NHPP | Active | TRUE
Indiana | 3405 | 2500079 | INDOT | I-265 Pavement Replacement | Pavement restoration project on I-265 from 0.36 miles west of I-65 to I-65, this DES # includes the small culvert repair/replacement portion. | Clark | 2028 | FALSE | The purpose of this project is to extend the functional life of the pavement by addressing structural and functional deficiencies. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 240424 | 240424 | CN | 2028 | 216382 | 24042 | 240424 | NHPP | Active | TRUE
Indiana | 3413 | 2001561 | INDOT | Statewide Signing and Installation of Conflict Warning Signs | This is a statewide signing installation and repair of conflict warning signs in various locations throughout the state. | Floyd | 2026 | FALSE | Installation of conflict warning signs are a safety initiative to help prevent injuries and accidents. |  |  | 1537734 | 1537734 | CN | 2026 | 1230187 | 307547 | 1537734 | HSIP-ST | Active | TRUE
Indiana | 3423 | 2500653 | INDOT | US 150 EB Over I-64, 8.81 Miles East of SR 335 | Replace superstructure on US 150 EB of I-64, 8.81 miles east of SR 335. | Floyd | 2031 | FALSE | The purpose of this project is to correct the deficiencies in the wearing surface, deck, and superstructure to help further protect the structure and extend the service life of the bridge. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 5984882 | 5984882 | PE | 2026 | 675000 | 75000 | 750000 | NHPP | Active | TRUE
Indiana | 3423 | 2500653 | INDOT | US 150 EB Over I-64, 8.81 Miles East of SR 335 | Replace superstructure on US 150 EB of I-64, 8.81 miles east of SR 335. | Floyd | 2031 | FALSE | The purpose of this project is to correct the deficiencies in the wearing surface, deck, and superstructure to help further protect the structure and extend the service life of the bridge. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 5984882 | 5984882 | U | 2027 | 9000 | 1000 | 10000 | NHPP | Active | TRUE
Indiana | 3424 | 2500654 | INDOT | US 150 WB Over I-64, 8.81 Miles East of SR 335 | Replace superstructure on US 150 WB over I-64, 8.81 miles east of SR 335. | Floyd | 2031 | FALSE | The purpose of this project is to correct the deficiencies in the wearing surface, deck, and superstructure to help further protect the structure and extend the service life of the bridge. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 5984882 | 5984882 | PE | 2026 | 675000 | 75000 | 750000 | NHPP | Active | TRUE
Indiana | 3424 | 2500654 | INDOT | US 150 WB Over I-64, 8.81 Miles East of SR 335 | Replace superstructure on US 150 WB over I-64, 8.81 miles east of SR 335. | Floyd | 2031 | FALSE | The purpose of this project is to correct the deficiencies in the wearing surface, deck, and superstructure to help further protect the structure and extend the service life of the bridge. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 5984882 | 5984882 | U | 2027 | 9000 | 1000 | 10000 | NHPP | Active | TRUE
Indiana | 3425 | 2500631 | INDOT | SR 60 Over Persimmon Run, 4.93 Miles West of SR 111 | SR 60 over Persimmon Run, 4.93 miles west of SR 111, bridge thin deck overlay. | Clark | 2031 | FALSE | The purpose of this project is to maintain or improve the current condition ratings of this bridge deck and wearing surface. Applying a thin deck overlay will extend the performance life of this structure, thereby, delaying the need for a more costly rigid overlay project. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 417577 | 417577 | PE | 2026 | 120000 | 30000 | 150000 | STBG-ST | Active | TRUE
Indiana | 3427 | 2201149 | INDOT | Traffic Signal Modernization | Traffic signal improvements at I-265 WB/EB at State Street and Paoli Pike, and I-265 WB/EB at Grant Line Road. | Floyd | 2027 | FALSE | This project will improve the traffic signals on the off ramps on I-265 at Grant Line Road and State Street. |  | 2680 - Safety Improvements - Indiana | 1187875 | 1187875 | CN | 2027 | 855000 | 95000 | 950000 | HSIP-ST | Active | TRUE
Indiana | 3432 | 2500785 | INDOT | I-265 at International Drive | Access control project (right of way) I-265 at International Drive. | Clark | 2031 | FALSE | INDOT began to purchase Limited Access Right of Way (LARW) near Interstate interchanges where there currently is inadequate coverage. Currently, the interchange only has LARW along International drive for roughly 0 to 300 feet of the interchange terminal intersections. It is desirable to have between 600’ and 1300’ of LARW protection. |  |  | 2209773 | 2209773 | PE | 2026 | 27000 | 3000 | 30000 | NHPP | Active | TRUE
Indiana | 3432 | 2500785 | INDOT | I-265 at International Drive | Access control project (right of way) I-265 at International Drive. | Clark | 2031 | FALSE | INDOT began to purchase Limited Access Right of Way (LARW) near Interstate interchanges where there currently is inadequate coverage. Currently, the interchange only has LARW along International drive for roughly 0 to 300 feet of the interchange terminal intersections. It is desirable to have between 600’ and 1300’ of LARW protection. |  |  | 2209773 | 2209773 | ROW | 2028 | 1745100 | 193900 | 1939000 | NHPP | Active | TRUE
Indiana | 3458 | 2300106 | Floyd County Board of Commissioners | Floyd County Bridge Inspection and Inventory Program 2026-2029 | It is county-wide bridge inspection and inventory program in accordance with the National Bridge Inspection Standards Cycle 2026-2029. | Floyd | 2029 | FALSE | It is a requirement for all bridges in the county except the highway bridges should be inspected. Copies of the SI&A reports shall be provided to the adjacent county if required. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 291475 | 291475 | PE | 2026 | 122125 | 30531 | 152656 | Bridge | Active | TRUE
Indiana | 3458 | 2300106 | Floyd County Board of Commissioners | Floyd County Bridge Inspection and Inventory Program 2026-2029 | It is county-wide bridge inspection and inventory program in accordance with the National Bridge Inspection Standards Cycle 2026-2029. | Floyd | 2029 | FALSE | It is a requirement for all bridges in the county except the highway bridges should be inspected. Copies of the SI&A reports shall be provided to the adjacent county if required. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 291475 | 291475 | PE | 2027 | 13690 | 3422 | 17112 | Bridge | Active | TRUE
Indiana | 3458 | 2300106 | Floyd County Board of Commissioners | Floyd County Bridge Inspection and Inventory Program 2026-2029 | It is county-wide bridge inspection and inventory program in accordance with the National Bridge Inspection Standards Cycle 2026-2029. | Floyd | 2029 | FALSE | It is a requirement for all bridges in the county except the highway bridges should be inspected. Copies of the SI&A reports shall be provided to the adjacent county if required. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 291475 | 291475 | PE | 2028 | 83676 | 20919 | 104595 | Bridge | Active | TRUE
Indiana | 3463 | 11.13.15 | Blue River Services | Purchase Transit Vehicles (Section 5310-25 TRADITIONAL Project) | Blue River Services Fleet for Floyd County Project to purchase one ADA-accessible full-size van. The project will provide on-demand transportation service for seniors in assisted living residences in Floyd County and for individuals with disabilities. | Floyd | 2026 | FALSE | The purpose of this Section 5310 project is to provide transportation for seniors and individuals with disabilities when public transportation is insufficient, inappropriate, or unavailable. | 2291 |  | 99800 | 99800 | Transit Capital | 2026 | 79840 | 19960 | 99800 | Section 5310 | Active | TRUE
Indiana | 3470 | 30.09.01 | Blue River Services | Operating Expenses (Section 5310-25 OTHER Project) | Blue River Services Fleet for Floyd County Project for eligible operating expenses to provide on-demand transportation service for seniors in assisted living residences in Floyd County and for individuals with disabilities. | Floyd | 2026 | FALSE | The purpose of this Section 5310 project is to provide transportation for seniors and individuals with disabilities when public transportation is insufficient, inappropriate, or unavailable. | 2291 |  | 15420 | 15420 | Transit Capital | 2026 | 7710 | 7710 | 15420 | Section 5310 | Active | TRUE
Indiana | 3471 | 30.09.01 | LifeSpan | Operating Expenses (Section 5310-25 OTHER Project) | Lifespan Resources Transportation Project for eligible operating expenses to provide transportation for individuals with disabilities to and from day services and work programs and to provide on-demand transportation for seniors and individuals with disabilities for medical trips, including critical care trips such as dialysis, and chemotherapy, as well as trips to the grocery, senior center, library, and post office, with an emphasis on serving low income residents. | Clark, Floyd |  | FALSE | The purpose of this Section 5310 project is to provide transportation for seniors and individuals with disabilities when public transportation is insufficient, inappropriate, or unavailable. | 2291 |  | 181928 | 181928 | Transit Capital | 2026 | 90964 | 90964 | 181928 | Section 5310 | Active | TRUE
Indiana | 3474 | 2200005 | INDOT | Signing Project (New/Modernized) Statewide | This is a statewide signing modernization project in various locations throughout the state, including Clark and Floyd counties. | Clark, Floyd | 2027 | FALSE | Installation of modern traffic signing in various locations statewide. |  | 2680 - Safety Improvements - Indiana | 1569361 | 1569361 | CN | 2027 | 1255489 | 313873 | 1569362 | HSIP-ST | Active | TRUE
Indiana | 3476 | 2401797 | Clark County | Bethany Road CR 403 Intersection Improvements | Intersection improvements at CR 403 and Bethany Road. A roundabout may be considered for this intersection. | Clark | 2032 | FALSE | Clark County has applied for and received HSIP approval for this intersection. The number of serious accidents at this intersection has increased and we are looking to improve the safety of the intersection. |  |  | 6756066 | 6756066 | U | 2027 | 198000 | 22000 | 220000 | HSIP-ST | Active | TRUE
Indiana | 3476 | 2401797 | Clark County | Bethany Road CR 403 Intersection Improvements | Intersection improvements at CR 403 and Bethany Road. A roundabout may be considered for this intersection. | Clark | 2032 | FALSE | Clark County has applied for and received HSIP approval for this intersection. The number of serious accidents at this intersection has increased and we are looking to improve the safety of the intersection. |  |  | 6756066 | 6756066 | PE | 2027 | 247500 | 362300 | 609800 | HSIP-ST | Active | TRUE
Indiana | 3476 | 2401797 | Clark County | Bethany Road CR 403 Intersection Improvements | Intersection improvements at CR 403 and Bethany Road. A roundabout may be considered for this intersection. | Clark | 2032 | FALSE | Clark County has applied for and received HSIP approval for this intersection. The number of serious accidents at this intersection has increased and we are looking to improve the safety of the intersection. |  |  | 6756066 | 6756066 | ROW | 2027 | 495000 | 55000 | 550000 | HSIP-ST | Active | TRUE
Indiana | 3477 | 2500051 | INDOT | AASHTO Safety Software | Purchase AASHTO safety software. | Clark, Floyd | 2030 | FALSE | Purchase AASHTO safety software for internal use. |  |  | 2670000 | 2670000 | PE | 2026 | 696000 | 174000 | 870000 | HSIP-ST | Active | TRUE
Indiana | 3477 | 2500051 | INDOT | AASHTO Safety Software | Purchase AASHTO safety software. | Clark, Floyd | 2030 | FALSE | Purchase AASHTO safety software for internal use. |  |  | 2670000 | 2670000 | PE | 2027 | 360000 | 90000 | 450000 | HSIP-ST | Active | TRUE
Indiana | 3477 | 2500051 | INDOT | AASHTO Safety Software | Purchase AASHTO safety software. | Clark, Floyd | 2030 | FALSE | Purchase AASHTO safety software for internal use. |  |  | 2670000 | 2670000 | PE | 2028 | 360000 | 90000 | 450000 | HSIP-ST | Active | TRUE
Indiana | 3478 | 2500811 | INDOT | SR 62 at Utica Sellersburg Intersection | Intersection improvement on SR 62 at Utica/Sellersburg Road. | Clark | 2031 | FALSE | To improve safety and overall traffic flow on State Road 62. | 3431 |  | 2878272 | 2878272 | ROW | 2027 | 34944 | 8736 | 43680 | HSIP-ST | Active | TRUE
Indiana | 3478 | 2500811 | INDOT | SR 62 at Utica Sellersburg Intersection | Intersection improvement on SR 62 at Utica/Sellersburg Road. | Clark | 2031 | FALSE | To improve safety and overall traffic flow on State Road 62. | 3431 |  | 2878272 | 2878272 | U | 2027 | 80000 | 20000 | 100000 | HSIP-ST | Active | TRUE
Indiana | 3478 | 2500811 | INDOT | SR 62 at Utica Sellersburg Intersection | Intersection improvement on SR 62 at Utica/Sellersburg Road. | Clark | 2031 | FALSE | To improve safety and overall traffic flow on State Road 62. | 3431 |  | 2878272 | 2878272 | PE | 2027 | 332800 | 83200 | 416000 | HSIP-ST | Active | TRUE
Indiana | 3481 | 2600095 | INDOT | District Bridge Project (Rehabilitation) | Bridge repair/rehab, Seymour District, various locations. | Clark, Floyd | 2027 | FALSE | For repair/rehab of bridge locations, throughout Seymour District, as needed. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 1000000 | 1000000 | CN | 2027 | 900000 | 100000 | 1000000 | NHPP | Active | TRUE
Indiana | 3482 | 2600155 | INDOT | I-265 Tree Removal/Clearing | Tree removal and clearing on I-265 from MM 0-12.8, EB and WB. | Clark, Floyd | 2028 | FALSE | This project is to remove overgrown tree/shrubs on state right of way that may become a safety hazard to the motoring public. |  | 2680 - Safety Improvements - Indiana | 304826 | 304826 | PE | 2027 | 26843 | 2983 | 29826 | HSIP-ST | Active | TRUE
Indiana | 3482 | 2600155 | INDOT | I-265 Tree Removal/Clearing | Tree removal and clearing on I-265 from MM 0-12.8, EB and WB. | Clark, Floyd | 2028 | FALSE | This project is to remove overgrown tree/shrubs on state right of way that may become a safety hazard to the motoring public. |  | 2680 - Safety Improvements - Indiana | 304826 | 304826 | CN | 2028 | 247500 | 27500 | 275000 | HSIP-ST | Active | TRUE
Indiana | 3483 | 2600154 | INDOT | I-65 Tree Removal/Clearing | Tree removal on I-65 NB/SB from 0-101 MM. | Clark, Floyd | 2028 | FALSE | This is removal of tree/shrubs from state right of way on I 65 NB/SB to improve safety for the traveling public. |  | 2680 - Safety Improvements - Indiana | 1592738 | 1592738 | PE | 2027 | 128465 | 14273 | 142738 | HSIP-ST | Active | TRUE
Indiana | 3483 | 2600154 | INDOT | I-65 Tree Removal/Clearing | Tree removal on I-65 NB/SB from 0-101 MM. | Clark, Floyd | 2028 | FALSE | This is removal of tree/shrubs from state right of way on I 65 NB/SB to improve safety for the traveling public. |  | 2680 - Safety Improvements - Indiana | 1592738 | 1592738 | CN | 2028 | 1305000 | 145000 | 1450000 | HSIP-ST | Active | TRUE
Indiana | 3485 | 2500451, 2500452 | INDOT | Charlestown SR 3 Drainage Project | The purpose of this project is to extend the functional life of the pavement by addressing functional and structural deficiencies and to improve the drainage system along SR 3 near SR 62 so the road will not flood during standard storm events. The need for this project is evidenced by cracks in the surface layer of the pavement, and by a history of large rain events resulting in closure of SR 3 that limits local mobility. | Clark | 2031 | FALSE | The anticipated outcome of this project is improved drainage and extending the life of the pavement along SR 3. This will improve the mobility of the traveling public. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 14759812 | 14759812 | PE | 2026 | 360000 | 90000 | 450000 | NHPP | Active | TRUE
Indiana | 3485 | 2500451, 2500452 | INDOT | Charlestown SR 3 Drainage Project | The purpose of this project is to extend the functional life of the pavement by addressing functional and structural deficiencies and to improve the drainage system along SR 3 near SR 62 so the road will not flood during standard storm events. The need for this project is evidenced by cracks in the surface layer of the pavement, and by a history of large rain events resulting in closure of SR 3 that limits local mobility. | Clark | 2031 | FALSE | The anticipated outcome of this project is improved drainage and extending the life of the pavement along SR 3. This will improve the mobility of the traveling public. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 14759812 | 14759812 | PE | 2027 | 919850 | 229962 | 1149812 | NHPP | Active | TRUE
Indiana | 3486 | 2200935 | INDOT | Seymour District Raised Pavement Markings (RPM) Refurbishments | District raised pavement markings (RPM) refurbishments in various locations, Seymour District FY 2027. | Clark, Floyd | 2027 | FALSE | To improve the raised pavement markings in various locations in the Seymour District. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 750000 | 750000 | CN | 2027 | 600000 | 150000 | 750000 | HSIP-ST | Active | TRUE
Indiana | 3487 | 2501085 | INDOT | I-65 Median Drain Work at Silver Creek | Replacement of median inlets and drainage on I-65 at Silver Creek. | Clark | 2028 | FALSE | To repair and replace, inlets and drainage structure on I-65 at Silver Creek. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 674841 | 674841 | CN | 2028 | 607357 | 67484 | 674841 | NHPP | Active | TRUE
Indiana | 3499 | 2300464 | INDOT | SR 64 Bridge Over Georgetown Creek | Thin deck overlay on SR 64 bridge over Georgetown Creek, 4.32 miles west of I-64. | Floyd | 2031 | FALSE | The project need is based on the current condition of the structure elements and notable deficiencies in the wearing surface, deck, superstructure, and approach slabs. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 1416411 | 1416411 | PE | 2027 | 280000 | 70000 | 350000 | NHPP | Active | TRUE
Indiana | 3500 | 2600379 | INDOT | SR 62 Bridge Over East Fork | SR 62 bridge replacement over East Fork, 2.09 miles west of 362. | Clark | 2031 | FALSE | The purpose of this project is to correct the deficiencies in the wearing surface, deck, superstructure and substructure to help further protect and extend the service life of the structure. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 4573572 | 4573572 | PE | 2027 | 400000 | 100000 | 500000 | NHPP | Active | TRUE
Indiana | 3501 | 2600608 | INDOT | SR 60 Small Structure and Drain Construction | Small structure and drain construction to correct deficiencies in the structure in order to extend or reset the service life of the asset on SR 60, 5.7 miles west of I-65, Corydon Pike approach. | Clark | 2031 | FALSE | This project is needed based on the current condition of the structure elements. |  | 2676 - Roadway & Bridge Preservation & Rehabilitation - Indiana | 639000 | 639000 | PE | 2027 | 160000 | 40000 | 200000 | NHPP | Active | TRUE