## Sheet1
Project | KIPDA ID | STATE ID | Phase | Fiscal Year | Program | MPO Dedicated Federal Funds Programmed in the TIP | Project Phase Status | Actual or Estimated Date of Authorization | Federal Funding Amount Authorized (If Applicable) | Progress
FLOYD COUNTY
Bridge 51 (Blackiston Mill Road) Replacement Project | 1558 | 1700788 | PE | 2024 | STBG-MPO | 202688 | Federal Funding Authorized | 2024-03-02 | 202688 | PO closed with funds remainin, new PO to be issued. For design reviews during construction.
|  |  | PE | 2027 | STBG-MPO | 11274
|  |  | ROW | 2024 | STBG-MPO | 997312 | Federal Funding Authorized | 2024-05-08 | 997312 | Complete
|  |  | CE | 2026 | STBG-MPO | 675891 | Federal Funding Authorized | 2025-12-11 | 675891 | In progress.
|  |  | CN | 2026 | STBG-MPO | 5632428 | Federal Funding Authorized | 2025-12-11 | 5632428 | Construction in progress and on schedule. Bridge to be complete this year, approaches and demo next year.
|  |  | CN | 2026 | Local Bridge | 1669799 | Federal Funding Authorized | 2025-12-18 | 1669799
Bridge 38 - (Baylor Wissman) Replacement | 3366 | 2401835 | PE | 2026 | Group III | 360000 |  |  | 360000 | PE on schedule, environmental field work complete/early coordination in progress
|  |  | ROW | 2027 | STBG-MPO | 32000
|  |  | CE | 2029 | STBG-MPO | 276000 | Federal Funding Not Yet Authorized
|  |  | CN | 2029 | STBG-MPO | 1852000 | Federal Funding Not Yet Authorized
Baylor Wissman Hilltop | 3367 | 2401834 | PE | 2026 | Group III | 161481 |  |  | 161481 | PE on schedule.
|  |  | ROW | 2029 | HSIP-MPO | 256460 | Federal Funding Not Yet Authorized |  |  |  | KIPDA NOTE: This project needs to get HSIP approval from INDOT. KIPDA will work with the county for application submission
|  |  | CE | TBD | TBD | 257620 | Federal Funding Not Yet Authorized
|  |  | CN | TBD | TBD | 833320 | Federal Funding Not Yet Authorized
Highway 150 Break Highlander Point | 3368 | 2401836 | PE | 2026 | Group III | 315000 |  |  | 315000 | PE on schedule, Coordination with Environmental sub on Community Impact Assessment initiated.
|  |  | CE | 2028 | STBG-MPO | 402029 | Federal Funding Not Yet Authorized
|  |  | CN | 2028 | STBG-MPO | 2680191 | Federal Funding Not Yet Authorized
Charlestown Road Corridor Complete Street Multi Use Trail | 2128 | 1400550 | CE | 2025 | HSIP-State | 435494 |  |  | 435494 | Awaiting last bit of railing for pedestrian bridge to start project termination.
|  |  | CE | 2025 | HSIP-MPO | 264937 | Federal Funding Authorized |  | 264937
|  |  | C | 2025 | HSIP-State | 2903293 |  |  | 2903293
NEW ALBANY
Graybrook Lane Extension | 3102 | 2301310 | PE | 2025 |  | 357109
|  |  | ROW | 2030 | STBG-MPO | 439200 | Federal Funding Not Yet Authorized |  | N/A
|  |  | U | TBD | TBD | 80000 |  |  | N/A | KIPDA NOTE: No federal funding for this phase at this time
|  |  | C | TBD | TBD | 2074949 |  |  |  | KIPDA NOTE: No federal funding for this phase at this time
Intersection of E. Spring St. & Beharrell Ave. | 3136 | 2301550 | PE | 2026 | HSIP-MPO | 252000 | Federal Funding Authorized |  | 252000
|  |  | ROW | 2027 | HSIP-MPO | 400000 |  |  |  | We are working with the consultant on a historical element that has been found.
|  |  | C | 2029 | HSIP-MPO | 1932000 | Federal Funding Not Yet Authorized |  | N/A
Slate Run Road Phase II | 3369 | 2401854 | PE | 2026 | Group III | 200000 | Federal Funding Authorized |  | 200000
|  |  | ROW | 2027 | TA-MPO | 402940 |  |  |  | We are working with the consultant on a historical element that has been found.
|  |  | ROW | 2028 | TA-MPO | 1033060 | Federal Funding Not Yet Authorized |  | N/A
|  |  | CE | 2030 | TA-MPO | 400000 | Federal Funding Not Yet Authorized |  | N/A
|  |  | CN | 2030 | CRP-MPO | 4080000 | Federal Funding Not Yet Authorized |  | N/A
CLARKSVILLE
Progress Way Improvements | 3018 | 2300582 | ROW | 2025 | STBG-MPO | 300000 | Federal Funding Authorized |  | 69815 | Attorneys are working on the last parcel
|  |  | U | 2027 | STBG-MPO | 700000 | Federal Funding Not Yet Authorized |  |  | Certs have been received on most. IAW should have theirs soon.
|  |  | CE | 2027 | STBG-MPO | 336000 | Federal Funding Not Yet Authorized |  |  | The letting date has moved to February 2026
|  |  | C | 2027 | STBG-MPO | 3200000 | Federal Funding Not Yet Authorized
Riverside Drive Reconstruction (Only fill out "Project Phase Status" Column & "Progress" Column) | 2393 | 1700725 | - | 2023 | - | - | Federal Funding Authorized | - | - | Waiting on the flood control gate to be manufactured.
CLARK COUNTY
Henryville Sidewalk | 3180 | 2301302 | PE | 2025 | PROTECT (TA) | 144000 | Federal Funding Authorized |  | 144000
|  |  | PE | 2026 | Group III | 100000 | Federal Funding Authorized |  | 100000 | Environmental will be sent to INDOT in August. Once Environmantal is reviewed we will begin the ROW process.
|  |  | ROW | 2027 | INDOT Funds | 520661
|  |  | U | 2028 | INDOT Funds | 45000 | Federal Funding Not Yet Authorized |  | N/A
|  |  | CE | 2029 | INDOT Funds | 140400 | Federal Funding Not Yet Authorized |  | N/A
|  |  | CN | 2029 | INDOT Funds | 1072373 | Federal Funding Not Yet Authorized |  | N/A
Small Structure Inventory Study | 3330 | 2401845 | Planning | 2025 | Group III | 200000 | Federal Funding Authorized |  | 200000 | Project complete. Final invoice and closeout will be ready by August.
CR-311 and Sellersburg Improvements | 3364 | 2401840 | PE | 2026 | Group III | 600000 | Federal Funding Authorized |  | 600000 | Preliminary Engineering report will be sent to the County in August
|  |  | PE | 2026 | CMAQ-MPO | 142733 | Federal Funding Authorized |  | 142733
|  |  | PE | 2027 | CMAQ-MPO | 50341
|  |  | ROW | 2028 | CMAQ-MPO | 500000 | Federal Funding Not Yet Authorized |  | N/A
|  |  | ROW | 2029 | CMAQ-MPO | 500000 | Federal Funding Not Yet Authorized |  | N/A
|  |  | U | 2030 | CMAQ-MPO | 500000 | Federal Funding Not Yet Authorized |  | N/A
Memphis Blue Lick Roadway Improvements | 3365 | 2401839 | Planning | 2026 | Group III | 100000 | Federal Funding Authorized |  | 100000 | Preliminary Draft report was presented to County for review. Final should be ready by September.