## Project Updates
Project | KIPDA ID | STATE ID | Phase | Program | MPO Dedicated Federal Funds | Currently Programmed Fiscal Year | Has this phase been authorized? (Yes or No) | Are you at least 90% confident that this phase can be obligated in the current fiscal year (FY26)? (Yes or No) | Are you at least 90% confident that this phase can be obligated in the upcoming fiscal year (FY27)? (Yes or No) | Need a phase shift? (Yes or No) | If so, what fiscal year will you need to shift to? | Project Sponsor Notes (Optional)
LOUISVILLE METRO
AB Sawyer Greenway Shared Use Path | 1662 | 5-529.00 | Construction | STBG-MPO | 3555600 | 2026 | No | No | Yes | Yes | FY27
Bicycle & Pedestrian Education, Encouragement, Enforcement & Evaluation | 337 | 5-965.15 | Program | STBG-MPO | 150000 | 2026+ | Yes
Cooper Chapel Rd. Phase 3 | 223 | 05-404.01 | Design | STBG-MPO | 65080 | 2024 | Yes
|  |  | Right of Way | STBG-MPO | 779400 | 2024 | Yes
|  |  | Utilities | STBG-MPO | 2098000 | 2026 | No | No | Yes | Yes | FY27
|  |  | Construction | STBG-MPO | 18153600 | 2027 | No | No | No | Yes | FY28
I-65/Brook St Ramp | 224 | 05-378.10 & 05-80521.00 | Utilities | STBG-MPO | 640000 | 2026 | No | No |  | No |  |  | KIPDA Comment: It does not look like this project received any funding via the KYTC six-year highway plan, so we probably need to remove these funds from this project to be utilized in the upcoming CFP
Kentuckiana Air Education | 369 | 5-244.00 | Program | STBG-MPO | 200000 | 2025+
North Hubbards Ln. | 3233 | 5-479.10 | Construction | STBG-MPO | 5809589 | 2026 | No | No | Yes | Yes | FY27
Northeast Louisville Loop MET, Section 2 Beckley Station to Bircham Rd. | 2269 | 5-3030.20 | Construction | STBG-MPO | 2080000 | 2025 | Yes
Olmsted Parkways Multi-Use Path System Section 1 | 2622 | 5-3709.00 | Construction | STBG-MPO | 2750000 | 2026 | No | No | Yes | Yes | FY27 | Awaiting fully executed ROW funds MOA since 9/2/25
Olmsted Parkways Multi-Use Path System Section 2 | 2623 | 5-3709.00 | ROW | STBG-MPO | 1451000 | 2026 | No | No | Yes | Yes | FY27 | Check cost estimates. Additional funds may be needed.
|  |  | Utilities | STBG-MPO | 100000 | 2026 | No | No | No | Yes | FY28
Olmsted Parkways Multi-Use Path System Section 3 | 2624 | 5-3709.00 | Design | STBG-MPO | 111111 | 2026 | Yes
|  |  | ROW | STBG-MPO | 942000 | 2026 | No | Yes | Yes | No |  | Metro plans to request programmed FY26 ROW funds this summer
Olmsted Parkways Multi-Use Path System Section 4 | 2625 | 5-506.00 | ROW | STBG-MPO | 1977000 | 2026 | No | Yes |  | No |  | Metro plans to request all ROW funds programmed for FY26
|  |  | Utilities | STBG-MPO | 100000 | 2027 | No |  | Yes | No
Olmsted Parkways Multi-Use Path System Section 5 | 2626 | 5-506.00 | ROW | STBG-MPO | 2146000 | 2027 | No | Yes |  | No |  | Metro plans to request all ROW funds programmed for FY26
Olmsted Parkways Multi-Use Path System Section 6 | 2627 | 5-506.60 | ROW | STBG-MPO | 53600 | 2025 | Yes
|  |  | Utilities | STBG-MPO | 515200 | 2027 | No | Yes |  | No |  | Metro plans to request all ROW funds programmed for FY26
Olmsted Parkways Multi-Use Path System Section 7 | 2628 | 5-506.70 | ROW | STBG-MPO | 111200 | 2025 | Yes
|  |  | Utilities | STBG-MPO | 145200 | 2027 | No |  | Yes | No
One-Way Street Conversion to Two-Way Phase 1 | 1809 | 5-470.00 | Design | STBG-MPO | 80000 | 2025 | Yes
|  |  | Construction | STBG-MPO | 10874000 | 2026 | No | Yes |  | No |  | Finalizing PDC 7/28/2026
River Road Widening to Zorn Ave | 163 | 5-91.02 | Utilities | STBG-MPO | 2800000 | 2024 | Yes
|  |  | Construction | STBG-State | 4784907 | 2026 | Yes
|  |  | Construction | STBG-MPO | 18929715 | 2026 | Yes
River Road Multi-Modal Improvements | 2540 | 5-3217.00 | Construction | TA-MPO | 2200000 | 2024 | yes
|  |  | Construction | STBG-MPO | 400000 | 2026 | Yes
Stony Brook Drive Sidewalk Connector | 2594 | 5-571.00 | Construction | STBG-MPO | 562000 | 2026 | Yes
Buechel Bank Road | 381 | 5-8001.00 | Utilities | STBG-MPO | 1600000 | 2026 | No | No | Yes | Yes | FY27
|  |  | Construction | STBG-MPO | 6005000 | 2027 | No | No
Northeast Louisville Loop MET, Section 3 Bircham Rd. to Beckley Creek Park | 2270 | 5-3030.30 | Design | STBG-MPO | 445000 | 2026 | No | No | Yes | Yes | FY27 |  | KIPDA Comment: KIPDA staff would not recommend a phase shift exception request for this design phase. Needs to get authorized this year or funding should be shifted to other project needs within KIPDA's funding program
|  |  | ROW | STBG-MPO | 636000 | 2026 | No | No | Yes | Yes | FY27
|  |  | Utilities | STBG-MPO | 20000 | 2027 | No | No | No | No
|  |  | Construction | STBG-MPO | 3200000 | 2029 | No | No | No | No
River Road Extension | 1338 | 5-512.00 | Construction | STBG-MPO | 9600000 | 2026 | No | No |  | Yes
Reimagine 9th Street | 2733 | 5-80324.00 | Construction | STBG-MPO | 3896000 | 2026 | No | Yes |  | No |  |  | KIPDA Comment: This project obviously has other funding, but I have only listed KIPDA's MPO-dedicated funding portion here
Blanton Lane Sidewalk | 2920 | 5-3004.00 | ROW | TA-MPO | 506880 | 2025 | Yes
|  |  | Construction | TA-MPO | 1159200 | 2026 | No | No | No | Yes | FY28
Crums Lane Sidewalk Phase 1 | 2896 | 5-3011.00 | ROW | TA-MPO | 352978 | 2025 | Yes
|  |  | Construction | TA-MPO | 596120 | 2026 | No | No | No | Yes | FY28
Gagel Avenue Sidewalk | 2921 | 5-3040.00 | ROW | TA-MPO | 440000 | 2024 | Yes
|  |  | Construction | TA-MPO | 1400000 | 2026 | No | No | No | Yes | FY28
Louisville Loop Shared Use Path - McNeely Lake Segment | 2539 | 5-3034.00 | Design | TA-MPO | 242689 | 2025 | Yes
|  |  | Design | STBG-MPO | 350000 | 2025 | Yes
|  |  | Construction | TA-MPO | 5040000 | 2027 | No | No | No | Yes | FY28
Bernheim Lane Sidewalk and Road Reconfiguration | 2895 | 5-3002.00 | Construction | TA-MPO | 688000 | 2025 | Yes
Dodge Gap Jefferson Memorial Forest - Louisville Loop Shared Use Path | 2087 | 5-523.00 | Design | CRP-MPO | 98354 | 2025 | Yes
|  |  | ROW | CRP-MPO | 111000 | 2026 | No | No | Yes | Yes | FY27
|  |  | Utilities | CRP-MPO | 25000 | 2027 | No |  | Yes | No
Northeast Louisville Loop Section II (Eastwood Cut-off) | 2116 | 5-525.00 | Design | CRP-MPO | 32000 | 2024 | Yes
|  |  | Construction | CRP-MPO | 826000 | 2025 | Yes | [5 empty] | KIPDA Comment: Only authorized $480,000 of CRP funds. Extra funds remaining with project until next CFP. Need an update if any remaining funds needed.
Ohio River Levee Trail Phase III | 1109 | 5-505.00 | Design | CRP-MPO | 220000 | 2026 | No | Yes |  | No
|  |  | Construction | CRP-MPO | 6463000 | 2026 | No | No | Yes | Yes | FY28
Pond Creek Jefferson Memorial Forest - Louisville Loop Shared Use Path | 2086 | 5-522.00 | Design | STBG-MPO | 135000 | 2024 | Yes
|  |  | ROW | CRP-MPO | 680000 | 2025 | Yes
|  |  | Utilities | CRP-MPO | 55000 | 2027 | No
Westport Road Sidewalk through I-265 Interchange | 3121 | 5-598.00 | Design | CRP-MPO | 45000 | 2025 | Yes
|  |  | Construction | CRP-MPO | 895000 | 2026 | No | No | No | Yes | FY28
Medora Jefferson Memorial Forest (IMF) - Louisville Loop Shared Use Path | 2092 | 5-524.00 | Construction | TA-MPO | 4305000 | 2026 | No | No | Yes | Yes | FY27
Northeast Louisville Loop MET Section 4 Beckley Creek Park to Eastwood Cuttoff | 2271 | 5-3030.40 | Construction | STBG-MPO | 1103520 | 2026 | No | No | Yes | Yes | FY27
Ohio River Valley NE Bike/Ped Improvements Phase 1 (Louisville Loop) | 2979 | 5-3036.00 | Construction | STBG-MPO | 640000 | 2026 | No | No | Yes | Yes | FY27
|  |  | Construction | CRP-MPO | 3760000 | 2029 | No | No |  | No
Ohio River Valley NE Bike/Ped Improvements Phase II (Louisville Loop) | 2980 | 5-584.00 | ROW | CRP-MPO | 88000 | 2026 | No | No | Yes | Yes | FY27 | ROW funds and Utilities funds will need a phase shift to FY27
|  |  | Utilities | CRP-MPO | 28000 | 2026 | No | No | Yes | Yes | FY27
|  |  | Construction | CRP-MPO | 2696000 | 2028 | No | No | No | No
Dixie Highway Streetscape - Maple to Garland | 3308 | 5-478.81 | ROW | CRP-MPO | 48000 | 2026 | Yes
|  |  | Construction | CRP-MPO | 1743000 | 2026 | No | No | No | Yes | FY28
South Hubbards Lane | 3024 | 5-479.20 | Construction | TA-MPO | 500000 | 2027 | No | No | Yes | No
LaGrange & Whipps Mill Intersection Improvements | 3126 |  | Construction | STBG-MPO | 1123000 | 2026
JEFFERSONTOWN
Bluegrass Commerce Park Bicycle/Pedestrian Trail Phase II | 2084 | 05-543.00 | Construction | STBG-MPO | 2130000 | 2025 | Yes |  |  | No
Galene Drive/Sprowl Road Collector Extension | 3113 |  | Planning | STBG-MPO | 264000 | 2026 | [5 empty] | relinquish funds
|  |  | Design | STBG-MPO | 440000 | 2027 | No | No |  |  |  | relinquish funds
|  |  | ROW | STBG-MPO | 880000 | 2028 | No | No | No |  |  | relinquish funds
|  |  | Utilities | STBG-MPO | 440000 | 2029 | No | No | No |  |  | relinquish funds
|  |  | Construction | STBG-MPO | 4400000 | 2029 | No | No | No |  |  | relinquish funds
Good Samaritan Bicycle & Pedestrian Trail Connector | 2082 | 05-486.00 | Construction | STBG-MPO | 1460000 | 2026 | No | No | No | Yes | 2028 | Still design and utility work to figure out
Ruckriegel Parkway Sidewalk Improvement | 2619 | 05-198.00 | Construction | STBG-MPO | 529008 | 2027 | No | No |  |  |  | plan to update cost estimate as part of this call for projects cycle
Watterson Trail Phase 2 | 1583 | 05-518.00 | Utilities | STBG-MPO | 352000 | 2026 | No | No | Yes | Yes | 2027 | ROW close to being fully cleared
|  |  | Construction | STBG-MPO | 1232000 | 2026 | No | No
Billtown-Eastvie w Collector Extension | 3111 |  | Design | STBG-MPO | 310000 | 2026 | [5 empty] | Relinquish funds
|  |  | ROW | STBG-MPO | 176000 | 2027 | No | No |  |  |  | Relinquish funds
|  |  | Utilities | STBG-MPO | 528000 | 2028 | No | No |  |  |  | Relinquish funds
|  |  | Construction | STBG-MPO | 1056000 | 2029 | No | No |  |  |  | Relinquish funds
MIDDLETOWN
South Madison Avenue | 2320 | 5-3214.00 | Construction | STBG-MPO | 438344 | 2026 | No | No | Yes | Yes | FY27 | The construction phase is currently programmed in FY26. The City is currently waiting for a punch list from KYTC before the project can be put out to bid. Because the phase has not yet been authorized and the City is not 90% confident that it can be obligated in FY26, a phase shift to FY27 is requested.
KYTC
English Station Rd. | 188 | 5-353.00 | Design | STBG-MPO | 256000 | 2026 | Yes |  |  | No |  | authorized 3 11 26
|  |  | Utilities | STBG-MPO | 2800000 | 2026 | Yes |  |  | No |  | authorized 9 22 25 yes $4000 over | Looks like an additional $4,000 federal was authorized beyond what was programmed
|  |  | Construction | STBG-MPO | 11368000 | 2026 | No | No | yes | no |  | letting scheduled for Nov 2027. authorization expected soon.
KY 1931 Dixie Hwy to Doss HS | 2214 | 5-536.00 | Right of Way | STBG-MPO | 1220000 | 2026 | No | No | yes | yes | fy27 | may revise fm ROW to Utility phase funds
|  |  | Construction | STBG-MPO | 10780000 | 2028 | No | No | yes | yes | fy27 | letting scheduled for Nov 2027. authorization expected soon.
US 42 Jeff/Oldham Line to Ridgemoor Dr | 1271 | 5-441.01 | Design | STBG-MPO | 448000 | 2025 | Yes |  |  | No |  | authorized 7 10 25
|  |  | Utilities | STBG-MPO | 1520000 | 2026 | No | no | no | yes | fy28 | letting est fy29
|  |  | Construction | STBG-MPO | 5020000 | 2028 | No | No | no | no |  | letting est fy29
KY 2055 Mt Holly sidewalk | 3042 | 5-80110.00 | Design | STBG-MPO | 120000 | 2024 | Yes |  |  | No |  | authorized 8 30 24
|  |  | Design | STBG-MPO | 212000 | 2026 | yes | yes |  | no |  | authorized 7 23 26
|  |  | ROW | STBG-MPO | 24000 | 2026 | No | No | yes | yes | fy28 | expect phase cost increase
|  |  | Utilities | STBG-MPO | 24000 | 2026 | No | No | yes | yes | fy28 | expect phase cost increase
|  |  | Construction | STBG-MPO | 120000 | 2026 | No | No | No | yes | fy29 | expect phase cost increase
KY 1065 Outer Loop | 436 | 5-80203.00 | Planning | STBG-MPO | 200000 | 2024 | Yes |  |  | No |  | authorized 9 16 24
|  |  | Planning | STBG-MPO | 150000 | 2025 | Yes |  |  | No |  | authorized 5 15 25
KY 1932 Chenoweth Lane | 213 | 5-531.00 | Construction | STBG-MPO | 3696000 | 2025 | Yes |  |  | No |  | authorized only $3,696,000 on 12 22 26
US 42 Safety and Mobility Improvements from the Harrods Creek Bridge to River Road | 230 | 5-972.00 | Design | STBG-MPO | 800000 | 2024 | Yes |  |  | No |  | authorized 2 28 24
|  |  | Design | STBG-MPO | 128000 | 2026 | Yes |  |  | No |  | authorized 5 7 26
|  |  | ROW | STBG-MPO | 664000 | 2026 | No | no | yes | yes | FY27 | expect phase cost increase
|  |  | Utilities | STBG-MPO | 2080000 | 2026 | No | No | No | yes | fy28 | expect phase cost increase
|  |  | Construction | STBG-MPO | 6008000 | 2027 | No | No | No | yes | fy28 | expect phase cost increase
KY 2050 Herr Lane | 3069 | 5-80200.00 | Design | STBG-MPO | 335200 | 2024 | Yes |  |  | No |  | authorized 9 16 24
|  |  | ROW | STBG-MPO | 44000 | 2026 | No | no | yes | yes | fy27 | in final design
|  |  | Utilities | STBG-MPO | 128000 | 2026 | No | no | no | yes | fy28 | in final design
|  |  | Construction | STBG-MPO | 1728000 | 2027 | No | No | no | yes | fy28 | in final design
KY 864 Beulah Church Rd | 1879 | 5-481.00 | Design | STBG-MPO | 250000 | 2026 | Yes |  |  | no |  | $228,080 authorized, no need for $21,920 | Looks like $228,080 was authorized. Need for remaining $21,920?
|  |  | Utilities | STBG-MPO | 200000 | 2026 | no | yes |  | no |  | expected in Sept 2026 letting
|  |  | Construction | STBG-MPO | 17288000 | 2026 | no | yes |  | no |  | expected in Sept 2026 letting | Still on for August letting?
MT. WASHINGTON
Historic Multi-Use Trail Segment C | 2479 | 5-3216.00 | Construction | STBG-MPO | 3169814 | 2026 | No | no | yes | yes | 2027 | RW has entered condemnation on several properties
|  |  | Construction | STBG-State | 118000 | 2026 | No | no | yes | yes | 2027 | RW has entered condemnation on several properties
OLDHAM COUNTY
Mattingly/Old LaGrange Rd Trail | 2981 | 5-589.00 | Design | STBG-MPO | 260000 | 2026 | Yes |  |  |  |  | supplemental agreement for final design ($208,000 federal funds) approved by Fiscal Court 7/21/2026 awaiting final execution by KYTC
|  |  | ROW | STBG-MPO | 139000 | 2026 |  | No | Yes |  |  | Current RW estimate is $600K. Need ROW Funding increase
|  |  | Utilities | STBG-MPO | 139000 | 2027 |  | No | No | Yes | 29
|  |  | Construction | STBG-MPO | 500000 | 2028 | no | No | No | Yes | 29 | Current construction estimate is $2.4M. Need C increase
LaGrange Underpass West of LaGrange | 321 | 5-434.00 | Design | STBG-MPO | 120000 | 2026 | yes | yes | N/A | no
|  |  | Utilities | STBG-MPO | 1012000 | 2025 | yes |  |  | no
|  |  | Utilities | STBG-MPO | 2088000 | 2026 | Yes? - how much was actually authorized? $688,000? | yes | N/A |  |  | Will find out from Carl Jenkins - please standby
|  |  | Construction | STBG-MPO | 22625000 | 2026 | Yes |  |  |  |  | Constrtuction contract awarded and Pre-Construction conference mtg held.
Old LaGrange Road Improvements Oldham County Bicycle & Pedestrian Trail | 2175 | 5-410.01 | Right of Way | STBG-MPO | 239676 | 2024 | yes |  |  | no
|  |  | Right of Way | STBG-State | 340324 | 2024 | yes |  |  | no |  | ROW acquisition on-going however there may be concern with (or effect of) current/new ROW acquisition procedures
|  |  | Utilities | STBG-MPO | 750000 | 2026 | no |  |  |  |  | discuss adjusting based on status/note above
|  |  | Construction | STBG-MPO | 1458383 | 2026 | no |  |  |  |  | discuss adjusting based on status/note above
KY 22/Clore Lane Intersection Improvements | 3141 | 5-596.00 | Design | STBG-MPO | 188889 | 2024 | yes |  |  | no
|  |  | Design | STBG-MPO | 196569 | 2026 | yes - only authorized $68,569. Anticipate need for any more design funding? |  | N/A |  |  | supplemental agreement for final design ($128,000 federal funds) approved by Fiscal Court 7/21/2026 awaiting final execution by KYTC
|  |  | ROW | STBG-MPO | 733333 | 2026 | no | no | yes | yes | 2027
|  |  | Utilities | STBG-MPO | 622222 | 2026 | no | no | no | yes | 2027
|  |  | Construction | STBG-MPO | 1888889 | 2028 | no | no | no | yes | 2029
Kenwood Road | 2615 | 5-588.00 | Design | STBG-MPO | 325000 | 2024 | yes |  |  | no
|  |  | ROW | STBG-MPO | 490000 | 2026 | no | No | No | Yes | 2027 | Concern with current/new ROW acquisition procedures
|  |  | Utilities | STBG-MPO | 664063 | 2026 | no | No | No | Yes | 2028
|  |  | Construction | STBG-MPO | 2003125 | 2027 | no | No | No | Yes | 2029
UNIVERSITY OF LOUISVILLE
2nd Street / 3rd Street / Museum Drive Intersection and Brandeis Avenue Pedestrian Improvements | 2982 | 5-581.00 | Design | STBG-MPO | 272800 | 2025 | Yes |  |  | No |  | Phase II design to be submitted for comments by December 2026.
|  |  | Utilities | STBG-MPO | 480000 | 2026 | No | no | yes | yes | 2027 | Working to remove utilties along Brandeis. While I believe we can begin the process to initiate the utilitiy relocation, I do not believe it can make it through all processes needed before the end of the fiscal year.
|  |  | Construction | STBG-MPO | 4112000 | 2026 | No | No | yes | Yes | 2027 | Slated for a late mid winter advertisement
University of Louisville Pedestrian Improvements - Lighting | 2225 | 5-3218.00 | Construction | STBG-MPO | 589640 | 2024 | Yes |  |  | No |  | Performing punchlist work. Initial Construction complete
University of Louisville Pedestrian Improvements - ADA Curb Cuts & Ramps | 2585 | 5-3220.00 | Construction | STBG-MPO | 534568 | 2025 | Yes |  |  | No |  | Performing punchlist work. Initial Construction complete
TARC
Bus Stop Improvements at Transit Node Eastern Parkway and Preston/Shelby Street | 3129 |  | Design | STBG-MPO | 50000 | 2026 | Yes |  |  | No
|  |  | Construction | CRP-MPO | 121165 | 2026 | Yes |  |  | No |  | For all of 3129: Minor adjustments to the locations of improvements based on TARC's new route structure.
Bus Stop and Access Improvements - M. Ali and Chestnut Street Corridor, KY | 3137 |  | PE | CRP-MPO | 100000 | 2026 | Yes |  |  | No
|  |  | Construction | STBG-MPO | 84512 | 2026 | Yes |  |  | No
|  |  | Construction | CRP-MPO | 138375 | 2026 | Yes |  |  | No |  | For all of 3137: Minor adjustments to the locations of improvements based on TARC's new route structure.
Louisville Downtown Transit Center Study | 3403 |  | Planning | STBG-MPO (IN) | 100000 | 2025 | Yes |  |  | No |  | Site assessments complete, Categorical Exemption worksheets near complete, ~50% expended.
|  |  | Planning | STBG-MPO (KY) | 400000 | 2025 | Yes |  |  | No
Louisville Downtown Transit Center | 3416 |  | Design | STBG-MPO (KY) | 1000000 | 2027 | No | No